## Version Control
© ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
| Version No. | Date | Author | Change Description
| D 0.1 | 2012-01-31 | Sachin Mulay | Initial template definition - draft
| I1.0 | 2012-02-21 | Priya Ekbote | Issued
| D 1.1 | 2012-03-16 | Sachin Mulay | Modified the template format
| D 1.2 | 2012-10-08 | Sachin Mulay | Added Guideline tab
| I 2.0 | 2012-10-08 | Priya Ekbote | Issued
| D 2.1 | 2012-10-17 | Sachin Mulay | Added "Projects" Sheet & updated guide line tab

## Guideline
© ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
1. Maintain the project level data in projects sheet
2. Create 1 sheet per month and maintain projects worked on by the resources on weekly basis within that month
3. Make a provision to identify leaves/Holidays per week
4 Maintain capacity utilisation per month based on billable and non-billable work

## Projects
Project Name | Project Type | Start Date | End Date | Status | No. of resources | FTE | Subgroup | Project Manager | CMMi Implementation
Messmo | Customer Managed |  |  | Inprogress | 4 | 3.25 | PHP | Rajnesh | No
Silverdepot | Customer Managed |  |  | Inprogress | 1 | 1 | PHP | Kiran Vidhate | No
Hitched | Customer Managed |  |  | Inprogress | 3 | 3 | ASP.Net | Kiran Vidhate | No
Kidspot | Customer Managed |  |  | Inprogress | 2 | 2 | ASP.Net | Rajnesh | No
Roodlane Medical | Customer Managed |  |  | Inprogress | 2 | 2 | ASP.Net | Amod | No
VMComplete | Customer Managed |  |  | Inprogress | 1 | 1 | PHP | Kiran Vidhate | No
Intenix | Customer Managed |  |  | Inprogress | 5 | 5 | ASP.Net | Amod | No
SelfIT | Aress Managed |  |  | Inprogress | 4 | 3.5 | ASP.Net | Sachin | No
SelfIT - Event Mgmt | Aress Managed |  |  | Inprogress | 2 | 1.25 | iPhone | Sachin | Yes
DoIT | Aress Managed |  |  | Inprogress | 3 | 2.5 | ASP.Net | Sachin | No
Talaeo | Customer Managed |  |  | Inprogress | 2 | 2 | ASP.Net | Kiran Vidhate | No
Right Consultants | Customer Managed |  |  | Inprogress | 2 | 1.25 | ASP.Net | Rupal | No
Founders42 | Aress Managed |  |  | Inprogress | 2 | 2 | PHP | Rupal | No
Meno | Customer Managed |  |  | Inprogress | 1 | 1 | ColdFusion | Rajnesh | No
Brainhost | Customer Managed |  |  | Inprogress | 3 | 3 | PHP | Pawankumar | No
ESCt | Customer Managed |  |  | Inprogress | 4 | 4 | ASP.Net | Jyoti | No
Tearfunds | Aress Managed |  |  | Inprogress | 2 | 2 | PHP | Jyoti | No
Tearfunds - Android | Aress Managed |  |  | Inprogress | 2 | 1.25 | Android | Jyoti | Yes
CCCHealth | Customer Managed |  |  | Inprogress | 2 | 1.25 | ASP.Net | Sachin | No
System9 | Customer Managed |  |  | Inprogress | 2 | 2 | ASP.Net | Rajnesh | No
PCA | Aress Managed |  |  | Inprogress | 1 | 1 | ASP.Net | Jyoti | No
Co-create News stand app | Aress Managed |  |  | Future | 1 | 1 | iPhone | Rajnesh | No
Credit Union - DNN | Aress Managed |  |  | Inprogress | 1 | 1 | ASP.Net | Sachin | No
Crisis Action | Aress Managed |  |  | Inprogress | 2 | 1.25 | PHP | Kiran Vidhate | No
Education Leads | Aress Managed |  |  | Inprogress | 1 | 1 | ASP.Net | Kiran Vidhate | No
Beverage Container Recycling | Aress Managed |  |  | Inprogress | 2 | 2 | ASP.Net | Kiran Vidhate | No
PPL Tracking | Aress Managed |  |  | Inprogress | 1 | 1 | PHP | Rupal | No
WYNP | Aress Managed |  |  | Inprogress | 1 | 1 | PHP | Jyoti | No
InfoAktiv | Customer Managed |  |  | Inprogress | 1 | 1 | ASP.Net | Sudhir | No
MiniSport | Aress Managed |  |  | Inprogress | 2 | 2 | PHP | Pawankumar | No
ESN | Aress Managed |  |  | Inprogress | 5 | 4.5 | ASP.Net | Jyoti | Yes
Note on H1: arees software: ASP.NET PHP Mobile - iphone Mobile - android Mobile - cross platform

## Oct 2012
© ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
[6 empty] | Where | xyz, abcd , pqr - Are the projects on which they are working
Resource | Week1 <6 days > | Week2 <5 days> | Week3 <6 days> | Week4 <6 days> | Week5 <3 days>
Priya | SM | SM | SM | SM | SM
Jyoti | PDM | PDM | PDM | PDM | PDM |  | Un Billed
Sachin M | PM | PM | PM | PM | PM |  | Partially billed
Anjali | BA | BA | BA | BA | BA |  | Completely billed
Krushna | Messmo | Messmo | Messmo | Messmo | Messmo
Vijay | Messmo | Messmo | Messmo | Messmo | Messmo
Mahendra | Messmo | Messmo | Messmo | Messmo | Messmo
Sandip | Silverdepot | Silverdepot | Silverdepot | Silverdepot | Silverdepot
Kiran | Hitched | Hitched | Hitched | Hitched | Hitched
Nirav | Hitched | Hitched | Hitched | Hitched | Hitched
Shrikant | Hitched | Hitched | Hitched | Hitched | Hitched
Meenal | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Mrunmayi | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Kavita | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Manisha | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Vaishali | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Nahid | Roodlane | Roodlane | Roodlane | Roodlane | Roodlane
Deepali | Roodlane | Roodlane | Roodlane | Roodlane | Roodlane
Kamal | VMComplete, F42 | VMComplete, F42 | VMComplete, F42 | VMComplete, F42 | VMComplete, F42
Sachin K | Intenix | Intenix | Intenix | Intenix | Intenix
Amod | Intenix | Intenix | Intenix | Intenix | Intenix
Swapna | Intenix | Intenix | Intenix | Intenix | Intenix
Poonam S | Intenix | Intenix | Intenix | Intenix | Intenix
Pankaj Pawar | Intenix | Intenix | Intenix | Intenix | Intenix
Aakriti | Intenix | Intenix | Intenix | Intenix | Intenix
Nitin | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web
Chinmay | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web
Rajnesh | SelfIT - Event Mgmt | SelfIT - Event Mgmt | SelfIT - Event Mgmt | SelfIT - Event Mgmt | SelfIT - Event Mgmt
Anand | DoIT | DoIT | DoIT | DoIT | DoIT
Tushar | DoIT | DoIT | DoIT | DoIT | DoIT
Niranjan | Talaeo | Talaeo | Talaeo | Talaeo | Talaeo
Ananda | Right Consultants | Right Consultants | Right Consultants | Right Consultants | Right Consultants
Gaurav | Meno | Meno | Meno | Meno | Meno
Pawankumar | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost
Sunil Game | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost
Devesh | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost
Sudhir | ESCt | ESCt | ESCt | ESCt | ESCt
Sachin Shinde | ESCt | ESCt | ESCt | ESCt | ESCt
Reshma | ESCt | ESCt | ESCt | ESCt | ESCt
Megha | ESCt | ESCt | ESCt | ESCt | ESCt
Prasad | Tearfunds | Tearfunds | Tearfunds | Tearfunds | Tearfunds
Chanchal | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android
Tejas | Tearfunds | Tearfunds | Tearfunds | Tearfunds | Tearfunds
Madhav | CCCHealth | CCCHealth | CCCHealth | CCCHealth | CCCHealth
Hemant Atre | System9 | System9 | System9 | System9 | System9
Lalit | System9 | System9 | System9 | System9 | System9
Mandar | PCA | PCA | PCA | PCA | PCA
Rakesh B | PCA | PCA | PCA | PCA | PCA
Pankaj K | DNN | DNN | DNN | DNN | DNN
Ashok Daware | Crisis Action | Crisis Action | Crisis Action | Crisis Action | Crisis Action
Pravin | BCR | BCR | BCR | BCR | BCR
Sarvesh | BCR | BCR | BCR | BCR | BCR
Supriya | PPL | PPL | PPL | PPL | PPL
Rupal | WYNP | WYNP | WYNP | WYNP | WYNP
Mangesh | InfoAktiv | InfoAktiv | InfoAktiv | InfoAktiv | InfoAktiv
Pratik | MiniSport | MiniSport | MiniSport | MiniSport | MiniSport
Jagdish | MiniSport | MiniSport | MiniSport | MiniSport | MiniSport
Abhijit | ESN | ESN | ESN | ESN | ESN
Bhagyashree | ESN | ESN | ESN | ESN | ESN
Sameer M | ESN | ESN | ESN | ESN | ESN
Rajesh W | Designer | Designer | Designer | Designer | Designer
Ravi S | Designer | Designer | Designer | Designer | Designer
Kavita | Designer | Designer | Designer | Designer | Designer
Sunil Raut | Designer | Designer | Designer | Designer | Designer
Santoshkumar Pande | Designer | Designer | Designer | Designer | Designer
Dynaneshwar | QA | QA | QA | QA | QA
Tatyasaheb Patil | QA | QA | QA | QA | QA
Jayvant | QA | QA | QA | QA | QA
Amol Bansod | QA | QA | QA | QA | QA
Tonny | QA | QA | QA | QA | QA
Abhishek Patel | QA | QA | QA | QA | QA

## Nov 2012
© ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
[6 empty] | Where | xyz, abcd , pqr - Are the projects on which they are working
Resource | Week1 <3 days > | Week2 <6 days> | Week3 <6 days> | Week4 <6 days> | Week5 <3 days>
Priya | SM | SM | SM | SM | SM
Jyoti | PDM | PDM | PDM | PDM | PDM |  | Un Billed
Sachin M | PM | PM | PM | PM | PM |  | Partially billed
Anjali | BA | BA | BA | BA | BA |  | Completely billed
Krushna | Messmo | Messmo | Messmo | Messmo
Vijay | Messmo | Messmo | Messmo | Messmo
Mahendra | Messmo | Messmo | Messmo | Messmo
Sandip | Silverdepot | Silverdepot | Silverdepot | Silverdepot
Kiran | Hitched | Hitched | Hitched | Hitched
Nirav | Hitched | Hitched | Hitched | Hitched
Shrikant | Hitched | Hitched | Hitched | Hitched
Meenal | Kidspot | Kidspot | Kidspot | Kidspot
Mrunmayi | Kidspot | Kidspot | Kidspot | Kidspot
Kavita | Kidspot | Kidspot | Kidspot | Kidspot
Manisha | Kidspot | Kidspot | Kidspot | Kidspot
Vaishali | Kidspot | Kidspot | Kidspot | Kidspot
Nahid | Roodlane | Roodlane | Roodlane | Roodlane
Deepali | EnergiseYou | EnergiseYou | On leave | On leave
Kamal | VMComplete, F42 | VMComplete, F42 | VMComplete | VMComplete
Sachin K | Intenix | Intenix | Intenix | Intenix
Amod | Intenix | Intenix | Intenix | Intenix
Swapna | Intenix | Intenix | Intenix | Intenix
Poonam S | Intenix | Intenix | Intenix | Intenix
Pankaj Pawar | Intenix | Intenix | Intenix | Intenix
Aakriti | SelfIT - Web services | SelfIT - Web services | SelfIT - Web services | SelfIT - Web services
Nitin | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web
Chinmay | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web
Rajnesh | SelfIT - Event Mgmt | SelfIT - Event Mgmt | SelfIT - Event Mgmt | Tearfunds Android
Anand | DoIT | DoIT | DoIT | DoIT
Tushar | DoIT | DoIT | DoIT | DoIT
Niranjan | Talaeo | Talaeo | Talaeo | Talaeo
Ananda | Right Consultants | Right Consultants | Right Consultants | Right Consultants
Gaurav | Meno | Meno | Meno | Meno
Pawankumar | Brainhost | Brainhost | Brainhost | Brainhost
Sunil Game | Brainhost | Brainhost | Brainhost | Brainhost
Devesh | Brainhost | Brainhost | Brainhost | Brainhost
Sudhir | ESCt | ESCt | ESCt | ESCt
Sachin Shinde | ESCt | ESCt | ESCt | ESCt
Reshma | ESCt | ESCt | ESCt | ESCt
Megha | ESCt | ESCt | ESCt | ESCt
Prasad | Co-Create | Co-Create | Co-Create | Co-Create
Chanchal | Tearfunds - Android | Tearfunds - Android | On Leave | Tearfunds - Android
Tejas | Tearfunds | Tearfunds | ESN iOS App | ESN iOS App
Ashok Daware | Tearfunds Dashboard | Tearfunds Dashboard | Tearfunds Dashboard | Tearfunds Dashboard
Madhav | CCCHealth | CCCHealth | CCCHealth | CCCHealth
Hemant Atre | System9 | System9 | System9 | System10
Lalit | System9 | System9 | Resigned | Resigned
Mandar | PCA | PCA | PCA | PCA
Rakesh B | PCA | PCA | PCA | PCA
Pankaj K | DNN | DNN | System9 | System9
Pravin | BCR | BCR | BCR | BCR
Sarvesh | BCR, Thirdstream | BCR, Thirdstream | BCR, Thirdstream | BCR, Thirdstream
Rupal | WYNP | WYNP | WYNP | WYNP
Mangesh | ISSA | ISSA | ISSA | ISSA
Pratik | MiniSport | MiniSport | MiniSport | MiniSport
Jagdish | MiniSport | MiniSport | MiniSport | MiniSport
Abhijit | ESN | ESN | ESN | ESN
Bhagyashree | ESN | ESN | ESN | ESN
Sameer M | ESN | ESN | ESN | ESN
Ravi S | Designer | Designer | Designer | Designer
Kavita | Designer | Designer | Designer | Designer
Sunil Raut | Designer | Designer | Designer | Designer
Santoshkumar Pande | Designer | Designer | Designer | Designer
Prashant Malpure | Designer | Designer | Designer | Designer
Dynaneshwar | QA | QA | QA | QA
Tatyasaheb Patil | QA | QA | QA | QA
Jayvant | QA | QA | QA | QA
Amol Bansod | QA | QA | QA | QA
Tonny | QA | QA | QA | QA
Abhishek Patel | QA | QA | QA | QA
Note on D4: Priya: Working days = 3 + 3 Diwali Holidays

## Dec 2012
© ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
[7 empty] | Where | xyz, abcd , pqr - Are the projects on which they are working
Resource | Week1 <1 days > | Week2 <6 days> | Week3 <6 days> | Week4 <6 days> | Week5 <3 days> | Week6 <2 days>
Priya | SM | SM | SM | SM | SM | SM |  | Un Billed
Jyoti | PDM | PDM | PDM | PDM | PDM | PDM |  | Partially billed
Sachin M | PM | PM | PM | PM | PM | PM |  | Completely billed
Anjali | BA | BA | BA | BA | BA | BA
Krushna | Messmo | Messmo | Messmo | Messmo | Messmo | Messmo
Vijay | Messmo | Messmo | Messmo | Messmo | Messmo | Messmo
Mahendra | Messmo | Messmo | Messmo | Messmo | Messmo | Messmo
Sandip | Silverdepot | Silverdepot | Silverdepot | Silverdepot | Silverdepot | Silverdepot
Kiran | Hitched | Hitched | Hitched | Hitched | Hitched | Hitched
Nirav | iPhone Training | iPhone Training | Sociodesk | Sociodesk | Sociodesk | Sociodesk
Shrikant | Right Consultants | Right Consultants | Right Consultants | Right Consultants | Right Consultants | Right Consultants
Meenal | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Mrunmayi | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Kavita | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Manisha | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Vaishali | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Nahid | Roodlane | Roodlane | Roodlane | Roodlane | Roodlane | Roodlane
Deepali | On leave | On leave | On leave | On leave | On leave | Android Training
Kamal | VMComplete, F42 | VMComplete, F42 | VMComplete | VMComplete | VMComplete | VMComplete
Sachin K | Intenix | Intenix | Intenix | Intenix | Intenix | Intenix
Amod | Intenix | Intenix | Intenix | Intenix | Intenix | Intenix
Swapna | Intenix | Intenix | Intenix | Intenix | Intenix | Intenix
Poonam S | Intenix | Intenix | Intenix | Intenix | Intenix | Intenix
Pankaj Pawar | Intenix | Intenix | Intenix | Intenix | Intenix | Intenix
Aakriti | SelfIT - Web services | SelfIT - Web services | Sociodesk | Sociodesk | Sociodesk | Sociodesk
Nitin | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web
Chinmay | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web
Rajnesh | Tearfunds Android | Tearfunds Android | Tearfunds Android | Tearfunds Android | Tearfunds Android | Tearfunds Android
Anand | DoIT | DoIT | DoIT | DoIT | DoIT | DoIT
Tushar | DoIT | DoIT | Sociodesk | Sociodesk | Sociodesk | Sociodesk
Niranjan | Talaeo | Talaeo | Talaeo | Talaeo | Talaeo | Talaeo
Ananda | Right Consultants | Right Consultants | Right Consultants | Leave | Leave | Leave
Gaurav | Meno | Meno | Meno | Meno | Meno | Meno
Pawankumar | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost
Sunil Game | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost
Sudhir | ESCt | ESCt | ESCt | ESCt | ESCt | ESCt
Sachin Shinde | ESCt | ESCt | ESCt | ESCt | ESCt | ESCt
Reshma | ESCt | ESCt | ESCt | ESCt | ESCt | ESCt
Megha | ESCt | ESCt | ESCt | ESCt | ESCt | ESCt
Prasad | Co-Create | Co-Create | Sociodesk | Sociodesk | Sociodesk | Sociodesk
Chanchal | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android
Tejas | ESN iOS App | ESN iOS App | ESN iOS App | ESN iOS App | ESN iOS App | ESN iOS App
Ashok Daware | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost
Madhav | CCCHealth | CCCHealth | CCCHealth | CCCHealth | CCCHealth | CCCHealth
Hemant Atre | System9 | System9 | System9 | System10 | System10 | System10
Mandar | PCA | PCA | PCA | PCA | PCA | PCA
Rakesh B | PCA | PCA | PCA | PCA | PCA | PCA
Pankaj K | DNN | DNN | System9 | System9 | System9 | System9
Pravin | BCR | BCR | Basedata | Basedata | Basedata | Basedata
Sarvesh | BCR, Thirdstream | BCR, Thirdstream | BCR, Thirdstream | BCR, Thirdstream | BCR, Thirdstream | BCR, Thirdstream
Rupal | WYNP | WYNP | Tearfunds | Tearfunds | Tearfunds | Tearfunds
Mangesh | ISSA | ISSA | ISSA | ISSA | ISSA | ISSA
Pratik | MiniSport | MiniSport | MiniSport | MiniSport | MiniSport | MiniSport
Jagdish | MiniSport | MiniSport | MiniSport | MiniSport | MiniSport | MiniSport
Abhijit | ESN | ESN | ESN | ESN | ESN | ESN
Bhagyashree | ESN | ESN | ESN | ESN | ESN | ESN
Sameer M | ESN | ESN | ESN | ESN | ESN | ESN
Ravi S | Designer | Designer | Designer | Designer | Designer | Designer
Kavita | Designer | Designer | Designer | Designer | Designer | Designer
Sunil Raut | Designer | Designer | Designer | Designer | Designer | Designer
Santoshkumar Pande | Designer | Designer | Designer | Designer | Designer | Designer
Prashant Malpure | Designer | Designer | Designer | Designer | Designer | Designer
Dynaneshwar | QA | QA | QA | QA | QA | QA
Tatyasaheb Patil | QA | QA | QA | QA | QA | QA
Jayvant | QA | QA | QA | QA | QA | QA
Amol Bansod | QA | QA | QA | QA | QA | QA
Tonny | QA | QA | QA | QA | QA | QA
Abhishek Patel | QA | QA | QA | QA | QA | QA
Note on D4: Priya: Working days = 3 + 3 Diwali Holidays

## Jan 2013
© ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
[6 empty] | Where: | xyz, abcd , pqr - Are the projects on which they are working
Resource | Week1 <6 days > | Week2 <7 days> | Week3 <7 days> | Week4 <7 days> | Week5 <4 days>
Priya | SM | SM | SM | SM | SM |  | Un Billed
Jyoti | PDM | PDM | PDM | PDM | PDM |  | Partially billed
Sachin M | PM | PM | PM | PM | PM |  | Completely billed
Anjali | BA | BA | BA | BA | BA
Krushna | Messmo | Messmo | Messmo | Messmo | Messmo
Vijay | Messmo | Messmo | Messmo | Messmo | Messmo
Mahendra | Messmo | Messmo | Messmo | Messmo | Messmo
Sandip | Silverdepot | Silverdepot | Silverdepot | Silverdepot | Silverdepot
Kiran | Hitched | Hitched | Hitched | Hitched | Hitched
Nirav | Sociodesk | Sociodesk | Sociodesk | Sociodesk | Sociodesk
Shrikant | LeapJobber | LeapJobber | LeapJobber | LeapJobber | LeapJobber
Meenal | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Mrunmayi | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Kavita | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Manisha | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
Vaishali | Designer | Designer | Designer | Designer | Designer
Nahid | Roodlane | Roodlane | Roodlane | Roodlane | Roodlane
Deepali | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android
Kamal | F42 | F42 | F42 | F42 | F42
Sachin K | Sociodesk | Sociodesk | Sociodesk | Sociodesk | Sociodesk
Amod | Intenix | Intenix | Intenix | Intenix | Intenix
Swapna | Intenix | Intenix | Intenix | Intenix | Intenix
Poonam S | Intenix | Intenix | Intenix | Intenix | Intenix
Pankaj Pawar | Intenix | Intenix | Intenix | Intenix | Intenix
Poonam K | Intenix | Intenix | Intenix | Intenix | Intenix
Nitin | SelfIT | SelfIT | SelfIT | SelfIT | SelfIT
Chinmay | SelfIT | SelfIT | SelfIT | SelfIT | SelfIT
Rajnesh | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android
Anand | DoIT | DoIT | DoIT | DoIT | DoIT
Tushar | Sociodesk | Sociodesk | Sociodesk | Sociodesk | Sociodesk
Niranjan | Intenix | Intenix | Intenix | Intenix | Intenix
Ananda | Merlin | Merlin | Merlin | Merlin | Merlin
Gaurav | Meno | Meno | Meno | Meno | Meno
Pawankumar | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost
Sunil Game | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost
Sudhir | ESCt | ESCt | ESCt | ESCt | ESCt
Sachin Shinde | ESCt | ESCt | ESCt | ESCt | ESCt
Reshma | ESCt | ESCt | ESCt | ESCt | ESCt
Megha | ESCt | ESCt | ESCt | ESCt | ESCt
Prasad | Sociodesk | Sociodesk | Sociodesk | Sociodesk | Sociodesk
Chanchal | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android | Tearfunds - Android
Tejas | Sociodesk | Sociodesk | Sociodesk | Sociodesk | Sociodesk
Ashok Daware | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost
Madhav | CCCHealth | CCCHealth | CCCHealth | CCCHealth | CCCHealth
Hemant Atre | System9 | System9 | System9 | System9 | System9
Mandar | PCA | PCA | PCA | PCA | PCA
Rakesh B | PCA | PCA | PCA | PCA | PCA
Pankaj K | System9 | System9 | System9 | System9 | System9
Pravin | Basedata | Basedata | Basedata | Basedata | Basedata
Sarvesh | Thirdstream | Thirdstream | Thirdstream | Thirdstream | Thirdstream
Rupal | Tearfunds - Web | Tearfunds - Web | Tearfunds - Web | Tearfunds - Web | Tearfunds - Web
Mangesh | ESCt | ESCt | ESCt | ESCt | ESCt
Pratik | MiniSport | MiniSport | MiniSport | MiniSport | MiniSport
Jagdish | MiniSport | MiniSport | MiniSport | MiniSport | MiniSport
Abhijit | ESN | ESN | ESN | ESN | ESN
Bhagyashree | ESN | ESN | ESN | ESN | ESN
Sameer M | ESN | ESN | ESN | ESN | ESN
Ravi S | Designer | Designer | Designer | Designer | Designer
Kavita | Designer | Designer | Designer | Designer | Designer
Sunil Raut | Designer | Designer | Designer | Designer | Designer
Santoshkumar Pande | Designer | Designer | Designer | Designer | Designer
Prashant Malpure | Designer | Designer | Designer | Designer | Designer
Dynaneshwar | QA | QA | QA | QA | QA
Tatyasaheb Patil | QA | QA | QA | QA | QA
Jayvant | QA | QA | QA | QA | QA
Amol Bansod | QA | QA | QA | QA | QA
Tonny | QA | QA | QA | QA | QA
Abhishek Patel | QA | QA | QA | QA | QA

## Feb 2013
© ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
[6 empty] | Where | xyz, abcd , pqr - Are the projects on which they are working
Resource | Week1 <3days > | Week2 <6 days> | Week3 <6 days> | Week4 <6 days> | Week5 <4 days>
Priya | SM | SM |  |  |  |  | Un Billed
Jyoti | PDM | PDM |  |  |  |  | Partially billed
Sachin M | PM | PM |  |  |  |  | Completely billed
Anjali | BA | BA
Sunayana | Messmo | Messmo
Vijay | Messmo | Messmo
Mahendra | Messmo | Messmo
Sandip | Silverdepot | Silverdepot
Kiran | Hitched | Hitched
Shrikant | Education Leads | Education Leads
Meenal | Kidspot | Kidspot
Mrunmayi | Kidspot | Kidspot
Kavita | Kidspot - CMS | Kidspot - CMS
Manisha | Kidspot - CMS | Kidspot - CMS
Nahid | Roodlane | Roodlane
Rupal | Tearfunds - Web | Tearfunds - Web
Deepali | Tearfunds - Android | Tearfunds - Android
Kamal | eMedspace | eMedspace
Pratik | eMedspace | eMedspace
Prasad | eMedspace | eMedspace
Krushna | eMedspace | eMedspace
Amod | Intenix | Intenix
Swapna | Intenix | Intenix
Poonam S | Intenix | Intenix
Pankaj Pawar | Simple Ecommerce | Simple Ecommerce
Poonam K | Simple Ecommerce | Simple Ecommerce
Nitin | SelfIT | SelfIT
Chinmay | SelfIT | SelfIT
Rajnesh | Tearfunds - Android | Tearfunds - Android
Anand | DoIT | DoIT
Niranjan | Talaeo | Talaeo
Ananda | Right Consultant | Right Consultant
Gaurav | Meno | Meno
Pawankumar | Brainhost | Brainhost
Sunil Game | Brainhost | Brainhost
Ashok Daware | Brainhost | Brainhost
Sudhir | ESCt | ESCt
Sachin Shinde | ESCt | ESCt
Reshma | ESCt | ESCt
Megha | KPI | MSG
Madhav | KPI | MSG
Hemant Atre | System9 | System9
Pankaj K | System9 | System9
Mandar | Intenix - BPD | Intenix - BPD
Rakesh B | Onecomms | Onecomms
Anup | Onecomms | Onecomms
Pravin | Basedata | Basedata
Sarvesh | Thirdstream | Thirdstream
Mangesh | InfoAktiv | InfoAktiv
Jagdish | MiniSport | MiniSport
Priyanka | Trainee | Trainee | Trainee | Trainee | Trainee
Ravi Kulkarni | Trainee | Trainee | Trainee | Trainee | Trainee
Sayali thete | Trainee | Trainee | Trainee | Trainee | Trainee
Megha Shelke | Trainee | Trainee | Trainee | Trainee | Trainee
Nilay | Trainee | Trainee | Trainee | Trainee | Trainee
Abhijit | ESN | ESN
Bhagyashree | ESN | ESN
Sameer M | ESN | ESN
Sachin K | ESN
Tushar | ESN
Nirav | ESN - Chat
Tejas | ESN-iPhone
Vaishali | Designer | Designer | Designer | Designer | Designer
Ravi S | Designer | Designer | Designer | Designer | Designer
Kavita | Designer | Designer | Designer | Designer | Designer
Sunil Raut | Designer | Designer | Designer | Designer | Designer
Santoshkumar Pande | Designer | Designer | Designer | Designer | Designer
Prashant Malpure | Designer | Designer | Designer | Designer | Designer
Dynaneshwar | QA | QA | QA | QA | QA
Tatyasaheb Patil | QA | QA | QA | QA | QA
Jayvant | QA | QA | QA | QA | QA
Amol Bansod | QA | QA | QA | QA | QA
Tonny | QA | QA | QA | QA | QA
Abhishek Patel | QA | QA | QA | QA | QA

## Capacity Utilisation
© ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
Month | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
No of resources | [6 empty] | 72 | 71 | 70 | 70 | 74
No of resources billed | [6 empty] | 64.5 | 65 | 58 | 59 | 59
Capacity utilisation | [6 empty] | 89.58 | 91.55 | 82.86 | 84.29 | 79.73 | #DIV/0!