## Version Control
© ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
| Version No. | Date | Author | Change Description
| D 0.1 | 2012-01-31 | Sachin Mulay | Initial template definition - draft
| I1.0 | 2012-02-21 | Priya Ekbote | Issued

## Project Vs. Project Type
Project | Project Type | Start Date | End Date | No. of resources | FTE | Subgroup
Messmo | Customer Managed | Ongoing | Ongoing | 4 | 3.25 | PHP
BaseData | Customer Managed | Ongoing | 2012-02-29 | 0 | 0 | ASP.Net
EnergyiseYou - EnergyCheck | Customer Managed | Ongoing | Ongoing | 3 | 1.5 | ASP.Net
SilverDepot, Crazy2shop | Customer Managed | Ongoing | Ongoing | 2 | 1.25
Hitched | Customer Managed | Ongoing | Ongoing | 3 | 3 | ASP.Net
Virtual Runner | Customer Managed | Ongoing | Ongoing | 3 | 1.5 | ASP.Net
Kidspot | Customer Managed | Ongoing | Ongoing | 4 | 3.25 | ASP
Roodlane | Customer Managed | Ongoing | Ongoing | 3 | 1.5 | ASP.Net
MT4 | Customer Managed | Ongoing | Ongoing | 4 | 2.35 | PHP
Intenix-CMS | Customer Managed | Ongoing | Ongoing | 5 | 5 | ASP.Net
SelfIT | Customer Managed | Ongoing | Ongoing | 4 | 2.25 | ASP.Net
PA | Customer Managed | Ongoing | Ongoing | 5 | 3.25 | ASP.Net
DoIT | Customer Managed | Ongoing | Ongoing | 5 | 3.5 | ASP.Net
Staples | Customer Managed | Ongoing | Ongoing | 7 | 5.5 | ASP.Net
Right Consultant - Phase 2 | Aress Managed | 2012-03-15 | 2012-06-19 | 6 | 3 | ASP.Net
Meno | Customer Managed | Ongoing | Ongoing | 2 | 1.25 | Coldfusion
TopNosh | Customer Managed | Ongoing | Ongoing | 3 | 2.25 | ASP.Net
iNosh Android | Customer Managed | Ongoing | Ongoing | 3 | 2.25 | Android - Java
Brainhost | Customer Managed | Ongoing | Ongoing | 2 | 1.25 | PHP
ESCt.Web | Customer Managed | Ongoing | Ongoing | 3 | 2.5 | ASP.Net
ESCt.Net | Customer Managed | Ongoing | Ongoing | 2 | 1.25 | ASP.Net
PSt Web | Customer Managed | Ongoing | Ongoing | 3 | 2.25 | ASP.Net
WYNP | Customer Managed | Ongoing | Ongoing | 4 | 2.25 | PHP
Whats Shakn | Customer Managed | Ongoing | Ongoing | 5 | 3.5 | PHP/iPhone
TKES | Aress Managed | 2012-02-27 | 2012-04-17 | 7 | 3.5 | PHP
20$Banners | Customer Managed | Ongoing | Ongoing | 1 | 1 | N/A

## Feb 2012
Sr. No | Resource | Week1 (6 days) | Week2 (6 days) | Week3 (6 days) | Week4 (6 days) | Week5 (3 days)
1 | Priya |  |  |  | SM | SM
2 | Sachin |  |  |  | PM | PM
3 | Jyoti |  |  |  | PM | PM
4 | Anjali |  |  |  | Messmo | Messmo
5 | Vijay B |  |  |  | Messmo, iPhone Training | Messmo, iPhone Training
6 | Krushna |  |  |  | Messmo | Messmo
7 | Mahendra |  |  |  | Messmo | Messmo
8 | Pravin U |  |  |  | BaseData | BaseData
9 | Swapnil Khairnar |  |  |  | SilverDepot, Crazy2shop | SilverDepot, Crazy2shop
10 | Kiran |  |  |  | Hitched | Hitched
11 | Nirav |  |  |  | Hitched | Hitched
12 | Shrikant |  |  |  | Hitched | Hitched
13 | Deepali |  |  |  | Kidspot | Kidspot
14 | Meenal |  |  |  | Kidspot | Kidspot
15 | Netra |  |  |  | Roodlane | Roodlane (1d)
16 | Jagdish |  |  |  | MT4 | MT4
17 | Kamal |  |  |  | MT4 | MT4
18 | Mangesh |  |  |  | Intenix-CMS | Intenix-CMS
19 | Sumant |  |  |  | Intenix-CMS, Absent (6d) | Intenix-CMS, Absent (6d)
20 | Mandar |  |  |  | Intenix-CMS | Intenix-CMS
21 | Poonam Sonar |  |  |  | Intenix-CMS | Intenix-CMS
22 | Nitin |  |  |  | SelfIT - Desktop | SelfIT - Desktop
23 | Sachin K |  |  |  | Intenix-CMS | Intenix-CMS
24 | Chinmay |  |  |  | SelfIT - Web | SelfIT - Web
25 | Poonam K |  |  |  | PA | PA
26 | Swapna |  |  |  | PA | PA
27 | Anand |  |  |  | DoIT | DoIT
28 | Devesh |  |  |  | DoIT | DoIT
29 | Tushar |  |  |  | DoIT | DoIT
30 | Amod |  |  |  | Staples | Staples
31 | Rakesh Biradar |  |  |  | Staples | Staples
32 | Nahid |  |  |  | Staples | Staples
33 | Lalit |  |  |  | Aress Intranet - Sharepoint | Aress Intranet - Sharepoint
34 | Niranjan |  |  |  | Staples | Staples
35 | Ravi |  |  |  | Intenix PM | Intenix PM
36 | Rakesh S |  |  |  | Right Consultant | Right Consultant
37 | Ananda |  |  |  | Right Consultant | Right Consultant
38 | Rupal |  |  |  | Moodle, RC (PL) | Moodle, RC (PL)
39 | Gaurav |  |  |  | Meno | Meno
40 | Hemant |  |  |  | TopNosh | TopNosh
41 | Chanchal |  |  |  | iNosh Android | iNosh Android
42 | Pawankumar |  |  |  | Brainhost | Brainhost
43 | Sudhir |  |  |  | ESCt.Web | ESCt.Web
44 | Sachin Shinde |  |  |  | ESCt.Net | ESCt.Net
45 | Reshma |  |  |  | ESCt.Web | ESCt.Web
46 | Madhav |  |  |  | PSt Web | PSt Web
47 | Sudarshan |  |  |  | WYNP | WYNP
48 | Pratik |  |  |  | WYNP | WYNP
49 | Sunil |  |  |  | Whats Shakn | Whats Shakn
50 | Ashok Daware |  |  |  | Whats Shakn | Whats Shakn
51 | Rajnesh |  |  |  | Whats Shakn - iPhone | Whats Shakn - iPhone
52 | Supriya |  |  |  | Review System | TKES (2 days)
53 | Rajesh W |  |  |  | Design | Design
54 | Vaishali |  |  |  | Design, SEO | Design, SEO
55 | Ravi S |  |  |  | Design | Design
56 | Kavita |  |  |  | Design | Design
57 | Sunil Raut |  |  |  | Design | Design
58 | Yogendra Kothavade |  |  |  | Design | Design
59 | Santoshkumar Pande |  |  |  | Design | Design
60 | Dynaneshwar |  |  |  | WYNP - QA, GTEC - QA | WYNP - QA, GTEC - QA
61 | Tatyasaheb Patil |  |  |  | TopNosh QA, MT 4 - QA | TopNosh QA, MT 4 - QA
62 | Jayvant |  |  |  | ESCt - QA, RC - QA | ESCt - QA, RC - QA
63 | Amol Bansod |  |  |  | SelfIT - QA, DoIT - QA, Roodlane - QA | SelfIT - QA, DoIT - QA, Roodlane - QA
64 | Tonny |  |  |  | Intenix - QA | Intenix - QA
65 | 12 freshers |  |  |  | ASP.Net Advance training | ASP.Net Advance training
66 | Prasad Patil |  |  |  | iPhone Training | iPhone Training
|  |  |  | Billable Resources | 46.25 | 47.25
| Color Code | Non Billable | No of Resources
|  | 1 | 19
|  | 0.5 | 1
|  | 0.25 | 1

## Mar 2012
Sr. No | Resource | Week1 (3 days) | Week2 (5 days + 1 holiday) | Week3 (6 days) | Week4 (6 days) | Week5 (6 days)
1 | Priya | SM | SM | SM | SM | SM
2 | Sachin | PM, CMMi | PM, CMMi | PM, CMMi | PM, CMMi | PM, CMMi
3 | Jyoti | ESCt - PL (2 hrs/day), TopNosh, PSt, TKES, Misc | ESCt - PL (2 hrs/day), TopNosh, PSt, TKES, Misc | ESCt - PL (2 hrs/day), TopNosh, PSt, TKES, Misc | ESCt - PL (2 hrs/day), TopNosh, PSt, TKES, Misc | ESCt - PL (2 hrs/day), TopNosh, PSt, TKES, Misc
4 | Anjali | Messmo | Messmo | Messmo | Messmo | Messmo
5 | Vijay B | Messmo, iPhone Training | Messmo, iPhone Training | Messmo, iPhone Training | Messmo, iPhone Training | Messmo
6 | Krushna | Messmo | Messmo | Messmo | Messmo | Java training
7 | Mahendra | Messmo | Messmo | Messmo | Messmo | Messmo
8 | Pravin U | energycheck | energycheck | energycheck | energycheck | energycheck
9 | Swapnil Khairnar | SilverDepot, Crazy2shop | SilverDepot, Crazy2shop | SilverDepot, Crazy2shop | SilverDepot, Crazy2shop | SilverDepot, Crazy2shop
10 | Kiran | Hitched | Hitched | Hitched | Hitched | Hitched
11 | Nirav | Hitched | Hitched | Hitched | Hitched | Hitched
12 | Shrikant | Hitched | Hitched | Hitched | Hitched | Hitched
13 | Deepali | Virtual Runner | Virtual Runner | Virtual Runner | Virtual Runner | Virtual Runner
14 | Meenal | Kidspot | Kidspot | Kidspot | Kidspot | Kidspot
15 | Netra | Roodlane | Roodlane | Roodlane | Roodlane | Roodlane
16 | Jagdish | MT4 | MT4 | MT4 | MT4 | MT4
17 | Kamal | MT4 | MT4 | MT4 | MT4 | MT4
18 | Mangesh | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS
19 | Mandar | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS
20 | Poonam Sonar | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS
21 | Nitin | SelfIT - Desktop | SelfIT - Desktop | SelfIT - Desktop | SelfIT - Desktop | SelfIT - Desktop
22 | Sachin K | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS
23 | Chinmay | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web | SelfIT - Web
24 | Poonam K | PA | PA | PA | PA | PA
25 | Swapna | PA | PA | PA | PA | PA
26 | Sarvesh Sharma | ASP.Net training | ASP.Net training | PA | PA | PA
27 | Anand | DoIT | DoIT | DoIT | DoIT | DoIT
28 | Devesh | DoIT | DoIT | DoIT | DoIT | Trust House Call
29 | Tushar | DoIT | DoIT | DoIT | DoIT | DoIT
30 | Amod | Staples | Staples | Staples | Staples | Staples
31 | Rakesh Biradar | Staples | Staples | Staples | Staples | Staples
32 | Nahid | Staples | Staples | Staples | Staples | Staples
33 | Lalit | Staples | Staples | Staples | Staples | PCA Project 2a
34 | Niranjan | Staples | Staples | Staples | Staples | Staples
35 | Ravi | Intenix PM, Whats Shakn, Silverdepot, Brainhost | Intenix PM, Whats Shakn, Silverdepot, Brainhost (2 days absence) | Intenix PM, Whats Shakn, Silverdepot, Brainhost | Intenix PM, Whats Shakn, Silverdepot, Brainhost | Intenix PM, Whats Shakn, Silverdepot, Brainhost
36 | Rakesh S | Right Consultant | Right Consultant | Right Consultant | Right Consultant | Right Consultant
37 | Ananda | Right Consultant | Right Consultant | Right Consultant | Right Consultant | Right Consultant
38 | Rupal | Moodle, RC (PL), TKES (PL) | Moodle, RC (PL), TKES (PL) | Moodle, RC (PL), TKES (PL) | Moodle, RC (PL), TKES (PL) | Moodle, RC (PL), TKES (PL)
39 | Gaurav | Meno | Meno | Meno | Meno | Meno
40 | Hemant | TopNosh | TopNosh | TopNosh | TopNosh | TopNosh
41 | Chanchal | iNosh Android | iNosh Android (1 day absent) | iNosh Android | iNosh Android | iNosh Android
42 | Pawankumar | Brainhost | Brainhost | Brainhost | Brainhost | Brainhost
43 | Sudhir | ESCt.Web | ESCt.Web | ESCt.Web | ESCt.Web | ESCt.Web
44 | Sachin Shinde | ESCt.Net | ESCt.Net | ESCt.Net | ESCt.Net | ESCt.Net
45 | Reshma | ESCt.Web | ESCt.Web | ESCt.Web | ESCt.Web | ESCt.Web
46 | Madhav | PSt Web | PSt Web | PSt Web | PSt Web | PSt Web
47 | Pratik | WYNP | WYNP | WYNP | WYNP | WYNP
48 | Sunil | Whats Shakn | Whats Shakn | Whats Shakn | Whats Shakn | Whats Shakn
49 | Ashok Daware | Whats Shakn | Whats Shakn | Whats Shakn | Whats Shakn | Whats Shakn
50 | Rajnesh | Whats Shakn - iPhone | Whats Shakn - iPhone | Whats Shakn - iPhone | Whats Shakn - iPhone | Whats Shakn - iPhone
51 | Supriya | TKES | TKES | TKES | TKES | TKES
52 | Sudarshan | WYNP | TKES | TKES | TKES | TKES
53 | Rajesh W | Design | Design | Design | Design | Design
54 | Vaishali | Design, SEO | Design, SEO | Design, SEO | Design, SEO | Design, SEO
55 | Titiksha |  |  | Kidspot Data Entry | Kidspot Data Entry | Kidspot Data Entry
56 | Ravi S | Design | Design | Design | Design | Design
57 | Kavita | Design | Design | Design | Design | Design
58 | Sunil Raut | Design | Design | Design | Design | Design
59 | Yogendra Kothavade | Design | Design | Design | Design | Design
60 | Santoshkumar Pande | Design | Design | Design | Design | Design
61 | Dynaneshwar | WYNP - QA | WYNP - QA, WS | WYNP - QA, WS | WYNP - QA, WS | WYNP - QA, WS
62 | Tatyasaheb Patil | TopNosh QA, MT 4 - QA | TopNosh QA, MT 4 - QA | TopNosh QA, MT 4 - QA | TopNosh QA, MT 4 - QA | TopNosh QA, MT 4 - QA
63 | Jayvant | ESCt - QA, RC - QA | ESCt - QA, RC - QA | ESCt - QA, RC - QA | ESCt - QA, RC - QA | ESCt - QA, RC - QA
64 | Amol Bansod | SelfIT - QA, DoIT - QA, Roodlane - QA | SelfIT - QA, DoIT - QA, Roodlane - QA | SelfIT - QA, DoIT - QA, Roodlane - QA | SelfIT - QA, DoIT - QA, Roodlane - QA | SelfIT - QA, DoIT - QA, Roodlane - QA
65 | Tonny | Intenix - QA | Intenix - QA | Intenix - QA | Intenix - QA | Intenix - QA
66 | Prasad Patil | iPhone training | iPhone training | Leave | Leave | Leave
67 | Sandip Salunke | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training
68 | Tejas Bharambe | ASP.Net training | ASP.Net training | ASP.Net training | iPhone training | iPhone training
69 | Rupali Suryavanshi | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training
70 | Mrunmayi Chavanke | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training
71 | Bhagyashree Pawar | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training
72 | Megha Vispute | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training | ESCt.Net
73 | Pankaj Pawar | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training
74 | Pradeep Kadnor | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training
75 | Abhijit Ghule | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training | PSt.Web
76 | Modraj Bhavsar | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training | Intenix CMS
77 | Sameer More | ASP.Net training | ASP.Net training | ASP.Net training | DoIT | DoIT
Note on E56: Priya: Joined from 12-Mar-2012
Note on E67: Priya: Leave from 16-Mar to 06-Mar

## Apr 2012
Sr. No | Resource | Week 1 | Week 2 | Week 3 | Week 4
1 | Priya | SM | SM | SM | SM
2 | Sachin | PM, CMMi | PM, CMMi | PM, CMMi | PM, CMMi
3 | Jyoti | ESCt - PL (2 hrs/day), TopNosh, PSt, Misc | ESCt - PL (2 hrs/day), TopNosh, PSt, Misc | ESCt - PL (2 hrs/day), TopNosh, PSt, Misc | ESCt - PL (2 hrs/day), TopNosh, PSt, Misc
4 | Anjali | Messmo | Messmo | Messmo | Messmo
5 | Vijay B | Messmo | Messmo | Messmo | Messmo
6 | Krushna | Java Training | Java Training | Java Training | Java Training
7 | Mahendra | Messmo | Messmo | Messmo | Messmo
8 | Pravin U | EnergiseYou - DSE | EnergiseYou - DSE | EnergiseYou - DSE | EnergiseYou - DSE
9 | Swapnil Khairnar | SilverDepot, Crazy2shop | SilverDepot, Crazy2shop | SilverDepot, Crazy2shop | SilverDepot, Crazy2shop
10 | Kiran | Hitched | Hitched | Hitched | Hitched
11 | Nirav | Hitched | Hitched | Hitched | Hitched
12 | Shrikant | Hitched | Hitched | Hitched | Hitched
13 | Deepali | Virtual Runner | Kidspot | Kidspot | Kidspot
14 | Meenal | Kidspot | Kidspot | Kidspot | Kidspot
15 | Netra | Roodlane | Roodlane | Roodlane | Roodlane
16 | Jagdish | MT4 | MT4 | MT4 | MT4
17 | Kamal | MT4 | MT4 | MT4 | MT4
18 | Mangesh | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS
19 | Mandar | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS
20 | Poonam Sonar | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS
21 | Nitin | SelfIT - Desktop | iPhone training | SelfIT | SelfIT
22 | Sachin K | Intenix-CMS | Intenix-CMS | Intenix-CMS | Intenix-CMS
23 | Chinmay | SelfIT - Web | Sharepoint training | SelfIT | SelfIT
24 | Poonam K | PA | PA | PA | PA
25 | Swapna | PA | PA | PA | PA
26 | Sarvesh Sharma | PA | PA | PA | PA
27 | Anand | DoIT | Asterisk Research | Asterisk Research, DoIT | DoIT
28 | Devesh | Data Collection Script | QA System | Brainhost | Brainhost
29 | Tushar | DoIT | Asterisk Research | Asterisk Research, DoIT | DoIT
30 | Amod | Staples | Staples | Staples | Staples
31 | Rakesh Biradar | Staples | Staples | PSt | PSt
32 | Nahid | Staples | Staples | Staples | Staples
33 | Lalit | Staples | Virtual Runner | Virtual Runner | Virtual Runner
34 | Niranjan | Staples | Staples | Staples | Staples
35 | Ravi | Intenix PM, Whats Shakn, Silverdepot, Brainhost | Intenix PM, Whats Shakn, Silverdepot, Brainhost (2 days absence) | Intenix PM, Whats Shakn, Silverdepot, Brainhost (2 days absence) | Intenix PM, Whats Shakn, Silverdepot, Brainhost (2 days absence)
36 | Rakesh S | Right Consultant | Right Consultant | Right Consultant | Right Consultant
37 | Ananda | Right Consultant | Right Consultant | Right Consultant | Right Consultant
38 | Rupal | Moodle, RC (PL), TKES (PL) | Moodle, RC (PL), TKES (PL) | Onsite Reports | Onsite Reports
39 | Gaurav | Meno | Meno | Meno | Meno
40 | Hemant | TopNosh | TopNosh | TopNosh | TopNosh
41 | Chanchal | iNosh Android | iNosh Android, OMM Phonegap | iNosh Android, OMM Phonegap | iNosh Android, OMM Phonegap
42 | Pawankumar | Brainhost | Brainhost | Brainhost | Brainhost
43 | Sudhir | ESCt.Web | ESCt.Web | ESCt.Web | ESCt.Web
44 | Sachin Shinde | ESCt.Net | ESCt.Net | ESCt.Net | ESCt.Net
45 | Reshma | ESCt.Web | ESCt.Web | ESCt.Web | ESCt.Web
46 | Madhav | PSt Web | PSt Web | PSt Web | PSt Web
47 | Pratik | WYNP | WYNP | WYNP | WYNP
48 | Sunil | Whats Shakn | OMM | Brainhost | Brainhost
49 | Ashok Daware | Whats Shakn | Wheel Deal | Wheel Deal | Wheel Deal
50 | Rajnesh | Whats Shakn - iPhone | PiT enhancements | PiT enhancements | PiT enhancements
51 | Supriya | TKES | TKES | TKES | TKES
52 | Sudarshan | OMM | OMM | OMM, Tearfunds | Tearfunds
53 | Rajesh W | Design | Design | Design | Design
54 | Vaishali | Design, SEO | Design, SEO | Design, SEO | Design, SEO
55 | Titiksha | Kidspot | absent | Kidspot | Kidspot
56 | Ravi S | Design | Design | Design | Design
57 | Kavita | Design | Design | Design | Design
58 | Sunil Raut | Design | Design | Design | Design
59 | Yogendra Kothavade | Design | Design | Design | Design
60 | Santoshkumar Pande | Design | Design | Design | Design
61 | Dynaneshwar | WYNP - QA | WYNP - QA, WS | WYNP - QA, WS | WYNP - QA, WS
62 | Tatyasaheb Patil | TopNosh QA, MT 4 - QA | TopNosh QA, MT 4 - QA | TopNosh QA, MT 4 - QA | TopNosh QA, MT 4 - QA
63 | Jayvant | ESCt - QA, RC - QA | ESCt - QA, RC - QA | ESCt - QA, RC - QA | ESCt - QA, RC - QA
64 | Amol Bansod | SelfIT - QA, DoIT - QA, Roodlane - QA | SelfIT - QA, DoIT - QA, Roodlane - QA | SelfIT - QA, DoIT - QA, Roodlane - QA | SelfIT - QA, DoIT - QA, Roodlane - QA
65 | Tonny | Intenix - QA | Intenix - QA | Intenix - QA | Intenix - QA
66 | Prasad Patil | Absent | OMM | Onsite Reports | Onsite Reports
67 | Sandip Salunke | ASP.Net training | BAS-Web app | BAS-Web app | BAS-Web app
68 | Tejas Bharambe | iPhone training | iPhone training | Tearfund | Tearfund
69 | Rupali Suryavanshi | ASP.Net training | Kidspot CMS | ASP.Net training | ASP.Net training
70 | Mrunmayi Chavanke | DNN | DNN | DNN | DNN
71 | Bhagyashree Pawar | DNN | DNN | Intenix | Intenix
72 | Megha Vispute | ESCt.Web | ESCt.Web | ESCt.Web | ESCt.Web
73 | Pankaj Pawar | ASP.Net training | BAS-Web app | BAS-Web app | BAS-Web app
74 | Pradeep Kadnor | ASP.Net training | ASP.Net training | ASP.Net training | ASP.Net training
75 | Abhijit Ghule | PSt Web | PSt Web | PSt Web | PSt Web
76 | Modraj Bhavsar | Intenix CMS | Absent | Absent | Absent
77 | Sameer More | ASP.Net training | ASP.Net training | Sarepoint | Sarepoint

## Capacity Utilisation
Month | Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
No of resources | Feb: 77; Mar: 77; Apr: 77
No of resources billed | Feb: 58; Mar: 61; Apr: 67
Capacity utilisation |  | 75.32 | 79.22 | 87.01 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!