## Project review details
CMMI Level wise, process area wise implementation review
Project Name : | Socio Desk
Project Type :
Project Leader :

## REQM
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area - Requirements Management
SG 1 | Manage Requirements
SP 1.1 | Understand Requirements | Develop an understanding with the requirements providers on the meaning of the requirements. | 1. Lists of criteria for distinguishing appropriate requirements providers 2. Criteria for evaluation and acceptance of requirements 3. Results of analyses against criteria 4. A set of approved requirements | Attach initial requirement understanding documents, notes, proposal where in requirement understanding is specified | mails, MOM chat session with requirements provider on understanding requirements
SP 1.2 | Obtain Commitment to Requirements | Obtain commitment to requirements from project participants | 1. Requirements impact assessments 2. Documented commitments to requirements and requirements changes | Project induction MOM | Project schedule, mail
SP 1.3 | Manage Requirements Changes | Manage changes to the requirements as they evolve during the project. | 1. Requirements change requests 2. Requirements change impact reports 3. Requirements status 4. Requirements database | Change request | Mail on change
SP 1.4 | Maintain Bi-directional Traceability of Requirements | Maintain bidirectional traceability among the requirements and work products. | 1. Requirements traceability matrix, 2. Requirements tracking system | Traceability Matrix | SVN screenshot
SP 1.5 | Ensure Alignment Between Project Work and Requirements | Ensure that project plans and work products remain aligned with requirements | 1. Documentation of inconsistencies between requirements and project plans and work products, including sources and conditions 2. Corrective actions | Updated schedule | Change request
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the requirements management process. | - | REQM process - purpose and scope | release mail
GP2.2 | Plan the process | Establish and maintain the plan for performing the requirements management process. | - | Project schedule
GP2.3 | Provide Resources | Provide adequate resources for performing the requirements management process, developing the work products and providing the services of the process. | Examples of resources include: 1. Requirements tracking tools 2. Traceability tools | Project Plan section 15, Tracebaility Matrix, RA
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the requirements management process, developing the work products, and providing the services of the requirements management process. | - | Project Plan section 6 Project Team stakeholder sheet | Project schedule
GP2.5 | Train People | Train the people performing or supporting the requirements management process as needed. | Examples of training topics include: 1. Application domain 2. Requirements definition, analysis, review, and management 3. Requirements management tools 4. Configuration management 5. Negotiation and conflict resolution | Training attendence (project team) | Project Plan training section, mail
GP2.6 | Control Work Products | Place selected work products of the requirements management process under appropriate levels of control | Examples of work products placed under control include: 1. Requirements 2. Requirements traceability matrix | snapshot of SVN where RA and Traceability matrix kept | Project Plan section 13.2
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the requirements management process as planned. | Examples of activities for stakeholder involvement include: 1. Resolving issues on the understanding of the requirements 2. Assessing the impact of requirements changes 3. Communicating the bidirectional traceability 4. Identifying inconsistencies among project plans, work products, and requirements | Project Team stakeholder sheet - Identification Involvement - Induction MOM | Email communication on CR
GP2.8 | Monitor and Control the Process | Monitor and control the requirements management process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Requirements volatility (percentage of requirements changed) 2. Schedule for coordination of requirements 3. Schedule for analysis of a proposed requirements change | Metrics Analysis Report MOM of 21 Nov 2012 Project schedule
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the requirements management process against its process description, standards, and procedures, and address noncompliance. | Examples of activities reviewed: 1. Managing requirements 2. Identifying inconsistencies among project plans, work products, and requirements Examples of work products reviewed 1. Requirements 2. Requirements traceability matrix | Audit observation Report Audit Checklist | Email on audit scheduling
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the requirements management process with higher-level management and resolve issues. | - | MOM of Dec with Sr. Management
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Requirements Management process | - | REQM-RD Process Tailoring form
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the requirement management process to support the future use and improvement of the organization’s processes and process assets | Process related experiences include the following: 1. Requirements traceability matrix 2. Number of unfunded requirements changes after baselining 3. Lessons learned in resolving ambiguous requirements | RA document, Traceability Matrixs to be shared on Aress code library PCR Tracker

## PP
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area- Project Planning
SG 1 | Establish Estimates
SP 1.1 | Estimate the Scope of the Project | Establish a top-level work breakdown structure (WBS) to estimate the scope of the project. | 1. Task descriptions, 2. Work package descriptions, 3. WBS | Estimation sheet _ WBS | proposal
SP 1.2 | Establish Estimates of Work Product and Task Attributes | Establish and maintain estimates of the attributes of the work products and tasks. | 1. Size and complexity of tasks and work products, 2. Estimating models , 3. Attribute estimates 4. Technical Approach | Estimation sheet _ complexities | Estimation guideline
SP 1.3 | Define Project Lifecycle Phases | Define the project life-cycle phases on which to scope the planning effort. | 1. Project life-cycle phases | Project Plan section | Lifecycle standard
SP 1.4 | Estimate Effort and Cost | Estimate the project’s effort and cost for work products and tasks based on estimation rationale | 1. Estimation rationale, 2. Project effort estimates , 3. Project cost estimates | Estimation -effort, phase distribution (rationale part of estimation) | Estimation guideline
SG 2 | Develop a Project Plan
SP 2.1 | Establish the Budget and Schedule | Establish and maintain the project’s budget and schedule. | 1. Project schedules, 2. Schedule dependencies, 3. Project budget | Project schedule
SP 2.2 | Identify Project Risks | Identify and analyze project risks. | 1. Identified risks, 2. Risk impacts and probability of occurrence, 3. Risk priorities | Risk Rigster | Org Level Risk register
SP 2.3 | Plan Data Management | Plan for the management of project data. | 1. Data management plan 2. Master list of managed data 3. Data content and format description 4. Lists of data requirements for acquirers and suppliers 5. Privacy requirements 6. Security requirements 7. Security procedures 8. Mechanisms for data retrieval, reproduction, and distribution 9. Schedule for the collection of project data 10. List of project data to be collected | Project Plan section - to be modified as discussed
SP 2.4 | Plan the Project's Resources | Plan for resources to perform the project | 1. Work packages 2. WBS task dictionary 3. Staffing requirements based on project size and scope 4. Critical facilities and equipment list 5. Process and workflow definitions and diagrams 6. Project administration requirements list 7. Status reports | Project Plan section 15
SP 2.5 | Plan Needed Knowledge and Skills | Plan for knowledge and skills needed to perform the project. | 1. Inventory of skill needs 2. Staffing and new hire plans 3. Databases (e.g., skills, training) 4. Training plans | Project Plan section 16
SP 2.6 | Plan Stakeholder Involvement | Plan the involvement of identified stakeholders. | 1. Stakeholder involvement plan | Project Team stakeholder sheet , Project Plan section 6.2
SP 2.7 | Establish the Project Plan | Establish and maintain the overall project plan content. | 1. Overall project plan | Project Plan
SG 3 | Obtain Commitment to the Plan
SP 3.1 | Review Plans that Affect the Project | Review all plans that affect the project to understand project commitments. | 1. Record of the reviews of plans that affect the project | Timesheet portal - Review effort, date of review and name of reviewer Mail on comments
SP 3.2 | Reconcile Work and Resource Levels | Adjust the project plan to reconcile available and estimated resources | 1. Revised methods and corresponding estimating parameters (e.g., better tools, the use of off-the-shelf components) 2. Renegotiated budgets 3. Revised schedules 4. Revised requirements list 5. Renegotiated stakeholder agreements | Project Plan, Project schedule
SP 3.3 | Obtain Plan Commitment | Obtain commitment from relevant stakeholders responsible for performing and supporting plan execution. | 1. Documented requests for commitments, 2. Documented commitments | Project Plan approval mail
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Project Planning process. | - | PP process - purpose and scope | release mail
GP2.2 | Plan the process | Establish and maintain the plan for performing the Project Planning process. | - | Project schedule
GP2.3 | Provide Resources | Provide adequate resources for performing the Project Planning process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Experienced estimators 2. Schedulers 3. Technical experts in applicable areas (e.g., product domain, technology) | Project plan template, Estimation sheet, Estimation guideline
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Project Planning process, developing the work products, and providing the services of the project planning process. | - | Project Plan section 6 Project Team stakeholder sheet | Project schedule
GP2.5 | Train People | Train the people performing or supporting the Project Planning process as needed. | Examples of training topics include: 1. Estimating 2. Budgeting 3. Identifying and analyzing risks 4. Managing data 5. Planning 6. Scheduling | PM training attendence sheet | Email
GP2.6 | Control Work Products | Place selected work products of the Project Planning process under appropriate levels of control | Examples of work products placed under control include: 1. Work breakdown structure 2. Project plan 3. Data management plan 4. Stakeholder involvement plan | Snapshot SVN folder where project plan, schedule and estimation sheet, Tailoring form kept
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Project Planning process as planned. | Examples of activities for stakeholder involvement include: 1. Establishing estimates 2. Reviewing and resolving issues on the completeness and correctness of the project risks 3. Reviewing data management plans 4. Establishing project plans 5. Reviewing project plans and resolving issues on work and resource issues | Project Team stakeholder sheet Induction MOM
GP2.8 | Monitor and Control the Process | Monitor and control the Project Planning process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Number of revisions to the plan 2. Cost, schedule, and effort variance per plan revision 3. Schedule for development and maintenance of program plans | Metrics Analysis Report Project schedule, Weekly MOM during project planning
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Project Planning process against its process description, standards, and procedures, and address noncompliance. | - | Audit observation Report (Project planning) Audit Checklist | Email on audit scheduling
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Project Planning process with higher-level management and resolve issues. | - | MOM with Sr. Management (during project Planning)
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Project Planning process | - | PP process Tailoring form
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Project Planning process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Project data library structure 2. Project attribute estimates 3. Risk impacts and probability of occurrence | Project Plan, estimation to be shared in PAL PCR tracker

## PMC
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area - Project Monitoring & Control
SG 1 | Monitor the Project Against the Plan
SP 1.1 | Monitor Project Planning Parameters | Monitor the actual values of the project planning parameters against the project plan. | 1. Records of project performance 2. Records of significant deviations 3. Cost performance reports | Project schedule, Metrics Analysis Report | Weekly MOM
SP 1.2 | Monitor Commitments | Monitor commitments against those identified in the project plan. | 1. Records of commitment reviews | Weekly MOM Metrics Analysis Report | Project schedule
SP 1.3 | Monitor Project Risks | Monitor risks against those identified in the project plan. | 1. Records of project risk monitoring | Risk Register | Weekly MOM/MOM with Sr. Management
SP 1.4 | Monitor Data Management | Monitor the management of project data against the project plan. | 1. Records of data management | Weekly MOM SVN snapshot of project folder | Project schedule
SP 1.5 | Monitor Stakeholder Involvement | Monitor stakeholder involvement against the project plan. | 1. Records of stakeholder involvement | weekly MOM Project schedule | Project stakeholder matrix
SP 1.6 | Conduct Progress Reviews | Periodically review the project's progress, performance, and issues. | 1. Documented project review results | weekly MOM Project schedule Metrics Analysis
SP 1.7 | Conduct Milestone Reviews | Review the project’s accomplishments and results at selected project milestones | 1. Documented milestone review results | Milestone/phase completion MOM | Project schedule
SG 2 | Manage Corrective Action to Closure
SP 2.1 | Analyze Issues | Collect and analyze issues and determine corrective actions to address them | 1. List of issues requiring corrective actions | Issue Tracker | mail/MOM where issues are discussed and actions are identified
SP 2.2 | Take Corrective Action | Take corrective action on identified issues. | 1. Corrective action plans | Issue Tracker
SP 2.3 | Manage Corrective Actions | Manage corrective actions to closure. | 1. Corrective action results | Issue Tracker
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Project Monitoring and Control process. | - | PMC process - purpose and scope
GP2.2 | Plan the process | Establish and maintain the plan for performing the Project Monitoring and Control process. | - | Project schedule, Project Plan section 7
GP2.3 | Provide Resources | Provide adequate resources for performing the Project Monitoring and Control process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Cost tracking systems 2. Effort reporting systems 3. Action item tracking systems 4. Project management and scheduling programs | project schedule, MOM
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Project Monitoring and Control process, developing the work products, and providing the services of the Project Monitoring and Control process. | - | Project Plan section 6 Project Team stakeholder sheet | Project schedule
GP2.5 | Train People | Train the people performing or supporting the Project Monitoring and Control process as needed. | Examples of training topics include: 1. Monitoring and control of projects 2. Risk management 3. Data management | PM training attendence sheet | Email
GP2.6 | Control Work Products | Place selected work products of the Project Monitoring and Control process under appropriate levels of control | Examples of work products placed under control include: 1. Project schedules with status 2. Project measurement data and analysis 3. Earned value reports | Snapshot SVN folder where weekly MOM, Metrics Analysis, phase completion MOM are kept
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Project Monitoring and Control process as planned. | Examples of activities for stakeholder involvement include: 1. Assessing the project against the plan 2. Reviewing commitments and resolving issues 3. Reviewing project risks 4. Reviewing project progress 5. Managing corrective actions to closure | Project Team stakeholder sheet Weekly MOM
GP2.8 | Monitor and Control the Process | Monitor and control the Project Monitoring and Control process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Number of open and closed corrective actions 2. Schedule with status for monthly financial data collection, analysis, and reporting 3. Number and types of reviews performed 4. Review schedule (planned versus actual and slipped target dates) 5. Schedule for collection and analysis of monitoring data | Metrics Analysis Report Project schedule, Weekly MOM
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Project Monitoring and Control process against its process description, standards, and procedures, and address noncompliance. | - | Audit observation Report Audit Checklist | Email on audit scheduling
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Project Monitoring and Control process with higher-level management and resolve issues. | - | MOM with Sr. Management
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Project Monitoring and Control process | - | PMC process Tailoring form
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Project Monitoring and Control process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Records of significant deviations 2. Criteria for what constitutes a deviation 3. Corrective action results | weekly MOM, Metrics Analysis, phase completion MOM to be shared in PAL PCR tracker

## MA
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area - Measurement & Analysis
SG 1 | Align Measurement and Analysis Activities
SP 1.1 | Establish Measurement Objectives | Establish and maintain measurement objectives derived from identified information needs and objectives | 1. Measurement Objectives | PI Plan should be modified to address the measurement objectives and its target Project plan section 9.2 | MOM with PM & Sr. Mgmt discussing these target and their acceptance
SP 1.2 | Specify Measures | Specify measures to address the measurement objectives. | 1. Specifications of base and derived measures | Measurement guideline (measures to be modified as discussed) Project Plan section 9.2
SP 1.3 | Specify Data Collection and Storage Procedures | Specify how measurement data are obtained and stored | 1. Data collection and storage procedures, 2. Data collection tools | Measurement guideline (measures to be modified as discussed) Project Plan section 9.2
SP 1.4 | Specify Analysis Procedures | Specify how measurement data are analyzed and communicated | 1. Analysis specification and procedures, 2. Data analysis tools | Measurement guideline (measures to be modified as discussed)
SG 2 | Provide Measurement Results
SP 2.1 | Obtain Measurement Data | Obtain specified measurement data. | 1. Base and derived measurement data sets, 2. Results of data integrity tests | Metrics Analysis Report | Project schedule, Timesheet report, Mantis Report
SP 2.2 | Analyze Measurement Data | Analyze and interpret measurement data. | 1. Analysis results and draft reports | Metrics Analysis Report | Measurement repository
SP 2.3 | Store Data and Results | Manage and store measurement data, measurement specifications, and analysis results. | 1. Stored data inventory (- Measurement plans, · Specifications of measures · Sets of data that have been collected · Analysis reports and presentations) | Metrics Analysis Report
SP 2.4 | Communicate Results | Communicate results of measurement and analysis activities to all relevant stakeholders | 1. Delivered reports and related analysis results 2. Contextual information or guidance to help interpret analysis results | Phase completion MOM | Mail to Sr. Management
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Measurement and Analysis process. | - | MA process - purpose and scope | release mail
GP2.2 | Plan the process | Establish and maintain the plan for performing the Measurement and Analysis process. | - | Project schdule | weekly MOM
GP2.3 | Provide Resources | Provide adequate resources for performing the Measurement and Analysis process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Statistical packages 2. Packages that support data collection over networks | Metrics Analysis Report Mantis, Timesheet, Project schedule
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Measurement and Analysis process, developing the work products, and providing the services of the Measurement and Analysis process. | - | Project Plan section 6 Project Team stakeholder sheet | Project schedule
GP2.5 | Train People | Train the people performing or supporting the Measurement and Analysis process as needed. | Examples of training topics include: 1. Statistical techniques 2. Data collection, analysis, and reporting processes 3. Development of goal related measurements (e.g., Goal Question Metric) | PM training attendence sheet | Email
GP2.6 | Control Work Products | Place selected work products of the Measurement and Analysis process under appropriate levels of control | Examples of work products placed under control include: 1. Measurement objectives 2. Specifications of base and derived measures 3. Data collection and storage procedures 4. Base and derived measurement data sets 5. Analysis results and draft reports 6. Data analysis tools | Snapshot SVN folder where, Metrics Analysis report is kept
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Measurement and Analysis process as planned. | Examples of activities for stakeholder involvement include: 1. Establishing measurement objectives and procedures 2. Assessing measurement data 3. Providing meaningful feedback to those who are responsible for providing the raw data on which the analysis and results depend | Project Team stakeholder sheet Weekly MOM
GP2.8 | Monitor and Control the Process | Monitor and control the Measurement and Analysis process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Percentage of projects using progress and performance measures 2. Percentage of measurement objectives addressed 3. Schedule for collection and review of measurement data | Metrics Analysis Report Project schedule, Weekly MOM
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Measurement and Analysis process against its process description, standards, and procedures, and address noncompliance. | - | Audit observation Report Audit Checklist | Email on audit scheduling
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Measurement and Analysis process with higher-level management and resolve issues. | - | MOM with Sr. Management
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Measurement and Analysis process | - | MA process Tailoring form
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Measurement and Analysis process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Data currency status 2. Results of data integrity tests 3. Data analysis reports | weekly MOM, Metrics Analysis report to be shared in PAL PCR tracker

## SAM
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | Affirmation
Process Area - Supplier Agreement Management
SG1 | Establish Supplier Agreements
SP 1.1 | Determine Acquisition Type | Determine the type of acquisition for each product or product component to be acquired. | 1. List of the acquisition types that will be used for all products and product components to be acquired
SP 1.2 | Select Suppliers | Select suppliers based on an evaluation of their ability to meet the specified requirements and established criteria. | 1. Market studies 2. List of candidate suppliers 3. Preferred supplier list 4. Trade study or other record of evaluation criteria, advantages and disadvantages of candidate suppliers, and rationale for selection of suppliers 5. Solicitation materials and requirements
SP1.3 | Establish Supplier Agreements | Establish and maintain supplier agreements | 1. Statements of work 2. Contracts 3. Memoranda of agreement 4. Licensing agreement
SG2 | Satisfy Supplier Agreements
SP 2.1 | Execute the Supplier Agreement | Perform activities with the supplier as specified in the supplier agreement | 1. Supplier progress reports and performance measures 2. Supplier review materials and reports 3. Action items tracked to closure 4. Product and documentation deliveries
SP 2.2 | Accept the Acquired Product | Ensure that the supplier agreement is satisfied before accepting the acquired product. | 1. Acceptance procedures 2. Acceptance reviews or test results 3. Discrepancy reports or corrective action plans
SP 2.3 | Ensure Transition of Products | Ensure the transition of products acquired from the supplier | 1.Transition plans, 2.Training reports , 3.Support and maintenance reports
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Supplier Agreement Management process. | -
GP2.2 | Plan the process | Establish and maintain the plan for performing the Supplier Agreement Management process. | -
GP2.3 | Provide Resources | Provide adequate resources for performing the Supplier Agreement Management process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Preferred supplier lists 2. Requirements tracking tools 3. Project management and scheduling programs
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Supplier Agreement Management process, developing the work products, and providing the services of the Supplier Agreement Management process. | -
GP2.5 | Train People | Train the people performing or supporting the Supplier Agreement Management process as needed. | Examples of training topics include: 1. Regulations and business practices related to negotiating and working with suppliers 2. Acquisition planning and preparation 3. Commercial off-the-shelf products acquisition 4. Supplier evaluation and selection 5. Negotiation and conflict resolution 6. Supplier management 7. Testing and transition of acquired products 8. Receiving, storing, using, and maintaining acquired products
GP2.6 | Control Work Products | Place selected work products of the Supplier Agreement Management process under appropriate levels of control | Examples of work products placed under control include: 1. Statements of work 2. Supplier agreements 3. Memoranda of agreement 4. Subcontracts 5. Preferred supplier lists
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Supplier Agreement Management process as planned. | Examples of activities for stakeholder involvement include: 1. Establishing criteria for evaluation of potential suppliers 2. Reviewing potential suppliers 3. Establishing supplier agreements 4. Resolving issues with suppliers 5. Reviewing supplier performance
GP2.8 | Monitor and Control the Process | Monitor and control the Supplier Agreement Management process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Number of changes made to the requirements for the supplier 2. Cost and schedule variance in accordance with the supplier agreement 3. Schedule for selecting a supplier and establishing an agreement
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Supplier Agreement Management process against its process description, standards, and procedures, and address noncompliance. | -
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Supplier Agreement Management process with higher-level management and resolve issues. | -
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Supplier Agreement Management process | -
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Supplier Agreement Management process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Results of supplier reviews 2. Trade studies used to select suppliers 3. Revision history of supplier agreements 4. Supplier performance reports

## PPQA
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | Affirmation
Process Area - Process & Product Quality Assurance
SG 1 | Objectively Evaluate Processes and Work Products
SP 1.1 | Objectively Evaluate Processes | Objectively evaluate selected performed processes against applicable process descriptions, standards, and procedures | 1. Evaluation reports, 2. Noncompliance reports, 3. Corrective actions | Audit report should be modified and add followup audit remarks, followup audit date and status of NC - closed/open | Add process checkpoint as discussed.
SP 1.2 | Objectively Evaluate Work Products | Objectively evaluate selected work products against applicable process descriptions, standards, and procedures | 1. Evaluation reports, 2. Noncompliance reports, 3. Corrective actions
SG 2 | Provide Objective Insight
SP 2.1 | Communicate and Resolve Noncompliance Issues | Communicate quality issues and ensure the resolution of noncompliance issues with the staff and managers | 1. Corrective action reports, 2. Evaluation reports, 3. Quality trends | Audit report should be modified and add followup audit remarks, followup audit date and status of NC - closed/open
SP 2.2 | Establish Records | Establish and maintain records of quality assurance activities | 1. Evaluation logs 2. Quality assurance reports 3. Status reports of corrective actions 4. Reports of quality trends | Add Trend report
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Process and Product Quality Assurance process. | - | PPQA process with purpose and scope | release mail
GP2.2 | Plan the process | Establish and maintain the plan for performing the Process and Product Quality Assurance process. | - | Org Level PPQA schedule to be attached
GP2.3 | Provide Resources | Provide adequate resources for performing the Process and Product Quality Assurance process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Evaluation tools 2. Noncompliance tracking tools | PPQA tracker
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Process and Product Quality Assurance process, developing the work products, and providing the services of the Process and Product Quality Assurance process. | - | Project Plan section 6.3 | Responsibility Matrix section of PPQA process
GP2.5 | Train People | Train the people performing or supporting the Process and Product Quality Assurance process as needed. | Examples of training topics include: 1. Process descriptions, standards, procedures, and methods for the project 2. Quality assurance objectives, process descriptions, standards, procedures, methods, and tools | PPQA Training attendence | Training schedule mail
GP2.6 | Control Work Products | Place selected work products of the Process and Product Quality Assurance process under appropriate levels of control | Examples of work products placed under control include: 1. Noncompliance reports 2. Evaluation logs and reports | SVN screen shot of all audit reports
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Process and Product Quality Assurance process as planned. | Examples of activities for stakeholder involvement include: 1. Establishing criteria for the objective evaluations of processes and work products 2. Evaluating processes and work products 3. Resolving noncompliance issues 4. Tracking noncompliance issues to closure | PPQA Tracker for identification Audit observation report - involvement
GP2.8 | Monitor and Control the Process | Monitor and control the Process and Product Quality Assurance process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Variance of objective process evaluations planned and performed 2. Variance of objective work product evaluations planned and performed 3. Schedule for objective evaluations | PPQA Tracker
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Process and Product Quality Assurance process against its process description, standards, and procedures, and address noncompliance. | - | Audit report of PPQA Function
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Process and Product Quality Assurance process with higher-level management and resolve issues. | - | Sr.Mgmet MOM on Audit findings
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Process and Product Quality Assurance process | - | PPQA process | release mail
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Process and Product Quality Assurance process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Evaluation logs 2. Quality trends 3. Noncompliance reports 4. Status reports of corrective actions | PPQA Tracker, PCR Tracker - improvement on PPQA process and other elements | SEPG MOM on discussion

## CM
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area - Configuration Management
SG 1 | Establish Baselines
SP 1.1 | Identify Configuration Items | Identify configuration items, components, and related work products to be placed under configuration management | 1. Identified configuration items | Project Plan section 13.2
SP 1.2 | Establish a Configuration Management System | Establish and maintain a configuration management and change management system for controlling work products. | 1. Configuration management system with controlled work products 2. Configuration management system access control procedures 3. Change request database | Project Plan section 13
SP 1.3 | Create or Release Baselines | Create or release baselines for internal use and for delivery to the customer. | 1. Baselines 2. Description of baselines | Project plan section 13.2
SG 2 | Track and Control Changes
SP 2.1 | Track Change Requests | Track change requests for configuration items | 1. Change requests | Change request | Mail from client on change, defect log
SP 2.2 | Control Configuration Items | Control changes to configuration items. | 1. Revision history of configuration items 2. Archives of baselines | CI register, One CI log screen shot
SG 3 | Establish Integrity
SP 3.1 | Establish Configuration Management Records | Establish and maintain records describing configuration items. | 1. Revision history of configuration items 2. Change log 3. Change request records 4. Status of configuration items 5. Differences between baselines | CI register, Change log, PCA-FCA audit report
SP 3.2 | Perform Configuration Audits | Perform configuration audits to maintain integrity of configuration baselines. | 1. Configuration audit results, 2. Action items | PCA-FCA audit report
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Configuration Management process. | - | CM process - Purpose and scope
GP2.2 | Plan the process | Establish and maintain the plan for performing the Configuration Management process. | - | Project schedule
GP2.3 | Provide Resources | Provide adequate resources for performing the Configuration Management process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Configuration management tools 2. Data management tools 3. Archiving and reproduction tools 4. Database management systems | Project Plan CM section Change log
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Configuration Management process, developing the work products, and providing the services of the Configuration Management process. | - | Project Plan section 6 Project Team stakeholder sheet | Project schedule
GP2.5 | Train People | Train the people performing or supporting the Configuration Management process as needed. | Examples of training topics include: 1. Roles, responsibilities, and authority of the configuration management staff 2. Configuration management standards, procedures, and methods 3. Configuration library system | PM training attendence sheet | Email
GP2.6 | Control Work Products | Place selected work products of the Configuration Management process under appropriate levels of control | Examples of work products placed under control include: 1. Change request database 2. CCB meeting minutes 3. Archived baselines | Snapshot SVN folder where project plan, PCA FCA report, Change log kept
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Configuration Management process as planned. | Examples of activities for stakeholder involvement include: 1. Establishing baselines 2. Reviewing configuration management system reports and resolving issues 3. Assessing the impact of changes for configuration items 4. Performing configuration audits 5. Reviewing results of configuration management audits | Project Team stakeholder sheet PCA FCA report, | email
GP2.8 | Monitor and Control the Process | Monitor and control the Configuration Management process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Number of changes to configuration items 2. Number of configuration audits conducted 3. Schedule of CCB or audit activities | Change log, Project schedule
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Configuration Management process against its process description, standards, and procedures, and address noncompliance. | - | Audit observation Report (CM process) Audit Checklist | Email on audit scheduling
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Configuration Management process with higher-level management and resolve issues. | - | MOM with Sr. Management (discussion on CM acivity)
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Configuration Management process | - | CM process Tailoring form
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Configuration Management process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Trends in the status of configuration items 2. Configuration audit results 3. Change request aging reports | PCA-FCA audit report, Change request log shared to PAL PCR Tracker

## RD
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | Affirmation
Process Area - Requirements Development
SG 1 | Develop Customer Requirements
SP 1.1 | Elicit Needs | Elicit stakeholder needs, expectations, constraints, and interfaces for all phases of the product life cycle. | 1. Results of requirements elicitation activities | RA document | Review mail
SP 1.2 | Transform Stakeholder Needs into Customer Requirements | Transform stakeholder needs, expectations, constraints, and interfaces into prioritized customer requirements | 1. Prioritized customer requirements 2. Customer constraints on the conduct of verification 3. Customer constraints on the conduct of validation | RA document | Review mail
SG 2 | Develop Product Requirements
SP 2.1 | Establish Product and Product Component Requirements | Establish and maintain product and product component requirements, which are based on the customer requirements | 1. Derived requirements 2. Product requirements 3. Product component requirements 4. Architectural requirements, which specify or constrain the relationships among product components | RA Document
SP 2.2 | Allocate Product Component Requirements | Allocate the requirements for each product component. | 1. Requirement allocation sheets 2. Provisional requirement allocations 3. Design constraints 4. Derived requirements 5. Relationships among derived requirements | RA document section 3.0 (system workflow definition)
SP 2.3 | Identify Interface Requirements | Identify interface requirements. | 1. Interface requirements | RA document section 3.0 (system workflow definition - prerequisite)
SG 3 | Analyze and Validate Requirements
SP 3.1 | Establish Operational Concepts and Scenarios | Establish and maintain operational concepts and associated scenarios. | 1. Operational concept 2. Product or product component development, installation, operational, maintenance, and support concepts 3. Disposal concepts 4. Use cases 5. Timeline scenarios 6. New requirements | RA document, Prototypes
SP 3.2 | Establish a Definition of Required Functionality and Quality Attributes | Establish and maintain a definition of required functionality and quality attributes | 1. Definition of required functionality and quality attributes 2. Functional architecture 3. Activity diagrams and use cases 4. Object oriented analysis with services or methods identified 5. Architecturally significant quality attribute requirements | RA doucment - System workflow definition + System Overview - performance
SP 3.3 | Analyze Requirements | Analyze requirements to ensure that they are necessary and sufficient. | 1. Requirements defects reports 2. Proposed requirements changes to resolve defects 3. Key requirements 4. Technical performance measures | Timesheet portal - Review effort, date of review and name of reviewer Defect Log | Mail on review
SP 3.4 | Analyze Requirements to Achieve Balance | Analyze requirements to balance stakeholder needs and constraints. | 1. Assessment of risks related to requirements | RA document - assumptions and constraints
SP 3.5 | Validate Requirements | Validate requirements to ensure the resulting product will perform as intended in the end user's environment | 1. Record of analysis methods and results | client sign off
GG2 | Institutionalize a Managed Process |  |  | Same as of REQM
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Requirements Development process. | -
GP2.2 | Plan the process | Establish and maintain the plan for performing the Requirements Development process. | -
GP2.3 | Provide Resources | Provide adequate resources for performing the Requirements Development process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Requirements specification tools 2. Simulators and modeling tools 3. Prototyping tools 4. Requirements tracking tools
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Requirements Development process, developing the work products, and providing the services of the Requirements Development process. | -
GP2.5 | Train People | Train the people performing or supporting the Requirements Development process as needed. | Examples of training topics include: 1. Application domain 2. Requirements definition and analysis 3. Requirements elicitation 4. Requirements specification and modeling 5. Requirements tracking
GP2.6 | Control Work Products | Place selected work products of the Requirements Development process under appropriate levels of control | Examples of work products placed under control include: 1. Customer functional and quality attribute requirements 2. Definition of required functionality and quality attributes 3. Product and product component requirements 4. Interface requirements
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Requirements Development process as planned. | Examples of activities for stakeholder involvement include: 1. Reviewing the adequacy of requirements in meeting needs, expectations, constraints, and interfaces 2. Establishing operational concepts and operational, sustainment, and development scenarios 3. Assessing the adequacy of requirements 4. Prioritizing customer requirements 5. Establishing product and product component functional and quality attribute requirements 6. Assessing product cost, schedule, and risk
GP2.8 | Monitor and Control the Process | Monitor and control the Requirements Development process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Cost, schedule, and effort expended for rework 2. Defect density of requirements specifications 3. Schedule for activities to develop a set of requirements
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Requirements Development process against its process description, standards, and procedures, and address noncompliance. | -
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Requirements Development process with higher-level management and resolve issues. | -
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Requirements Development process | -
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Requirements Development process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. List of the requirements for a product that are found to be ambiguous 2. Number of requirements introduced at each phase of the project lifecycle 3. Lessons learned from the requirements allocation process

## TS
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area - Technical Solution
SG 1 | Select Product Component Solutions
SP 1.1 | Develop Alternative Solutions and Selection Criteria | Develop alternative solutions and selection criteria. | 1. Alternative solution screening criteria 2. Evaluation reports of new technologies 3. Alternative solutions 4. Selection criteria for final selection 5. Evaluation reports of COTS products | Create alternatives example and add in Tech specification document unders section 3. | attach DAR form
SP 1.2 | Select Product Component Solutions | Select the product component solutions based on selection criteria | 1. Product component selection decisions and rationale 2. Documented relationships between requirements and product components 3. Documented solutions, evaluations, and rationale | Attach DAR form
SG 2 | Develop the Design
SP 2.1 | Design the Product or Product Component | Develop a design for the product or product component. | 1. Product architecture, 2. Product component designs | Tech spec section 3
SP 2.2 | Establish a Technical Data Package | Establish and maintain a technical data package. | 1. Technical data packages | RA, TS and prototype
SP 2.3 | Design Interfaces Using Criteria | Design product component interfaces using established criteria | 1. Interface design specifications 2. Interface control documents 3. Interface specification criteria 4. Rationale for selected interface design | TS - section 3.5
SP 2.4 | Perform Make, Buy, or Reuse Analyses | Evaluate whether the product components should be developed, purchased, or reused based on established criteria. | 1. Criteria for design and product component reuse 2. Make-or-buy analyses 3. Guidelines for choosing COTS product components | TS section 3.2
SG 3 | Implement the Product Design
SP 3.1 | Implement the Design | Implement the designs of the product components. | 1. Implemented design | snapshot code folder | Code review checklist, Defect log
SP 3.2 | Develop Product Support Documentation | Develop and maintain the end-use documentation. | 1. End-user training materials 2. User's manual 3. Operator's manual 4. Maintenance manual 5. Online help | Attach release notes (if not user manual, operation manual, maintenance manual) Add deployment instructions
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Technical Solution process. | -
GP2.2 | Plan the process | Establish and maintain the plan for performing the Technical Solution process. | -
GP2.3 | Provide Resources | Provide adequate resources for performing the Technical Solution process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Design specification tools 2. Prototyping tools 3. Scenario definition and management tools 4. Requirements tracking tools 5. Simulators and modeling tools
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Technical Solution process, developing the work products, and providing the services of the Technical Solution process. | -
GP2.5 | Train People | Train the people performing or supporting the Technical Solution process as needed. | Examples of training topics include: 1. Application domain of the product and product components 2. Design methods 3. Architecture methods 4. Interface design 5. Unit testing techniques 6. Standards (e.g., product, safety, human factors, environmental) | Developer training attendence on QMS training | email on training
GP2.6 | Control Work Products | Place selected work products of the Technical Solution process under appropriate levels of control | Examples of work products placed under control include: 1. Product, product component, and interface designs 2. Technical data packages 3. Interface design documents 4. Criteria for design and product component reuse 5. Implemented designs (e.g., software code, fabricated product components) 6. User, installation, operation, and maintenance documentation | snapshot of SVN folder contains TS, RA | Project Plan section 13.2
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Technical Solution process as planned. | Examples of activities for stakeholder involvement include: 1. Developing alternative solutions and selection criteria 2. Obtaining approval on external interface specifications and design descriptions 3. Developing the technical data package 4. Assessing the make, buy, or reuse alternatives for product components 5. Implementing the design | Project Team stakeholder sheet - Identification Involvement -weekly MOM during design and development phase | email on review
GP2.8 | Monitor and Control the Process | Monitor and control the Technical Solution process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Cost, schedule, and effort expended for rework 2. Percentage of requirements addressed in the product or product component design 3. Size and complexity of the product, product components, interfaces, and documentation 4. Defect density of technical solutions work products 5. Schedule for design activities | Metrics Analysis Report MOM during design & coding phase Project schedule
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Technical Solution process against its process description, standards, and procedures, and address noncompliance. | - | Audit observation Report (design & development phase) Audit Checklist | Email on audit scheduling
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Technical Solution process with higher-level management and resolve issues. | - | MOM with Sr. Management during design and coding phase
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Technical Solution process | - | TS process, Tailoring form | release mail
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Technical Solution process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Results of the make, buy, or reuse analysis 2. Design defect density 3. Results of applying new methods and tools | TS, document reuse code shared on Aress code library PCR Tracker

## PI
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area - Product Integration
SG 1 | Prepare for Product Integration
SP 1.1 | Establish an Integration Strategy | Establish and maintain a product integration strategy | 1. Product integration strategy 2. Rationale for selecting or rejecting alternative product integration strategies | TS section 3.9
SP 1.2 | Establish the Product Integration Environment | Establish and maintain the environment needed to support the integration of the product components. | 1. Verified environment for product integration 2. Support documentation for the product integration environment | TS section 3.9
SP 1.3 | Establish Product Integration Procedures and Criteria | Establish and maintain procedures and criteria for integration of the product components. | 1. Product integration procedures 2. Product integration criteria | TS section 3.9, Project Plan
SG 2 | Ensure Interface Compatibility
SP 2.1 | Review Interface Descriptions for Completeness | Review interface descriptions for coverage and completeness. | 1. Categories of interfaces 2. List of interfaces per category 3. Mapping of the interfaces to the product components and product integration environment | TS Review record
SP 2.2 | Manage Interfaces | Manage internal and external interface definitions, designs, and changes for products and product components. | 1. Table of relationships among the product components and the external environment (e.g., main power supply, fastening product, computer bus system) 2. Table of relationships among the different product components 3. List of agreed-to interfaces defined for each pair of product components, when applicable 4. Reports from the interface control working group meetings 5. Action items for updating interfaces 6. Application program interface (API) 7. Updated interface description or agreement
SG 3 | Assemble Product Components and Deliver the Product
SP 3.1 | Confirm Readiness of Product Components for Integration | Confirm, prior to assembly, that each product component required to assemble the product has been properly identified, behaves according to its description, and that the product component interfaces comply with the interface descriptions | 1. Acceptance documents for the received product components 2. Delivery receipts 3. Checked packing lists. 4. Exception reports 5. Waivers | Unit Test report, Mantis UT defect log | Unit Test case def
SP 3.2 | Assemble Product Components | Assemble product components according to the product integration strategy and procedures | 1. Assembled product or product components | snapshot of build
SP 3.3 | Evaluate Assembled Product Components | Evaluate assembled product components for interface compatibility. | 1. Exception reports 2. Interface evaluation reports 3. Product integration summary reports | Integration test report Mantis IT defect log | Integration test case def
SP 3.4 | Package and Deliver the Product or Product Component | Package the assembled product or product component and deliver it to the appropriate customer. | 1. Packaged product or product components 2. Delivery documentation | Release note | mail to client
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Product Integration process. | -
GP2.2 | Plan the process | Establish and maintain the plan for performing the Product Integration process. | -
GP2.3 | Provide Resources | Provide adequate resources for performing the Product Integration process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Prototyping tools 2. Analysis tools 3. Simulation tools 4. Interface management tools 5. Assembly tools (e.g., compilers, make files, joining tools, jigs, fixtures)
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Product Integration process, developing the work products, and providing the services of the Product Integration process. | -
GP2.5 | Train People | Train the people performing or supporting the Product Integration process as needed. | Examples of training topics include: 1. Application domain 2. Product integration procedures and criteria 3. Organization’s facilities for integration and assembly
GP2.6 | Control Work Products | Place selected work products of the Product Integration process under appropriate levels of control | Examples of work products placed under control include: 1. Acceptance documents for the received product components 2. Evaluated assembled product and product components 3. Product integration strategy 4. Product integration procedures and criteria 5. Updated interface description or agreement | snapshot of build
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Product Integration process as planned. | Examples of activities for stakeholder involvement include: 1. Establishing the product integration strategy 2. Reviewing interface descriptions for completeness 3. Establishing the product integration procedures and criteria 4. Assembling and delivering the product and product components | Project Team stakeholder sheet - Identification Involvement -weekly MOM during build | email on review
GP2.8 | Monitor and Control the Process | Monitor and control the Product Integration process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Product component integration profile (e.g., product component assemblies planned and performed, number of exceptions found) 2. Integration evaluation problem report trends (e.g., number written and number closed) 3. Integration evaluation problem report aging (i.e., how long each problem report has been open) 4. Schedule for conduct of specific integration activities | Metrics Analysis Report MOM during build phase Project schedule
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Product Integration process against its process description, standards, and procedures, and address noncompliance. | - | Audit observation Report (build phase) Audit Checklist | Email on audit scheduling
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Product Integration process with higher-level management and resolve issues. | - | MOM with Sr. Management during build phase
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Product Integration process | - | TS process, VER_VAL process Tailoring form
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Product Integration process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Records of the receipt of product components, exception reports, confirmation of configuration status, and results of readiness checking 2. Percentage of total development effort spent in product integration (actual to date plus estimate to complete) 3. Defects found in the product and test environment during product integration 4. Problem reports resulting from product integration | TS, release note PCR Tracker

## VER
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area - Verification
SG 1 | Prepare for Verification
SP 1.1 | Select Work Products for Verification | Select work products to be verified and verification methods to be used | 1. Lists of work products selected for verification 2. Verification methods for each selected work product | Project Plan section 9.3, Test Plan
SP 1.2 | Establish the Verification Environment | Establish and maintain the environment needed to support verification. | 1. Verification environment | All Checklists, Project schedule- reviewer identification, Test Plan
SP 1.3 | Establish Verification Procedures and Criteria | Establish and maintain verification procedures and criteria for the selected work products. | 1. Verification procedures 2. Verification criteria | Project Plan section 9.3, Test Plan
SG 2 | Perform Peer Reviews
SP 2.1 | Prepare for Peer Reviews | Prepare for peer reviews of selected work products. | 1. Peer review schedule 2. Peer review checklist 3. Entry and exit criteria for work products 4. Criteria for requiring another peer review 5. Peer review training material 6. Selected work products to be reviewed | Project schedule, All review checklist | email for review
SP 2.2 | Conduct Peer Reviews | Conduct peer reviews of selected work products and identify issues resulting from these reviews | 1. Peer review results 2. Peer review issues 3. Peer review data | Timesheet portal - Review effort, date of review and name of reviewer Defect Log | Mail on review
SP 2.3 | Analyze Peer Review Data | Analyze data about preparation, conduct, and results of the peer reviews. | 1. Peer review data 2. Peer review action items | Metrics Defect Analysis, Mantis Report
SG 3 | Verify Selected Work Products
SP 3.1 | Perform Verification | Perform verification on selected work products. | 1. Verification results 2. Verification reports 3. Demonstrations 4. As-run procedures log | Unit test result , Mantis defect long | Unit tes case def
SP 3.2 | Analyze Verification Results | Analyze results of all verification activities | 1. Analysis report (e.g., statistics on performance, causal analysis of nonconformances, comparison of the behavior between the real product and models, trends) 2. Trouble reports 3. Change requests for verification methods, criteria, and the environment | Metrics Defect Analysis, Mantis Report for UT
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Verification process. | -
GP2.2 | Plan the process | Establish and maintain the plan for performing the Verification process. | -
GP2.3 | Provide Resources | Provide adequate resources for performing the Verification process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Test management tools 2. Test case generators 3. Test coverage analyzers 4. Simulators
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Verification process, developing the work products, and providing the services of the Verification process. | -
GP2.5 | Train People | Train the people performing or supporting the Verification process as needed. | Examples of training topics include: 1. Application or service domain 2. Verification principles, standards, and methods (e.g., analysis, demonstration, inspection, test) 3. Verification tools and facilities 4. Peer review preparation and procedures 5. Meeting facilitation
GP2.6 | Control Work Products | Place selected work products of the Verification process under appropriate levels of control | Examples of work products placed under control include: 1. Verification procedures and criteria 2. Peer review training material 3. Peer review data 4. Verification reports | snapshot of SVN folder - testplan, testcript kept
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Verification process as planned. | Examples of activities for stakeholder involvement include: 1. Selecting work products and methods for verification 2. Establishing verification procedures and criteria 3. Conducting peer reviews 4. Assessing verification results and identifying corrective action | Project Team stakeholder sheet - Identification Involvement -weekly MOM during unit testing activities | email on review
GP2.8 | Monitor and Control the Process | Monitor and control the Verification process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Verification profile (e.g., the number of verifications planned and performed, and the defects found; or defects categorized by verification method or type) 2. Number of defects detected by defect category 3. Verification problem report trends (e.g., number written, number closed) 4. Verification problem report status (i.e., how long each problem report has been open) 5. Schedule for a specific verification activity 6. Peer review effectiveness | Metrics Analysis Report MOM during UT phase Project schedule, Test case result
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Verification process against its process description, standards, and procedures, and address noncompliance. | - | Audit observation Report (Unit test ) Audit Checklist | Email on audit scheduling
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Verification process with higher-level management and resolve issues. | - | MOM with Sr. Management during UTphase
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Verification process | - | VER_VAL process Tailoring form
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Verification process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Peer review records that include conduct time and average preparation time 2. Number of product defects found through verification per development phase 3. Verification and analysis report | Metrics Report shared to PAL PCR tracker

## VAL
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area - Validation
SG 1 | Prepare for Validation
SP 1.1 | Select Products for Validation | Select products and product components to be validated and validation methods to be used | 1. Lists of products and product components selected for validation 2. Validation methods for each product or product component 3. Requirements for performing validation for each product or product component 4. Validation constraints for each product or product component | ST_IT Test Plan | Project Plan
SP 1.2 | Establish the Validation Environment | Establish and maintain the environment needed to support validation. | 1. Validation environment | ST_IT Test Plan
SP 1.3 | Establish Validation Procedures and Criteria | Establish and maintain procedures and criteria for validation. | 1. Validation procedures 2. Validation criteria 3. Test and evaluation procedures for maintenance, training, and support | ST_IT Test Plan
SG 2 | Validate Product or Product Components
SP 2.1 | Perform Validation | Perform validation on selected products and product components. | 1. Validation reports 2. Validation results 3. Validation cross-reference matrix 4. As-run procedures log 5. Operational demonstrations | ST_IT Test case result | ST_IT test case definition
SP 2.2 | Analyze Validation Results | Analyze results of validation activities. | 1. Validation deficiency reports 2. Validation issues 3. Procedure change request | Metrics Defect Analysis, Mantis Report for ST_IT
GG2 | Institutionalize a Managed Process |  |  | Same as of VER
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Validation process. | -
GP2.2 | Plan the process | Establish and maintain the plan for performing the Validation process. | -
GP2.3 | Provide Resources | Provide adequate resources for performing the Validation process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Test management tools 2. Test case generators 3. Test coverage analyzers 4. Simulators 5. Load, stress, and performance testing tools
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Validation process, developing the work products, and providing the services of the Validation process. | -
GP2.5 | Train People | Train the people performing or supporting the Validation process as needed. | Examples of training topics include: 1. Application domain 2. Validation principles, standards, and methods 3. Intended-use environment
GP2.6 | Control Work Products | Place selected work products of the Validation process under appropriate levels of control | Examples of work products placed under control include: 1. Lists of products and product components selected for validation 2. Validation methods, procedures, and criteria 3. Validation reports
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Validation process as planned. | Examples of activities for stakeholder involvement include: 1. Selecting the products and product components to be validated 2. Establishing the validation methods, procedures, and criteria 3. Reviewing results of product and product component validation and resolving issues 4. Resolving issues with the customers or end users
GP2.8 | Monitor and Control the Process | Monitor and control the Validation process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Number of validation activities completed (planned versus actual) 2. Validation problem report trends (e.g., number written, number closed) 3. Validation problem report aging (i.e., how long each problem report has been open) 4. Schedule for a specific validation activity
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Validation process against its process description, standards, and procedures, and address noncompliance. | -
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Validation process with higher-level management and resolve issues. | -
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Validation process | -
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Validation process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Product component prototype 2. Percentage of time the validation environment is available 3. Number of product defects found through validation per development phase 4. Validation analysis report

## IPM
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area – Integrated Project Management
SG 1 | Use the Project’s Defined Process
SP 1.1 | Establish the Project’s Defined Process | Establish and maintain the project’s defined process from project startup through the life of the project | 1. The project’s defined process | Project Plan section 5, Tailoring for,
SP 1.2 | Use Organizational Process Assets for Planning Project Activities | Use organizational process assets and the measurement repository for estimating and planning project activities | 1. Project estimates 2. Project plans | Estimation sheet (template) Measurement repository
SP 1.3 | Establish the Project's Work Environment | Establish and maintain the project’s work environment based on the organization’s work environment standards | 1. Equipment and tools for the project 2. Installation, operation, and maintenance manuals for the project work environment 3. User surveys and results 4. Use, performance, and maintenance records 5. Support services for the project’s work environment | Project Plan section 15 | Work environment standard
SP 1.4 | Integrate Plans | Integrate the project plan and other plans that affect the project to describe the project’s defined process | 1. Integrated plans | Project Plan
SP 1.5 | Manage the Project Using the Integrated Plans | Manage the project using the project plan, other plans that affect the project, and the project’s defined process | 1. Work products created by performing the project’s defined process 2. Collected measures (i.e., actuals) and status records or reports 3. Revised requirements, plans, and commitments 4. Integrated plans | Metrics Analysis,Project schedule Phase completion report, Milestone report
SP 1.6 | Establish Teams | Establish and maintain teams | 1. Documented shared vision 2. List of members assigned to each team 3. Team charters 4. Periodic team status reports | Project Team stakeholder sheet, Allocation mails from Sr. Management
SP 1.7 | Contribute to the Organizational Process Assets | Contribute process related experiences to organizational process assets | 1. Proposed improvements to organizational process assets 2. Actual process and product measures collected from the project 3. Documentation (e.g., exemplary process descriptions, plans, training modules, checklists, lessons learned) 4. Process artifacts associated with tailoring and implementing the organization’s set of standard processes on the project | Improvement sugesstion mail. Snap shot of mail
SG 2 | Coordinate and Collaborate with Relevant Stakeholders
SP 2.1 | Manage Stakeholder Involvement | Manage the involvement of the relevant stakeholders in the project. | 1. Agendas and schedules for collaborative activities 2. Recommendations for resolving relevant stakeholder issues 3. Documented issues (e.g., issues with stakeholder requirements, product and product component requirements, product architecture, product design) | Issue Tracker
SP 2.2 | Manage Dependencies | Participate with relevant stakeholders to identify, negotiate, and track critical dependencies | 1. Defects, issues, and action items resulting from reviews with relevant stakeholders 2. Critical dependencies 3. Commitments to address critical dependencies 4. Status of critical dependencies | Project schedule
SP 2.3 | Resolve Coordination Issues | Resolve issues with relevant stakeholders. | 1. Relevant stakeholder coordination issues 2. Status of relevant stakeholder coordination issues | Issue Tracker
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Integrated Project Management process. | - | PP process Purpose and scope
GP2.2 | Plan the process | Establish and maintain the plan for performing the Integrated Project Management process. | - | Project Schedule
GP2.3 | Provide Resources | Provide adequate resources for performing the Integrated Project Management process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Problem tracking and trouble reporting packages 2. Groupware 3. Video conferencing 4. Integrated decision database 5. Integrated product support environments | Estimation sheet (template) Measurement repository, Issue tracker
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Integrated Project Management process, developing the work products, and providing the services of the Integrated Project Management process. | - | Project Plan section 6 Project Team stakeholder sheet | Project schedule
GP2.5 | Train People | Train the people performing or supporting the Integrated Project Management process as needed. | Examples of training topics include: 1. Tailoring the organization’s set of standard processes to meet the needs of the project 2. Managing the project based on the project’s defined process 3. Using the organization’s measurement repository 4. Using the organizational process assets 5. Integrated management 6. Intergroup coordination 7. Group problem solving | PM training attendence sheet | Email
GP2.6 | Control Work Products | Place selected work products of the Integrated Project Management process under appropriate levels of control | Examples of work products placed under control include: 1. The project’s defined process 2. Project plans 3. Other plans that affect the project 4. Integrated plans 5. Actual process and product measurements collected from the project 6. Project’s shared vision 7. Team structure 8. Team charters | Snapshot SVN folder where project plan, weekly report, phase completion report, milestone report
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Integrated Project Management process as planned. | Examples of activities for stakeholder involvement include: 1. Resolving issues about the tailoring of organizational process assets 2. Resolving issues among the project plan and other plans that affect the project 3. Reviewing project progress and performance to align with current and projected needs, objectives, and requirements 4. Creating the project’s shared vision 5. Defining the team structure for the project 6. Populating teams | Project Team stakeholder sheet MOM - coordination issues are discussed
GP2.8 | Monitor and Control the Process | Monitor and control the Integrated Project Management process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Number of changes to the project’s defined process 2. Schedule and effort to tailor the organization’s set of standard processes 3. Interface coordination issue trends (i.e., number identified and number closed) 4. Schedule for project tailoring activities 5. Project's shared vision usage and effectiveness 6. Team structure usage and effectiveness 7. Team charters usage and effectiveness | Metrics Analysis Report Project schedule, Weekly MOM
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Integrated Project Management process against its process description, standards, and procedures, and address noncompliance. | - | Audit observation Report Audit Checklist | Email on audit scheduling
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Integrated Project Management process with higher-level management and resolve issues. | - | MOM with Sr. Management (during project Planning)
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Integrated Project Management process | - | PP process Tailoring form
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Integrated Project Management process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Project’s defined process 2. Number of tailoring options exercised by the project to create its defined process 3. Number of times the process asset library is accessed for assets related to project planning by project members 4. Team charters | Project Plan, estimation to be shared in PAL PCR tracker

## RSKM
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area - Risk Management
SG 1 | Prepare for Risk Management
SP 1.1 | Determine Risk Sources and Categories | Determine risk sources and categories. | 1.Risk source lists (external and internal), 2. Risk categories list | Org level Risk Register (to be modified as discussed)
SP 1.2 | Define Risk Parameters | Define parameters used to analyze and categorize risks and to control the risk management effort | 1.Risk evaluation, categorization, and prioritization criteria , 2.Risk management requirements (e.g. Control and approval levels, reassessment intervals, etc.) | Risk management guideline
SP 1.3 | Establish a Risk Management Strategy | Establish and maintain the strategy to be used for risk management. | 1. Project risk management strategy | Risk management guideline
SG 2 | Identify and Analyze Risks
SP 2.1 | Identify Risks | Identify and document risks. | List of identified risks, including the context, conditions, and consequences of risk occurrence | Project Risk register
SP 2.2 | Evaluate, Categorize, and Prioritize Risks | Evaluate and categorize each identified risk using defined risk categories and parameters, and determine its relative priority | 1. List of risks and their assigned priority | Project Risk register
SG 3 | Mitigate Risks
SP 3.1 | Develop Risk Mitigation Plans | Develop a risk mitigation plan in accordance with the risk management strategy | 1. Documented handling options for each identified risk 2. Risk mitigation plans 3. Contingency plans 4. List of those who are responsible for tracking and addressing each risk | Project Risk register
SP 3.2 | Implement Risk Mitigation Plans | Monitor the status of each risk periodically and implement the risk mitigation plan as appropriate. | 1. Updated lists of risk status 2. Updated assessments of risk likelihood, consequence, and thresholds 3. Updated list of risk handling options 4. Updated list of actions taken to handle risks 5. Risk mitigation plans of risk handling options | Project Risk register
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Risk Management process. | - | Risk Management process
GP2.2 | Plan the process | Establish and maintain the plan for performing the Risk Management process. | - | Project schedule - updated revisiting risks
GP2.3 | Provide Resources | Provide adequate resources for performing the Risk Management process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Risk management databases 2. Risk mitigation tools 3. Prototyping tools 4. Modeling and simulation tools | Risk Register
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Risk Management process, developing the work products, and providing the services of the Risk Management process. | - | Project Plan section 6 Project Team stakeholder sheet | Project schedule
GP2.5 | Train People | Train the people performing or supporting the Risk Management process as needed. | Examples of training topics include: 1. Risk management concepts and activities (e.g., risk identification, evaluation, monitoring, mitigation) 2. Measure selection for risk mitigation | PM training attendence sheet | Email
GP2.6 | Control Work Products | Place selected work products of the Risk Management process under appropriate levels of control | Examples of work products placed under control include: 1. Risk management strategy 2. Identified risk items 3. Risk mitigation plans | SVN snapshot where risk register kept
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Risk Management process as planned. | Examples of activities for stakeholder involvement include: 1. Establishing a collaborative environment for free and open discussion of risk 2. Reviewing the risk management strategy and risk mitigation plans 3. Participating in risk identification, analysis, and mitigation activities 4. Communicating and reporting risk management status | Project Team stakeholder sheet MOM on risk discussion
GP2.8 | Monitor and Control the Process | Monitor and control the Risk Management process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Number of risks identified, managed, tracked, and controlled 2. Risk exposure and changes to the risk exposure for each assessed risk, and as a summary percentage of management reserve 3. Change activity for risk mitigation plans (e.g., processes, schedule, funding) 4. Occurrence of unanticipated risks 5. Risk categorization volatility 6. Comparison of estimated versus actual risk mitigation effort and impact 7. Schedule for risk analysis activities 8. Schedule of actions for a specific mitigation | Updated risk register, Project schedule, MOM on risk discussion
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Risk Management process against its process description, standards, and procedures, and address noncompliance. | - | Audit observation Report (Risk management)Audit Checklist | Email on audit scheduling
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Risk Management process with higher-level management and resolve issues. | - | MOM with Sr. Management (during project Planning/risks discussion)
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Risk Management process | - | RSKM process Tailoring form
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Risk Management process to support the future use and improvement of the organization’s processes and process assets | Examples of process related experiences include: 1. Risk parameters 2. Risk categories 3. Risk status reports | Sharing of risk register to PAL PCR Tracker

## DAR
CMMI Model |  |  |  | <Name of Project>
| Practice Statement | Practice - Description | CMMI Typical work products | Artfact (Outcome of Practice and Consequences of the same) | SE
Process Area - Decision Analysis & Resolution
SG 1 | Evaluate Alternatives
SP 1.1 | Establish Guidelines for Decision Analysis | Establish and maintain guidelines to determine which issues are subject to a formal evaluation process. | 1. Guidelines for when to apply a formal evaluation process | DAR guideline - section 2 | SEPG MOM on DAR guideline discussion
SP 1.2 | Establish Evaluation Criteria | Establish and maintain criteria for evaluating alternatives and the relative ranking of these criteria | 1. Documented evaluation criteria, 2. Rankings of criteria importance | DAR form
SP 1.3 | Identify Alternative Solutions | Identify alternative solutions to address issues. | 1. Identified alternatives | DAR form
SP 1.4 | Select Evaluation Methods | Select evaluation methods. | 1. Selected evaluation methods | DAR Form | DAR guideline - section on evaluation methods
SP 1.5 | Evaluate Alternative Solutions | Evaluate alternative solutions using established criteria and methods | 1. Evaluation results | DAR form
SP 1.6 | Select Solutions | Select solutions from alternatives based on evaluation criteria. | 1. Recommended solutions to address significant issues | DAR form
GG2 | Institutionalize a Managed Process
GP2.1 | Establish an Organizational Policy | Establish and maintain an organizational policy for planning and performing the Decision Analysis and Resolution process. | - | DAR process - purpose and scope | release mail
GP2.2 | Plan the process | Establish and maintain the plan for performing the Decision Analysis and Resolution process. | - | MOM - discussion to triger the DAR process for selecting alternatives
GP2.3 | Provide Resources | Provide adequate resources for performing the Decision Analysis and Resolution process, developing the work products and providing the services of the process. | Examples of resources provided include: 1. Simulators and modeling tools 2. Prototyping tools 3. Tools for conducting surveys | DAR form, DAR guidelines
GP2.4 | Assign Responsibility | Assign responsibility and authority for performing the Decision Analysis and Resolution process, developing the work products, and providing the services of the Decision Analysis and Resolution process. | - | Project Plan section 6 Project Team stakeholder sheet | Project schedule
GP2.5 | Train People | Train the people performing or supporting the Decision Analysis and Resolution process as needed. | Examples of training topics include: 1. Formal decision analysis 2. Methods for evaluating alternative solutions against criteria | PM training attendence sheet | Email
GP2.6 | Control Work Products | Place selected work products of the Decision Analysis and Resolution process under appropriate levels of control | Examples of work products placed under control include: 1. Guidelines for when to apply a formal evaluation process 2. Evaluation reports containing recommended solutions | Snapshot SVN folder where DAR form is kept
GP2.7 | Identify and Involve Relevant Stakeholders | Identify and involve the relevant stakeholders of the Decision Analysis and Resolution process as planned. | Examples of activities for stakeholder involvement include: 1. Establishing guidelines for which issues are subject to a formal evaluation process 2. Defining the issue to be addressed 3. Establishing evaluation criteria 4. Identifying and evaluating alternatives 5. Selecting evaluation methods 6. Selecting solutions | Project Team stakeholder sheet DAR summary - involvement
GP2.8 | Monitor and Control the Process | Monitor and control the Decision Analysis and Resolution process against the plan for performing the process and take appropriate corrective action. | Examples of measures and work products used in monitoring and controlling include: 1. Cost-to-benefit ratio of using formal evaluation processes 2. Schedule for the execution of a trade study | DAR form Timesheet report on effort spent on DAR activities
GP2.9 | Objectively Evaluate Adherence | Objectively evaluate adherence of the Decision Analysis and Resolution process against its process description, standards, and procedures, and address noncompliance. | - | Audit observation Report (DAR activities) Audit Checklist | Email on audit scheduling
GP2.10 | Review Status with Higher Level Management | Review the activities, status, and results of the Decision Analysis and Resolution process with higher-level management and resolve issues. | - | DAR Summary (Sr. Managementy involvement)
GG3 | Institutionalize a Defined Process
GP3.1 | Establish a Defined Process | Establish and maintain the description of a defined Decision Analysis and Resolution process | - | DAR process Tailoring form
GP3.2 | Collect Process Related Experiences | Collect process related experiences derived from planning and performing the Decision Analysis and Resolution process to support the future use and improvement of the organization’s processes and process assets | Examples process related experiences include: 1. Number of alternatives considered 2. Evaluation results 3. Recommended solutions to address significant issues | DAR form to be shared in PAL PCR tracker