## Version History
©ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
| Version No. | Date | Author | Change Description
| D 0.1 | 2012-02-10 | Sachin Mulay | Initial draft of checklist point
| I1.0 | 2012-02-14 | Jyoti Yeotikar | Issued

## ProjectSchedule - Checklist
©ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
Project
Date checked
Checked by
srl No | Check list for Project Schedule | When | Confirmation
1 | Include activity for PPQA | once per month - if possible after milestone delivery
2 | Include activity for SQA | After completion of the selected phase before any of the milestone delivery. Minimum 1 SQA per project
3 | Include activity for PCA-FCA audit | After successful system-integration testing , before Final delivery
4 | Include induction meeting | start of project
5 | Include Weekly status meeting | weekly
6 | Include Milestone meetings | After milestone delivery
7 | Include Phase completion meetings | After phase completion
8 | Include closure meeting | end of project
9 | Include activity for updating project plan | Adhoc , Once per month , preferably after milestone delivery
10 | Include activity for updating risk register | Adhoc , Once per month , preferably after milestone delivery
11 | include activity to update MA | Milestone and phase completion meeting , final delivery
12 | backup recovery | once per month
13 | Is the project schedule in synch with estimation sheet | N/A
14 | revision of estimaties | at the end of RA/design phase
15 | MA review - PM, SM SQA | before project closure
16 | DAR | As per need basis