## Version History
©ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
Template History
| Version No. | Date | Author | Change Description
| D 0.1 | 2012-01-31 | Jyoti Yeotikar | Initial template definition - draft
| I1.0 | 2012-02-22 | Priya Ekbote | Issued

## Proposal -Checklist
©ARESS SOFTWARE AND EDUCATION TECHNOLOGIES PVT. LTD.
Company Confidential
Proposal title:
Verified BY:
Date Verified:
Srl No. | Check List - For Proposal | Checked
1 | Check if the system prototypes will be provided by the client.
a. If yes:
a.1. Scope for the analysis of the prototypes
a.2. Add a note that the estimates might be subject to revision after the detailed analysis of the prototypes
a.3. Add a note that the prototypes should be received during the analysis and design phase.
a.4. Add a note that our preferred format to receive the prototypes will be Adobe Photoshop.
a.5. Add estimates for conversion to HTML
b. If no:
a.1. Scope for implementation of system prototypes. Write a note that the prototypes of the essential screens will be provided in Adobe photoshop
a.2. Add estimates for conversion to HTML
2 | Check if the client requires website design: If yes Add estimates for the website designing. This is a standard block that we use
3 | Analyse the different roles in the system and make sure the break-down of the modules for each role is provided separately.
4 | Make sure that if there any third party components to be used, then their information is put in blue color.
5 | Also, if there any licenses required to make use of the third party application, then it is clearly informed that the client will need to provide us with the same.
6 | If it is a desktop application, then make sure we add estimates for:
a. Splash screen
b. Minimize app to system tray
c. Packaging and bundling. If required, mention the note that we would use InstallShield as the tool to create the installer package.
7 | Include the integration and testing block:
a. If desktop application, then make sure we include, OS compatibility and clearly specify the OS that would be considered for testing. Also, include considerations for 32 bit and 64 bit.
b. If web application, then make sure we include the Browser compatibility and clearly specify the browsers that would be considered for testing.
c. If mobile application, then make sure we include the mobile OS compatibility and clearly specify the mobile OS that would be considered for testing.
d. Make sure Integration testing is 20% of the complete analysis, design and development time of the project
8 | Make sure the technology details including the programming language, the database, the OS are clearly specified.
9 | Make sure the project hours are totaled correctly, and the estimates in man days are added in the Project Costing section.
10 | Make sure the revision history, date of the proposal are correct, and the document name also contains the date.