## 4. Project Integration Mgt
# | 1 | Knowledge Area | Project Integration Management | PMBOK # | 4 | Total Process | 6 [ I 1 ] [ P 1 ] [E 1 ] [ M&C 1 ] [ C 1 ]
Process Gourp | Process # | Process | Ellaboration | Process Flow | PF# | PF Details | Definition
Initiating | 4.1 | Develop Project Charter (P66) | This is the process of developing a document that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. Key benefit: Well-defined project start and project boundaries, creation of a formal record of the project, and a direct way for senior management to formally accept and commit to the project. | Input | 4.1.1.1 (P68) | Project statement of work SOW | SOW is a narrative description of products, services, or results to be delivered. by a project. The SOW references: - Business need, Product scope description, Strategic plan
Initiating | 4.1 |  |  |  | 4.1.1.2 (P69) | Business case | This document describes the necessary information from a business standpoint to determine whether or not the project is worth the required investment. Business Case is created as a result of one or more of the following: - Market demand, Organizational need, Customer request, Technological advance, Legal requirement, Ecological impacts, Social need
Initiating | 4.1 |  |  |  | 4.1.1.3 (P70) | Agreements | Agreements are used to define initial intentions for a project and may take the form of contracts, memorandums of understanding (MOUs), service level agreements (SLA), letter of agreements, letters of intent, verbal agreements, email, or other written agreements
Initiating | 4.1 |  |  |  | 4.1.1.4 (P70) | Enterprise environmental factors EEF | Refers to conditions, not under the control of the project team, that influence, constrain, or direct the project. factors include" - Organizational culture, structure, and governance, Geographic distribution, Government or industry standards, Infrastructure, Existing human resources, Personnel administration, Company work authorization systems, Marketplace conditions, Stakeholder risk tolerances, Political climate, Organization’s established communications channels, Commercial databases, Project management information system
Initiating | 4.1 |  |  |  | 4.1.1.5 (P70) | Organizational process assets OPA | OPA may be grouped into two categories: (1) processes and procedures, and (2) corporate knowledge base. OPA include plans, processes, policies, procedures, organization’s knowledge bases such as lessons learned and historical information
Initiating | 4.1 |  |  | Tools | 4.1.2.1 (P71) | Expert judgment | Is often used to assess the inputs used to develop the project charter. Such expertise is provided by any group, Other units within the organization, Consultants, Stakeholders, including customers or sponsors, Professional and technical associations, Industry groups, Subject matter experts (SME), and Project management office (PMO).
Initiating | 4.1 |  |  |  | 4.1.2.2 (P71) | Facilitation techniques | FT guide the development of the project charter. Brainstorming, conflict resolution, problem solving, and meeting management are examples of key techniques used by facilitators to help teams and individuals accomplish project activities.
Initiating | 4.1 |  |  | Output | 4.1.3.1 (P71) | Project charter | The document issued by the project initiator or sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities.
Planning | 4.2 | Develop Project Management Plan (P72) | This is the process of defining, preparing, and coordinating all subsidiary plans and integrating them into a comprehensive project management plan. The key benefit of this process is a central document that defines the basis of all project work. Key benefit: Central document that defines the basis of all project work. | Input | 4.2.1.1 (P74) | Project charter | The document issued by the project initiator or sponsor that formally authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities.
Planning | 4.2 |  |  |  | 4.2.1.2 (P74) | Outputs from other processes | Outputs from many of the other processes described in Sections 5 through 13 are integrated to create the project management plan. Any baselines and subsidiary plans that are an output from other planning processes are inputs to this process. In addition, changes to these documents may necessitate updates to the project management plan.
Planning | 4.2 |  |  |  | 4.2.1.3 (P74) | Enterprise environmental factors EEF | Refers to conditions, not under the control of the project team, that influence, constrain, or direct the project. factors include" - Organizational culture, structure, and governance, Geographic distribution, Government or industry standards, Infrastructure, Existing human resources, Personnel administration, Company work authorization systems, Marketplace conditions, Stakeholder risk tolerances, Political climate, Organization’s established communications channels, Commercial databases, Project management information system
Planning | 4.2 |  |  |  | 4.2.1.4 (P75) | Organizational process assets OPA | OPA may be grouped into two categories: (1) processes and procedures, and (2) corporate knowledge base. OPA include plans, processes, policies, procedures, organization’s knowledge bases such as lessons learned and historical information
Planning | 4.2 |  |  | Tools | 4.2.2.1 (P76) | Expert judgment | For this process expert judgment is utilized to: - Tailor the process to meet the project needs, - Develop technical and management details to be included in the project management plan, - Determine resources and skill levels - Define the level of configuration management - Determine which project documents will be subject to the formal change control process, and - Prioritize the work on the project
Planning | 4.2 |  |  |  | 4.2.2.2 (P76) | Facilitation techniques | FT guide the development of the project charter. Brainstorming, conflict resolution, problem solving, and meeting management are examples of key techniques used by facilitators to help teams and individuals accomplish project activities.
Planning | 4.2 |  |  | Output | 4.2.3.1 (P76) | Project management plan | This is the document that describes how the project will be executed, monitored, and controlled. It integrates and consolidates all of the subsidiary plans and baselines from the planning processes. Project baselines include, but are not limited to: - Scope baseline (Section 5.4.3.1), - Schedule baseline (Section 6.6.3.1), and - Cost baseline (Section 7.3.3.1). Subsidiary plans include, but are not limited to: - Scope management plan (Section 5.1.3.1), - Requirements management plan (Section 5.1.3.2), - Schedule management plan (Section 6.1.3.1), - Cost management plan (Section 7.1.3.1), - Quality management plan (Section 8.1.3.1), - Process improvement plan (Section 8.1.3.2), - Human resource management plan (Section 9.1.3.1), - Communications management plan (Section 10.1.3.1), - Risk management plan (Section 11.1.3.1), - Procurement management plan (Section 12.1.3.1), and - Stakeholder management plan (Section 13.2.3.1).
Executing | 4.3 | Direct and Manage Project Work (P79) | This is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project’s objectives. Key benefit: Provides overall management of the project work. | Input | 4.3.1.1 (P82) | Project management plan | The project management plan contains subsidiary plans concerning all aspects of the project. Those subsidiary plans related to project work include, but are not limited to: - Scope management plan (Section 5.1.3.1), - Requirements management plan (Section 5.1.3.2), - Schedule management plan (Section 6.1.3.1), - Cost management plan (Section 7.1.3.1), and - Stakeholder management plan (Section 13.2.3.1).
Executing | 4.3 |  |  |  | 4.3.1.2 (P82) | Approved change requests | These are an output of the Perform Integrated Change Control process, and include those requests reviewed and approved for implementation by the change control board (CCB).
Executing | 4.3 |  |  |  | 4.3.1.3 (P82) | Enterprise environmental factors EEF | This process is influenced by EEFs that include, - Organizational, company, or customer culture and structure of the performing or sponsor organizations - Infrastructure - Personnel administration - Stakeholder risk tolerances - Project management information system
Executing | 4.3 |  |  |  | 4.3.1.4 (P83) | Organizational process assets | This process is influenced by OPAs that include, - Standardized guidelines and work instructions - Communication and security requirements; - Issue and defect management procedures - Project files from previous projects (e.g., scope, cost, schedule, performance measurement baselines, project calendars
Executing | 4.3 |  |  | Tools | 4.3.2.1 (P83) | Expert judgment | Used to assess the inputs needed to direct and manage execution of the project management plan - Other units within the organization; - Consultants and other subject matter experts (internal and external); - Stakeholders, including customers, suppliers, or sponsors; and - Professional and technical associations.
Executing | 4.3 |  |  |  | 4.3.2.1 (P84) | Project management information system | This is part of the environmental factors, provides access to tools, such as a scheduling tool, a work authorization system, a configuration management system, an information collection and distribution system, or interfaces to other online automated systems.
Executing | 4.3 |  |  |  | 4.3.2.1 (P84) | Meetings | Meetings are used to discuss and address pertinent topics of the project when directing and managing project work.Meetings tend to be one of three types: - Information exchange; - Brainstorming, option evaluation, or design; or - Decision making.
Executing | 4.3 |  |  | Output | 4.3.3.1 (P84) | Deliverables | A deliverable is any unique and verifiable product, result or capability to perform a service that is required to be produced to complete a process, phase, or project.
Executing | 4.3 |  |  |  | 4.3.3.2 (P85) | Work performance data | These are the raw observations and measurements identified during activities being performed to carry out the project work. e.g. work completed, key performance indicators, technical performance measures
Executing | 4.3 |  |  |  | 4.3.3.3 (P85) | Change requests | A change request is a formal proposal to modify any document, deliverable, or baseline.Requests for a change may include: - Corrective action - Realigns the performance as per project management plan. - Preventive action - Ensures the future performance of the project work is aligned with the project management plan. - Defect repair - Activity to modify a nonconforming product - Updates - Changes to reflect modified or additional ideas or content.
Executing | 4.3 |  |  |  | 4.3.3.4 (P85) | Project mgt plan updates | Elements of the project management plan that may be updated
Executing | 4.3 |  |  |  | 4.3.3.5 (P86) | Project documents updates | Project documents that may be updated Requirements documentation, Project logs, Risk register and Stakeholder register
Monitoring and Controlling | 4.4 | Monitor and Control Project Work (P86) | Monitoring is an aspect of project management performed throughout the project. Continuous monitoring gives the project management team insight into the health of the project and identifies any areas that may require special attention. Monitoring includes: - Comparing actual project performance - Assessing performance - Identifying new risks - Maintaining an accurate, timely information - Monitoring implementation - Providing appropriate reporting on project progress Key benefit: Allows stakeholders to understand the current state of the project, the steps taken, and budget, schedule, and scope forecasts. | Input | 4.4.1.1 (P88) | Project management plan | Project management plan form the basis for controlling the project
Monitoring and Controlling | 4.4 |  |  |  | 4.4.1.2 (P89) | Schedule forecasts | The schedule forecasts are derived from progress against the schedule baseline and computed time estimate to complete (ETC). This is typically expressed in terms of schedule variance (SV) and schedule performance index (SPI).
Monitoring and Controlling | 4.4 |  |  |  | 4.4.1.3 (P89) | Cost forecasts | The cost forecasts are derived from progress against the cost baseline and computed estimates to complete (ETC). This is typically expressed in terms of cost variance (CV) and cost performance index (CPI). This is typically expressed in terms of cost variance (CV) and cost performance index (CPI).
Monitoring and Controlling | 4.4 |  |  |  | 4.4.1.4 (P90) | Validated changes | Approved changes that result from the Perform Integrated Change Control process require validation to ensure that the change was appropriately implemented
Monitoring and Controlling | 4.4 |  |  |  | 4.4.1.5 (P90) | Work performance information | Work performance information is circulated through communication processes. Examples of performance information are status of deliverables, implementation status for change requests, and forecasted estimates to complete.
Monitoring and Controlling | 4.4 |  |  |  | 4.4.1.6 (P90) | Enterprise environmental factors | Factors include, - Governmental or industry standards, - Organization work authorization systems, - Stakeholder risk tolerances, - Project management information system
Monitoring and Controlling | 4.4 |  |  |  | 4.4.1.7 (P91) | Organizational process assets | include, - Organizational communication requirements, - Financial controls procedures - Issue and defect management procedures, - Change control procedures - Risk control procedures, - Process measurement database, - Lessons learned
Monitoring and Controlling | 4.4 |  |  | Tools | 4.4.2.1 (P91) | Expert judgment | Used by the project management team to interpret the information provided by the monitor and control processes.
Monitoring and Controlling | 4.4 |  |  |  | 4.4.2.2 (P91) | Analytical techniques | Are applied in project management to forecast potential outcomes. Examples of analytical techniques are: Regression analysis, Grouping methods, Causal analysis, Root cause analysis, Forecasting methods, Failure mode and effect analysis (FMEA), Fault tree analysis (FTA), Reserve analysis, Trend analysis, Earned value management, and Variance analysis.
Monitoring and Controlling | 4.4 |  |  |  | 4.4.2.3 (P92) | Project management information system | Provides access to automated tools, such as scheduling, cost, and resourcing tools, performance indicators, databases, project records, and financials used during the Monitor and Control Project Work process.
Monitoring and Controlling | 4.4 |  |  |  | 4.4.2.4 (P92) | Meetings | Meetings may be face-to-face, virtual, formal, or informal. They may include project team members, stakeholders, and others involved in or affected by the project
Monitoring and Controlling | 4.4 |  |  | Output | 4.4.3.1 (P92) | Change requests | A change request is a formal proposal to modify any document, deliverable, or baseline.Requests for a change may include: - Corrective action - Realigns the performance as per project management plan. - Preventive action - Ensures the future performance of the project work is aligned with the project management plan. - Defect repair - Activity to modify a nonconforming product - Updates - Changes to reflect modified or additional ideas or content.
Monitoring and Controlling | 4.4 |  |  |  | 4.4.3.2 (P93) | Work performance reports | These are the raw observations and measurements identified during activities being performed to carry out the project work. e.g. work completed, key performance indicators, technical performance measures
Monitoring and Controlling | 4.4 |  |  |  | 4.4.3.3 (P93) | Project mgt plan updates | Elements of the project management plan that may be updated
Monitoring and Controlling | 4.4 |  |  |  | 4.4.3.4 (P94) | Project documents updates | Project documents that may be updated Requirements documentation, Project logs, Risk register and Stakeholder register
Monitoring and Controlling | 4.5 | Perform Integrated Change Control (P94) | This is the process of reviewing all change requests; approving changes and managing changes to deliverables, organizational process assets, project documents, and the project management plan; and communicating their disposition. The Perform Integrated Change Control process is conducted from project inception through completion and is the ultimate responsibility of the project manager. process includes a change control board (CCB), which is a formally chartered group responsible for reviewing, evaluating, approving, delaying, or rejecting changes to the project, and for recording and communicating such decisions. Key benefit: Allows for documented changes within the project to be considered in an integrated fashion while reducing project risk, which often arises from changes made without consideration to the overall project objectives or plans. | Input | 4.5.1.1 (P97) | Project management plan | This is the document that describes how the project will be executed, monitored, and controlled. It integrates and consolidates all of the subsidiary plans and baselines from the planning processes
Monitoring and Controlling | 4.5 |  |  |  | 4.5.1.2 (P97) | Work performance reports | These are the raw observations and measurements identified during activities being performed to carry out the project work. e.g. work completed, key performance indicators, technical performance measures
Monitoring and Controlling | 4.5 |  |  |  | 4.5.1.3 (P97) | Change requests | A change request is a formal proposal to modify any document, deliverable, or baseline.Requests for a change may include: - Corrective action - Realigns the performance as per project management plan. - Preventive action - Ensures the future performance of the project work is aligned with the project management plan. - Defect repair - Activity to modify a nonconforming product - Updates - Changes to reflect modified or additional ideas or content.
Monitoring and Controlling | 4.5 |  |  |  | 4.5.1.4 (P98) | Enterprise environmental factors | Factors include, - Governmental or industry standards, - Organization work authorization systems, - Stakeholder risk tolerances, - Project management information system
Monitoring and Controlling | 4.5 |  |  |  | 4.5.1.5 (P98) | Organizational process assets | Includes: Change control procedures, including the steps by which official organization standards, policies, plans, and other project documents will be modified, and how any changes will be approved, validated, and implemented;
Monitoring and Controlling | 4.5 |  |  | Tools | 4.5.2.1 (P98) | Expert judgment | Stakeholders may be asked to provide their expertise and may be asked to sit on the change control board (CCB). Stakeholder includes Consultants, Stakeholders, including customers or sponsors,Professional and technical associations, Industry groups, Subject matter experts (SMEs), PMOs
Monitoring and Controlling | 4.5 |  |  |  | 4.5.2.2 (P99) | Meetings | Change control board (CCB) is responsible for meeting and reviewing the change requests and approving, rejecting, or other disposition of those changes.
Monitoring and Controlling | 4.5 |  |  |  | 4.5.2.3 (P99) | Change control tools | Tools are used to manage the change requests and the resulting decisions. Additional considerations should be made for communication to assist the CCB members in their duties as well as distribute the decisions to the appropriate stakeholders.
Monitoring and Controlling | 4.5 |  |  | Output | 4.5.3.1 (P99) | Approved change requests | These are an output of the Perform Integrated Change Control process, and include those requests reviewed and approved for implementation by the change control board (CCB).
Monitoring and Controlling | 4.5 |  |  |  | 4.5.3.2 (P100) | Change log | A change log is used to document changes that occur during a project. These changes and their impact to the project in terms of time, cost, and risk, are communicated to the appropriate stakeholders. Rejected change requests are also captured in the change log.
Monitoring and Controlling | 4.5 |  |  |  | 4.5.3.3 (P100) | Project management plan updates | Elements of the project management plan that may be updated
Monitoring and Controlling | 4.5 |  |  |  | 4.5.3.4 (P100) | Project documents updates | Project documents that may be updated Requirements documentation, Project logs, Risk register and Stakeholder register
Closing | 4.6 | Close Project or Phase (P100) | Is the process of finalizing all activities across all of the Project Management Process Groups to formally complete the project or phase. Key benefit: Provides lessons learned, the formal ending of project work, and the release of organization resources to pursue new endeavors. | Input | 4.6.1.1 (P102) | Project management plan | The project management plan becomes the agreement between the project manager and project sponsor, defining what constitutes project completion.
Closing | 4.6 |  |  |  | 4.6.1.2 (P102) | Accepted deliverables | Accepted deliverables may include approved product specifications, delivery receipts, and work performance documents. Partial or interim deliverables may also be included for phased or cancelled projects.
Closing | 4.6 |  |  |  | 4.6.1.3 (P102) | Organizational process assets | Include, Project or phase closure guidelines or requirements, Historical information and lessons learned knowledge base
Closing | 4.6 |  |  | Tools | 4.6.2.1 (P102) | Expert judgment | These experts ensure the project or phase closure is performed to the appropriate standards. Sources includes, Other project managers, PMO, Professional and technical associations.
Closing | 4.6 |  |  |  | 4.6.2.2 (P103) | Analytical techniques | Analytical techniques used in project closeout are: Regression analysis, and Trend analysis.
Closing | 4.6 |  |  |  | 4.6.2.3 (P103) | Meetings | Meetings may be face-to-face, virtual, formal, or informal. This may include project team members and other stakeholders, involved in or affected by the project. Types of meetings include, but are not limited to lessons learned, closeout, user group, and review meetings.
Closing | 4.6 |  |  | Output | 4.6.3.1 (P103) | Final product, service, or result transition | This output refers to the transition of the final product, service, or result that the project was authorized to produce (or in the case of phase closure, the intermediate product, service, or result of that phase).
Closing | 4.6 |  |  |  | 4.6.3.2 (P103) | Organizational process assets updates | The organizational process assets that are updated include, Project files, Project or phase closure documents, Historical information

## Sheet1
# | 2 | Knowledge Area | Project Scope Management | PMBOK # | 5 | Total Process | 6 [ I 0 ] [ P 4 ] [E 0 ] [ M&C 2 ] [ C 0 ]
Process Gourp | Process # | Process | Ellaboration | Process Flow | PF# | PF Details
Initiating
Planning | 5.1 | Plan Scope Management (P107) | Is the process of creating a scope management plan that documents how the project scope will be defined, validated, and controlled. Key benefit: It provides guidance and direction on how scope will be managed throughout the project. | Input | 5.1.1.1 (P) | Project management plan
Planning | 5.1 |  |  |  | 5.1.1.2 (P) | Project charter
Planning | 5.1 |  |  |  | 5.1.1.3 (P) | Enterprise environmental factors EEF
Planning | 5.1 |  |  |  | 5.1.1.4 (P) | Organizational process assets OPA
Planning | 5.1 |  |  | Tools | 5.1.2.1 (P) | Expert judgment
Planning | 5.1 |  |  |  | 5.1.2.2 (P) | Meetings
|  |  |  | Output | 5.1.3.1 (P) | Scope management plan
Planning | 5.1 |  |  |  | 5.1.3.2 (P) | Requirements management plan
Planning | 5.2 | Collect Requirements (P110) | Process of determining, documenting, and managing stakeholder needs and requirements to meet project objectives. Key benefit: It provides the basis for defining and managing the project scope including product scope. | Input | 5.2.1.1 (P) | Scope management plan
Planning | 5.2 |  |  |  | 5.2.1.2 (P) | Requirements management plan
Planning | 4.2 |  |  |  | 5.2.1.3 (P) | Stakeholder management plan
Planning | 4.2 |  |  |  | 5.2.1.4 (P) | Project charter
[5 empty] | 5.2.1.5 (P) | Stakeholder register
Planning | 4.2 |  |  | Tools | 5.2.2.1 (P) | Interviews
[5 empty] | 5.2.2.2 (P) | Focus groups
[5 empty] | 5.2.2.3 (P) | Facilitated workshops
[5 empty] | 5.2.2.4 (P) | Group creativity techniques
[5 empty] | 5.2.2.5 (P) | Group decision-making techniques
[5 empty] | 5.2.2.6 (P) | Questionnaires and surveys
[5 empty] | 5.2.2.7 (P) | Observations
[5 empty] | 5.2.2.8 (P) | Prototypes
[5 empty] | 5.2.2.9 (P) | Benchmarking
[5 empty] | 5.2.2.10 (P) | Context diagrams
Planning | 4.2 |  |  |  | 5.2.2.11 (P) | Document analysis
|  |  |  | Output | 5.2.3.1 (P) | Requirements documentation
Planning | 4.2 |  |  |  | 5.2.3.2 (P) | Requirements traceability matrix
Planning | 5.3 | Define Scope (P120) | Process of developing a detailed description of the project and product Key benefit: It describes the project, service, or result boundaries by defining which of the requirements collected will be included in and excluded from the project scope. | Input | 5.3.1.1 (P) | Scope management plan
Planning | 5.3 |  |  |  | 5.3.1.2 (P) | Project charter
Planning | 5.3 |  |  |  | 5.3.1.3 (P) | Requirements documentation
Planning | 5.3 |  |  |  | 5.3.1.4 (P) | Organizational process assets
Planning | 5.3 |  |  | Tools | 5.3.2.1 (P) | Expert judgment
Planning | 5.3 |  |  |  | 5.3.2.2 (P) | Product analysis
[5 empty] | 5.3.2.3 (P) | Alternatives generation
Planning | 5.3 |  |  |  | 5.3.2.4 (P) | Facilitated workshops
Planning | 5.3 |  |  | Output | 5.3.3.1 (P) | Project scope statement
Planning | 5.3 |  |  |  | 5.3.3.2 (P) | Project documents updates
Planning | 5.4 | Create WBS (P125) | Process of subdividing project deliverables and project work into smaller, more manageable components. Key benefit: It provides a structured vision of what has to be delivered. | Input | 5.4.1.1 (P) | Scope management plan
Planning | 5.4 |  |  |  | 5.4.1.2 (P) | Project scope statement
Planning | 5.4 |  |  |  | 5.4.1.3 (P) | Requirements documentation
Planning | 5.4 |  |  |  | 5.4.1.4 (P) | Enterprise environmental factors
Planning | 5.4 |  |  |  | 5.4.1.5 (P) | Organizational process assets
Planning | 5.4 |  |  | Tools | 5.4.2.1 (P) | Decomposition
Planning | 5.4 |  |  |  | 5.4.2.2 (P) | Expert judgment
Planning | 5.4 |  |  | Output | 4.4.3.1 (P92) | Change requests
Planning | 5.4 |  |  |  | 4.4.3.2 (P93) | Work performance reports
Planning | 5.4 |  |  |  | 4.4.3.3 (P93) | Project mgt plan updates
Planning | 5.4 |  |  |  | 4.4.3.4 (P94) | Project documents updates
Executing
Monitoring and Controlling | 5.5 | Validate Scope | Key benefit: | Input | 4.5.1.1 (P97) | Project management plan
Monitoring and Controlling | 5.5 |  |  |  | 4.5.1.2 (P97) | Work performance reports
Monitoring and Controlling | 5.5 |  |  |  | 4.5.1.3 (P97) | Change requests
Monitoring and Controlling | 5.5 |  |  |  | 4.5.1.4 (P98) | Enterprise environmental factors
Monitoring and Controlling | 5.5 |  |  |  | 4.5.1.5 (P98) | Organizational process assets
Monitoring and Controlling | 5.5 |  |  | Tools | 4.5.2.1 (P98) | Expert judgment
Monitoring and Controlling | 5.5 |  |  |  | 4.5.2.2 (P99) | Meetings
Monitoring and Controlling | 5.5 |  |  |  | 4.5.2.3 (P99) | Change control tools
Monitoring and Controlling | 5.5 |  |  | Output | 4.5.3.1 (P99) | Approved change requests
Monitoring and Controlling | 5.5 |  |  |  | 4.5.3.2 (P100) | Change log
Monitoring and Controlling | 5.5 |  |  |  | 4.5.3.3 (P100) | Project management plan updates
Monitoring and Controlling | 5.5 |  |  |  | 4.5.3.4 (P100) | Project documents updates
Monitoring and Controlling | 5.6 | Close Project or Phase (P100) | Key benefit: | Input | 4.6.1.1 (P102) | Project management plan
Monitoring and Controlling | 5.6 |  |  |  | 4.6.1.2 (P102) | Accepted deliverables
Monitoring and Controlling | 5.6 |  |  |  | 4.6.1.3 (P102) | Organizational process assets
Monitoring and Controlling | 5.6 |  |  | Tools | 4.6.2.1 (P102) | Expert judgment
Monitoring and Controlling | 5.6 |  |  |  | 4.6.2.2 (P103) | Analytical techniques
Monitoring and Controlling | 5.6 |  |  |  | 4.6.2.3 (P103) | Meetings
Monitoring and Controlling | 5.6 |  |  | Output | 4.6.3.1 (P103) | Final product, service, or result transition
Monitoring and Controlling | 5.6 |  |  |  | 4.6.3.2 (P103) | Organizational process assets updates
Closing

## 5. Project Scope Mgt
# | PMBOK # | Knowlwdgee Area | Process Gourp | Process # | Process | Process Flow
2 | 5 | Project Scope Management | I
|  |  | P | 5.1 | 5.1 Plan Scope Management
|  |  |  | 5.2 | 5.2 Collect Requirements
|  |  |  | 5.3 | 5.3 Define Scope
|  |  |  | 5.4 | 5.4 Create WBS
E
|  |  | M | 5.5 | 5.5 Validate Scope
|  |  |  | 5.6 | 5.6 Control Scope
C
| 1 |  |  | 6

## Project Time Mgt
# | PMBOK # | Knowlwdgee Area | Process Gourp | Process # | Process | Process Flow
1 | 4 | Project Integration Management | I | 4.1 | 4.1 Develop Project Charter | I | 4.1.1.1 | Project statement of work
[7 empty] | 4.1.1.2 | Business case
[7 empty] | 4.1.1.3 | Agreements
[7 empty] | 4.1.1.4 | Enterprise environmental factors
[7 empty] | 4.1.1.5 | Organizational process assets
[6 empty] | T | 4.1.2.1 | Expert judgment
[7 empty] | 4.1.2.2 | Facilitation techniques
[6 empty] | O | 4.1.3.1 | Project charter
|  |  | P | 4.2 | 4.2 Develop Project Management Plan | I | 4.2.1.1 | Project charter
[7 empty] | 4.2.1.2 | Outputs from other processes
[7 empty] | 4.2.1.3 | Enterprise environmental factors
[7 empty] | 4.2.1.4 | Organizational process assets
[6 empty] | T | 4.2.2.1 | Expert judgment
[7 empty] | 4.2.2.2 | Facilitation techniques
[6 empty] | O | 4.2.3.1 | Project management plan
|  |  | E | 4.3 | 4.3 Direct and Manage Project Work | I | 4.3.1.1 | Project management plan
[7 empty] | 4.3.1.2 | Approved change requests
[7 empty] | 4.3.1.3 | Enterprise environmental factors
[7 empty] | 4.3.1.4 | Organizational process assets
[6 empty] | T | 4.3.2.1 | Expert judgment
[7 empty] | 4.3.2.1 | Project management information system
[7 empty] | 4.3.2.1 | Meetings
[6 empty] | O | 4.3.3.1 | Deliverables
[7 empty] | 4.3.3.2 | Work performance data
[7 empty] | 4.3.3.3 | Change requests
[7 empty] | 4.3.3.4 | Project management plan updates
[7 empty] | 4.3.3.5 | Project documents updates
|  |  | M | 4.4 | 4.4 Monitor and Control Project Work | I | 4.4.1.1 | Project management plan
[7 empty] | 4.4.1.2 | Schedule forecasts
[7 empty] | 4.4.1.3 | Cost forecasts
[7 empty] | 4.4.1.4 | Validated changes
[7 empty] | 4.4.1.5 | Work performance information
[7 empty] | 4.4.1.6 | Enterprise environmental factors
[7 empty] | 4.4.1.7 | Organizational process assets
[6 empty] | T | 4.4.2.1 | Expert judgment
[7 empty] | 4.4.2.2 | Analytical techniques
[7 empty] | 4.4.2.3 | Project management information system
[7 empty] | 4.4.2.4 | Meetings
[6 empty] | O | 4.4.3.1 | Change requests
[7 empty] | 4.4.3.2 | Work performance reports
[7 empty] | 4.4.3.3 | Project management plan updates
[7 empty] | 4.4.3.4 | Project documents updates
|  |  |  | 4.5 | 4.5 Perform Integrated Change Control | I | 4.5.1.1 | Project management plan
[7 empty] | 4.5.1.2 | Work performance reports
[7 empty] | 4.5.1.3 | Change requests
[7 empty] | 4.5.1.4 | Enterprise environmental factors
[7 empty] | 4.5.1.5 | Organizational process assets
[6 empty] | T | 4.5.2.1 | Expert judgment
[7 empty] | 4.5.2.2 | Meetings
[7 empty] | 4.5.2.3 | Change control tools
[6 empty] | O | 4.5.3.1 | Approved change requests
[7 empty] | 4.5.3.2 | Change log
[7 empty] | 4.5.3.3 | Project management plan updates
[7 empty] | 4.5.3.4 | Project documents updates
|  |  | C | 4.6 | 4.6 Close Project or Phase | I | 4.6.1.1 | Project management plan
[7 empty] | 4.6.1.2 | Accepted deliverables
[7 empty] | 4.6.1.3 | Organizational process assets
[6 empty] | T | 4.6.2.1 | Expert judgment
[7 empty] | 4.6.2.2 | Analytical techniques
[7 empty] | 4.6.2.3 | Meetings
[6 empty] | O | 4.6.3.1 | Final product, service, or result transition
[7 empty] | 4.6.3.2 | Organizational process assets updates
2 | 5 | Project Scope Management | I
|  |  | P | 5.1 | 5.1 Plan Scope Management
|  |  |  | 5.2 | 5.2 Collect Requirements
|  |  |  | 5.3 | 5.3 Define Scope
|  |  |  | 5.4 | 5.4 Create WBS
E
|  |  | M | 5.5 | 5.5 Validate Scope
|  |  |  | 5.6 | 5.6 Control Scope
C
3 | 6 | Project Time Management | I
|  |  | P | 6.1 | 6.1 Plan Schedule Management
|  |  |  | 6.2 | 6.2 Define Activities
|  |  |  | 6.3 | 6.3 Sequence Activities
|  |  |  | 6.4 | 6.4 Estimate Activity Resources
|  |  |  | 6.5 | 6.5 Estimate Activity Durations
|  |  |  | 6.6 | 6.6 Develop Schedule
E
|  |  | M | 6.7 | 6.7 Control Schedule
C
4 | 7 | Project Cost Management | I
|  |  | P | 7.1 | 7.1 Plan Cost Management
|  |  |  | 7.2 | 7.2 Estimate Costs
|  |  |  | 7.3 | 7.3 Determine Budget
E
|  |  | M | 7.4 | 7.4 Control Costs
C
5 | 8 | Project Quality Management | I
|  |  | P | 8.1 | 8.1 Plan Quality Management
|  |  | E | 8.2 | 8.2 Perform Quality Assurance
|  |  | M | 8.3 | 8.3 Control Quality
C
6 | 9 | Project Human Resource Management | I
|  |  | P | 9.1 | 9.1 Plan Human Resource Management
|  |  | E | 9.2 | 9.2 Acquire Project Team
|  |  |  | 9.3 | 9.3 Develop Project Team
|  |  |  | 9.4 | 9.4 Manage Project Team
M
C
7 | 10 | Project Communications Management | I
|  |  | P | 10.1 | 10.1 Plan Communications Management
|  |  | E | 10.2 | 10.2 Manage Communications
|  |  | M | 10.3 | 10.3 Control Communications
C
8 | 11 | Project Risk Management | I
|  |  | P | 11.1 | 11.1 Plan Risk Management
|  |  |  | 11.2 | 11.2 Identify Risks
|  |  |  | 11.3 | 11.3 Perform Qualitative Risk Analysis
|  |  |  | 11.4 | 11.4 Perform Quantitative Risk Analysis
|  |  |  | 11.5 | 11.5 Plan Risk Responses
E
|  |  | M | 11.6 | 11.6 Control Risks
C
9 | 12 | Project Procurement Management | I
|  |  | P | 12.1 | 12.1 Plan Procurement Management
|  |  | E | 12.2 | 12.2 Conduct Procurements
|  |  | M | 12.3 | 12.3 Control Procurements
|  |  | C | 12.4 | 12.4 Close Procurements
10 | 13 | Project Stakeholder Management | I | 13.1 | 13.1 Identify Stakeholders
|  |  | P | 13.2 | 13.2 Plan Stakeholder Management
|  |  | E | 13.3 | 13.3 Manage Stakeholder Engagement
|  |  | M | 13.4 | 13.4 Control Stakeholder Engagement
C
| 10 |  |  | 47

## Project Cost Mgt
# | PMBOK # | Knowlwdgee Area | Process Gourp | Process # | Process | Process Flow
1 | 4 | Project Integration Management | I | 4.1 | 4.1 Develop Project Charter | I | 4.1.1.1 | Project statement of work
[7 empty] | 4.1.1.2 | Business case
[7 empty] | 4.1.1.3 | Agreements
[7 empty] | 4.1.1.4 | Enterprise environmental factors
[7 empty] | 4.1.1.5 | Organizational process assets
[6 empty] | T | 4.1.2.1 | Expert judgment
[7 empty] | 4.1.2.2 | Facilitation techniques
[6 empty] | O | 4.1.3.1 | Project charter
|  |  | P | 4.2 | 4.2 Develop Project Management Plan | I | 4.2.1.1 | Project charter
[7 empty] | 4.2.1.2 | Outputs from other processes
[7 empty] | 4.2.1.3 | Enterprise environmental factors
[7 empty] | 4.2.1.4 | Organizational process assets
[6 empty] | T | 4.2.2.1 | Expert judgment
[7 empty] | 4.2.2.2 | Facilitation techniques
[6 empty] | O | 4.2.3.1 | Project management plan
|  |  | E | 4.3 | 4.3 Direct and Manage Project Work | I | 4.3.1.1 | Project management plan
[7 empty] | 4.3.1.2 | Approved change requests
[7 empty] | 4.3.1.3 | Enterprise environmental factors
[7 empty] | 4.3.1.4 | Organizational process assets
[6 empty] | T | 4.3.2.1 | Expert judgment
[7 empty] | 4.3.2.1 | Project management information system
[7 empty] | 4.3.2.1 | Meetings
[6 empty] | O | 4.3.3.1 | Deliverables
[7 empty] | 4.3.3.2 | Work performance data
[7 empty] | 4.3.3.3 | Change requests
[7 empty] | 4.3.3.4 | Project management plan updates
[7 empty] | 4.3.3.5 | Project documents updates
|  |  | M | 4.4 | 4.4 Monitor and Control Project Work | I | 4.4.1.1 | Project management plan
[7 empty] | 4.4.1.2 | Schedule forecasts
[7 empty] | 4.4.1.3 | Cost forecasts
[7 empty] | 4.4.1.4 | Validated changes
[7 empty] | 4.4.1.5 | Work performance information
[7 empty] | 4.4.1.6 | Enterprise environmental factors
[7 empty] | 4.4.1.7 | Organizational process assets
[6 empty] | T | 4.4.2.1 | Expert judgment
[7 empty] | 4.4.2.2 | Analytical techniques
[7 empty] | 4.4.2.3 | Project management information system
[7 empty] | 4.4.2.4 | Meetings
[6 empty] | O | 4.4.3.1 | Change requests
[7 empty] | 4.4.3.2 | Work performance reports
[7 empty] | 4.4.3.3 | Project management plan updates
[7 empty] | 4.4.3.4 | Project documents updates
|  |  |  | 4.5 | 4.5 Perform Integrated Change Control | I | 4.5.1.1 | Project management plan
[7 empty] | 4.5.1.2 | Work performance reports
[7 empty] | 4.5.1.3 | Change requests
[7 empty] | 4.5.1.4 | Enterprise environmental factors
[7 empty] | 4.5.1.5 | Organizational process assets
[6 empty] | T | 4.5.2.1 | Expert judgment
[7 empty] | 4.5.2.2 | Meetings
[7 empty] | 4.5.2.3 | Change control tools
[6 empty] | O | 4.5.3.1 | Approved change requests
[7 empty] | 4.5.3.2 | Change log
[7 empty] | 4.5.3.3 | Project management plan updates
[7 empty] | 4.5.3.4 | Project documents updates
|  |  | C | 4.6 | 4.6 Close Project or Phase | I | 4.6.1.1 | Project management plan
[7 empty] | 4.6.1.2 | Accepted deliverables
[7 empty] | 4.6.1.3 | Organizational process assets
[6 empty] | T | 4.6.2.1 | Expert judgment
[7 empty] | 4.6.2.2 | Analytical techniques
[7 empty] | 4.6.2.3 | Meetings
[6 empty] | O | 4.6.3.1 | Final product, service, or result transition
[7 empty] | 4.6.3.2 | Organizational process assets updates
2 | 5 | Project Scope Management | I
|  |  | P | 5.1 | 5.1 Plan Scope Management
|  |  |  | 5.2 | 5.2 Collect Requirements
|  |  |  | 5.3 | 5.3 Define Scope
|  |  |  | 5.4 | 5.4 Create WBS
E
|  |  | M | 5.5 | 5.5 Validate Scope
|  |  |  | 5.6 | 5.6 Control Scope
C
3 | 6 | Project Time Management | I
|  |  | P | 6.1 | 6.1 Plan Schedule Management
|  |  |  | 6.2 | 6.2 Define Activities
|  |  |  | 6.3 | 6.3 Sequence Activities
|  |  |  | 6.4 | 6.4 Estimate Activity Resources
|  |  |  | 6.5 | 6.5 Estimate Activity Durations
|  |  |  | 6.6 | 6.6 Develop Schedule
E
|  |  | M | 6.7 | 6.7 Control Schedule
C
4 | 7 | Project Cost Management | I
|  |  | P | 7.1 | 7.1 Plan Cost Management
|  |  |  | 7.2 | 7.2 Estimate Costs
|  |  |  | 7.3 | 7.3 Determine Budget
E
|  |  | M | 7.4 | 7.4 Control Costs
C
5 | 8 | Project Quality Management | I
|  |  | P | 8.1 | 8.1 Plan Quality Management
|  |  | E | 8.2 | 8.2 Perform Quality Assurance
|  |  | M | 8.3 | 8.3 Control Quality
C
6 | 9 | Project Human Resource Management | I
|  |  | P | 9.1 | 9.1 Plan Human Resource Management
|  |  | E | 9.2 | 9.2 Acquire Project Team
|  |  |  | 9.3 | 9.3 Develop Project Team
|  |  |  | 9.4 | 9.4 Manage Project Team
M
C
7 | 10 | Project Communications Management | I
|  |  | P | 10.1 | 10.1 Plan Communications Management
|  |  | E | 10.2 | 10.2 Manage Communications
|  |  | M | 10.3 | 10.3 Control Communications
C
8 | 11 | Project Risk Management | I
|  |  | P | 11.1 | 11.1 Plan Risk Management
|  |  |  | 11.2 | 11.2 Identify Risks
|  |  |  | 11.3 | 11.3 Perform Qualitative Risk Analysis
|  |  |  | 11.4 | 11.4 Perform Quantitative Risk Analysis
|  |  |  | 11.5 | 11.5 Plan Risk Responses
E
|  |  | M | 11.6 | 11.6 Control Risks
C
9 | 12 | Project Procurement Management | I
|  |  | P | 12.1 | 12.1 Plan Procurement Management
|  |  | E | 12.2 | 12.2 Conduct Procurements
|  |  | M | 12.3 | 12.3 Control Procurements
|  |  | C | 12.4 | 12.4 Close Procurements
10 | 13 | Project Stakeholder Management | I | 13.1 | 13.1 Identify Stakeholders
|  |  | P | 13.2 | 13.2 Plan Stakeholder Management
|  |  | E | 13.3 | 13.3 Manage Stakeholder Engagement
|  |  | M | 13.4 | 13.4 Control Stakeholder Engagement
C
| 10 |  |  | 47

## Project Quality Mgt
# | PMBOK # | Knowlwdgee Area | Process Gourp | Process # | Process | Process Flow
1 | 4 | Project Integration Management | I | 4.1 | 4.1 Develop Project Charter | I | 4.1.1.1 | Project statement of work
[7 empty] | 4.1.1.2 | Business case
[7 empty] | 4.1.1.3 | Agreements
[7 empty] | 4.1.1.4 | Enterprise environmental factors
[7 empty] | 4.1.1.5 | Organizational process assets
[6 empty] | T | 4.1.2.1 | Expert judgment
[7 empty] | 4.1.2.2 | Facilitation techniques
[6 empty] | O | 4.1.3.1 | Project charter
|  |  | P | 4.2 | 4.2 Develop Project Management Plan | I | 4.2.1.1 | Project charter
[7 empty] | 4.2.1.2 | Outputs from other processes
[7 empty] | 4.2.1.3 | Enterprise environmental factors
[7 empty] | 4.2.1.4 | Organizational process assets
[6 empty] | T | 4.2.2.1 | Expert judgment
[7 empty] | 4.2.2.2 | Facilitation techniques
[6 empty] | O | 4.2.3.1 | Project management plan
|  |  | E | 4.3 | 4.3 Direct and Manage Project Work | I | 4.3.1.1 | Project management plan
[7 empty] | 4.3.1.2 | Approved change requests
[7 empty] | 4.3.1.3 | Enterprise environmental factors
[7 empty] | 4.3.1.4 | Organizational process assets
[6 empty] | T | 4.3.2.1 | Expert judgment
[7 empty] | 4.3.2.1 | Project management information system
[7 empty] | 4.3.2.1 | Meetings
[6 empty] | O | 4.3.3.1 | Deliverables
[7 empty] | 4.3.3.2 | Work performance data
[7 empty] | 4.3.3.3 | Change requests
[7 empty] | 4.3.3.4 | Project management plan updates
[7 empty] | 4.3.3.5 | Project documents updates
|  |  | M | 4.4 | 4.4 Monitor and Control Project Work | I | 4.4.1.1 | Project management plan
[7 empty] | 4.4.1.2 | Schedule forecasts
[7 empty] | 4.4.1.3 | Cost forecasts
[7 empty] | 4.4.1.4 | Validated changes
[7 empty] | 4.4.1.5 | Work performance information
[7 empty] | 4.4.1.6 | Enterprise environmental factors
[7 empty] | 4.4.1.7 | Organizational process assets
[6 empty] | T | 4.4.2.1 | Expert judgment
[7 empty] | 4.4.2.2 | Analytical techniques
[7 empty] | 4.4.2.3 | Project management information system
[7 empty] | 4.4.2.4 | Meetings
[6 empty] | O | 4.4.3.1 | Change requests
[7 empty] | 4.4.3.2 | Work performance reports
[7 empty] | 4.4.3.3 | Project management plan updates
[7 empty] | 4.4.3.4 | Project documents updates
|  |  |  | 4.5 | 4.5 Perform Integrated Change Control | I | 4.5.1.1 | Project management plan
[7 empty] | 4.5.1.2 | Work performance reports
[7 empty] | 4.5.1.3 | Change requests
[7 empty] | 4.5.1.4 | Enterprise environmental factors
[7 empty] | 4.5.1.5 | Organizational process assets
[6 empty] | T | 4.5.2.1 | Expert judgment
[7 empty] | 4.5.2.2 | Meetings
[7 empty] | 4.5.2.3 | Change control tools
[6 empty] | O | 4.5.3.1 | Approved change requests
[7 empty] | 4.5.3.2 | Change log
[7 empty] | 4.5.3.3 | Project management plan updates
[7 empty] | 4.5.3.4 | Project documents updates
|  |  | C | 4.6 | 4.6 Close Project or Phase | I | 4.6.1.1 | Project management plan
[7 empty] | 4.6.1.2 | Accepted deliverables
[7 empty] | 4.6.1.3 | Organizational process assets
[6 empty] | T | 4.6.2.1 | Expert judgment
[7 empty] | 4.6.2.2 | Analytical techniques
[7 empty] | 4.6.2.3 | Meetings
[6 empty] | O | 4.6.3.1 | Final product, service, or result transition
[7 empty] | 4.6.3.2 | Organizational process assets updates
2 | 5 | Project Scope Management | I
|  |  | P | 5.1 | 5.1 Plan Scope Management
|  |  |  | 5.2 | 5.2 Collect Requirements
|  |  |  | 5.3 | 5.3 Define Scope
|  |  |  | 5.4 | 5.4 Create WBS
E
|  |  | M | 5.5 | 5.5 Validate Scope
|  |  |  | 5.6 | 5.6 Control Scope
C
3 | 6 | Project Time Management | I
|  |  | P | 6.1 | 6.1 Plan Schedule Management
|  |  |  | 6.2 | 6.2 Define Activities
|  |  |  | 6.3 | 6.3 Sequence Activities
|  |  |  | 6.4 | 6.4 Estimate Activity Resources
|  |  |  | 6.5 | 6.5 Estimate Activity Durations
|  |  |  | 6.6 | 6.6 Develop Schedule
E
|  |  | M | 6.7 | 6.7 Control Schedule
C
4 | 7 | Project Cost Management | I
|  |  | P | 7.1 | 7.1 Plan Cost Management
|  |  |  | 7.2 | 7.2 Estimate Costs
|  |  |  | 7.3 | 7.3 Determine Budget
E
|  |  | M | 7.4 | 7.4 Control Costs
C
5 | 8 | Project Quality Management | I
|  |  | P | 8.1 | 8.1 Plan Quality Management
|  |  | E | 8.2 | 8.2 Perform Quality Assurance
|  |  | M | 8.3 | 8.3 Control Quality
C
6 | 9 | Project Human Resource Management | I
|  |  | P | 9.1 | 9.1 Plan Human Resource Management
|  |  | E | 9.2 | 9.2 Acquire Project Team
|  |  |  | 9.3 | 9.3 Develop Project Team
|  |  |  | 9.4 | 9.4 Manage Project Team
M
C
7 | 10 | Project Communications Management | I
|  |  | P | 10.1 | 10.1 Plan Communications Management
|  |  | E | 10.2 | 10.2 Manage Communications
|  |  | M | 10.3 | 10.3 Control Communications
C
8 | 11 | Project Risk Management | I
|  |  | P | 11.1 | 11.1 Plan Risk Management
|  |  |  | 11.2 | 11.2 Identify Risks
|  |  |  | 11.3 | 11.3 Perform Qualitative Risk Analysis
|  |  |  | 11.4 | 11.4 Perform Quantitative Risk Analysis
|  |  |  | 11.5 | 11.5 Plan Risk Responses
E
|  |  | M | 11.6 | 11.6 Control Risks
C
9 | 12 | Project Procurement Management | I
|  |  | P | 12.1 | 12.1 Plan Procurement Management
|  |  | E | 12.2 | 12.2 Conduct Procurements
|  |  | M | 12.3 | 12.3 Control Procurements
|  |  | C | 12.4 | 12.4 Close Procurements
10 | 13 | Project Stakeholder Management | I | 13.1 | 13.1 Identify Stakeholders
|  |  | P | 13.2 | 13.2 Plan Stakeholder Management
|  |  | E | 13.3 | 13.3 Manage Stakeholder Engagement
|  |  | M | 13.4 | 13.4 Control Stakeholder Engagement
C
| 10 |  |  | 47

## Project Human Resource Mgt
# | PMBOK # | Knowlwdgee Area | Process Gourp | Process # | Process | Process Flow
1 | 4 | Project Integration Management | I | 4.1 | 4.1 Develop Project Charter | I | 4.1.1.1 | Project statement of work
[7 empty] | 4.1.1.2 | Business case
[7 empty] | 4.1.1.3 | Agreements
[7 empty] | 4.1.1.4 | Enterprise environmental factors
[7 empty] | 4.1.1.5 | Organizational process assets
[6 empty] | T | 4.1.2.1 | Expert judgment
[7 empty] | 4.1.2.2 | Facilitation techniques
[6 empty] | O | 4.1.3.1 | Project charter
|  |  | P | 4.2 | 4.2 Develop Project Management Plan | I | 4.2.1.1 | Project charter
[7 empty] | 4.2.1.2 | Outputs from other processes
[7 empty] | 4.2.1.3 | Enterprise environmental factors
[7 empty] | 4.2.1.4 | Organizational process assets
[6 empty] | T | 4.2.2.1 | Expert judgment
[7 empty] | 4.2.2.2 | Facilitation techniques
[6 empty] | O | 4.2.3.1 | Project management plan
|  |  | E | 4.3 | 4.3 Direct and Manage Project Work | I | 4.3.1.1 | Project management plan
[7 empty] | 4.3.1.2 | Approved change requests
[7 empty] | 4.3.1.3 | Enterprise environmental factors
[7 empty] | 4.3.1.4 | Organizational process assets
[6 empty] | T | 4.3.2.1 | Expert judgment
[7 empty] | 4.3.2.1 | Project management information system
[7 empty] | 4.3.2.1 | Meetings
[6 empty] | O | 4.3.3.1 | Deliverables
[7 empty] | 4.3.3.2 | Work performance data
[7 empty] | 4.3.3.3 | Change requests
[7 empty] | 4.3.3.4 | Project management plan updates
[7 empty] | 4.3.3.5 | Project documents updates
|  |  | M | 4.4 | 4.4 Monitor and Control Project Work | I | 4.4.1.1 | Project management plan
[7 empty] | 4.4.1.2 | Schedule forecasts
[7 empty] | 4.4.1.3 | Cost forecasts
[7 empty] | 4.4.1.4 | Validated changes
[7 empty] | 4.4.1.5 | Work performance information
[7 empty] | 4.4.1.6 | Enterprise environmental factors
[7 empty] | 4.4.1.7 | Organizational process assets
[6 empty] | T | 4.4.2.1 | Expert judgment
[7 empty] | 4.4.2.2 | Analytical techniques
[7 empty] | 4.4.2.3 | Project management information system
[7 empty] | 4.4.2.4 | Meetings
[6 empty] | O | 4.4.3.1 | Change requests
[7 empty] | 4.4.3.2 | Work performance reports
[7 empty] | 4.4.3.3 | Project management plan updates
[7 empty] | 4.4.3.4 | Project documents updates
|  |  |  | 4.5 | 4.5 Perform Integrated Change Control | I | 4.5.1.1 | Project management plan
[7 empty] | 4.5.1.2 | Work performance reports
[7 empty] | 4.5.1.3 | Change requests
[7 empty] | 4.5.1.4 | Enterprise environmental factors
[7 empty] | 4.5.1.5 | Organizational process assets
[6 empty] | T | 4.5.2.1 | Expert judgment
[7 empty] | 4.5.2.2 | Meetings
[7 empty] | 4.5.2.3 | Change control tools
[6 empty] | O | 4.5.3.1 | Approved change requests
[7 empty] | 4.5.3.2 | Change log
[7 empty] | 4.5.3.3 | Project management plan updates
[7 empty] | 4.5.3.4 | Project documents updates
|  |  | C | 4.6 | 4.6 Close Project or Phase | I | 4.6.1.1 | Project management plan
[7 empty] | 4.6.1.2 | Accepted deliverables
[7 empty] | 4.6.1.3 | Organizational process assets
[6 empty] | T | 4.6.2.1 | Expert judgment
[7 empty] | 4.6.2.2 | Analytical techniques
[7 empty] | 4.6.2.3 | Meetings
[6 empty] | O | 4.6.3.1 | Final product, service, or result transition
[7 empty] | 4.6.3.2 | Organizational process assets updates
2 | 5 | Project Scope Management | I
|  |  | P | 5.1 | 5.1 Plan Scope Management
|  |  |  | 5.2 | 5.2 Collect Requirements
|  |  |  | 5.3 | 5.3 Define Scope
|  |  |  | 5.4 | 5.4 Create WBS
E
|  |  | M | 5.5 | 5.5 Validate Scope
|  |  |  | 5.6 | 5.6 Control Scope
C
3 | 6 | Project Time Management | I
|  |  | P | 6.1 | 6.1 Plan Schedule Management
|  |  |  | 6.2 | 6.2 Define Activities
|  |  |  | 6.3 | 6.3 Sequence Activities
|  |  |  | 6.4 | 6.4 Estimate Activity Resources
|  |  |  | 6.5 | 6.5 Estimate Activity Durations
|  |  |  | 6.6 | 6.6 Develop Schedule
E
|  |  | M | 6.7 | 6.7 Control Schedule
C
4 | 7 | Project Cost Management | I
|  |  | P | 7.1 | 7.1 Plan Cost Management
|  |  |  | 7.2 | 7.2 Estimate Costs
|  |  |  | 7.3 | 7.3 Determine Budget
E
|  |  | M | 7.4 | 7.4 Control Costs
C
5 | 8 | Project Quality Management | I
|  |  | P | 8.1 | 8.1 Plan Quality Management
|  |  | E | 8.2 | 8.2 Perform Quality Assurance
|  |  | M | 8.3 | 8.3 Control Quality
C
6 | 9 | Project Human Resource Management | I
|  |  | P | 9.1 | 9.1 Plan Human Resource Management
|  |  | E | 9.2 | 9.2 Acquire Project Team
|  |  |  | 9.3 | 9.3 Develop Project Team
|  |  |  | 9.4 | 9.4 Manage Project Team
M
C
7 | 10 | Project Communications Management | I
|  |  | P | 10.1 | 10.1 Plan Communications Management
|  |  | E | 10.2 | 10.2 Manage Communications
|  |  | M | 10.3 | 10.3 Control Communications
C
8 | 11 | Project Risk Management | I
|  |  | P | 11.1 | 11.1 Plan Risk Management
|  |  |  | 11.2 | 11.2 Identify Risks
|  |  |  | 11.3 | 11.3 Perform Qualitative Risk Analysis
|  |  |  | 11.4 | 11.4 Perform Quantitative Risk Analysis
|  |  |  | 11.5 | 11.5 Plan Risk Responses
E
|  |  | M | 11.6 | 11.6 Control Risks
C
9 | 12 | Project Procurement Management | I
|  |  | P | 12.1 | 12.1 Plan Procurement Management
|  |  | E | 12.2 | 12.2 Conduct Procurements
|  |  | M | 12.3 | 12.3 Control Procurements
|  |  | C | 12.4 | 12.4 Close Procurements
10 | 13 | Project Stakeholder Management | I | 13.1 | 13.1 Identify Stakeholders
|  |  | P | 13.2 | 13.2 Plan Stakeholder Management
|  |  | E | 13.3 | 13.3 Manage Stakeholder Engagement
|  |  | M | 13.4 | 13.4 Control Stakeholder Engagement
C
| 10 |  |  | 47

## Project Communications Mgt
# | PMBOK # | Knowlwdgee Area | Process Gourp | Process # | Process | Process Flow
1 | 4 | Project Integration Management | I | 4.1 | 4.1 Develop Project Charter | I | 4.1.1.1 | Project statement of work
[7 empty] | 4.1.1.2 | Business case
[7 empty] | 4.1.1.3 | Agreements
[7 empty] | 4.1.1.4 | Enterprise environmental factors
[7 empty] | 4.1.1.5 | Organizational process assets
[6 empty] | T | 4.1.2.1 | Expert judgment
[7 empty] | 4.1.2.2 | Facilitation techniques
[6 empty] | O | 4.1.3.1 | Project charter
|  |  | P | 4.2 | 4.2 Develop Project Management Plan | I | 4.2.1.1 | Project charter
[7 empty] | 4.2.1.2 | Outputs from other processes
[7 empty] | 4.2.1.3 | Enterprise environmental factors
[7 empty] | 4.2.1.4 | Organizational process assets
[6 empty] | T | 4.2.2.1 | Expert judgment
[7 empty] | 4.2.2.2 | Facilitation techniques
[6 empty] | O | 4.2.3.1 | Project management plan
|  |  | E | 4.3 | 4.3 Direct and Manage Project Work | I | 4.3.1.1 | Project management plan
[7 empty] | 4.3.1.2 | Approved change requests
[7 empty] | 4.3.1.3 | Enterprise environmental factors
[7 empty] | 4.3.1.4 | Organizational process assets
[6 empty] | T | 4.3.2.1 | Expert judgment
[7 empty] | 4.3.2.1 | Project management information system
[7 empty] | 4.3.2.1 | Meetings
[6 empty] | O | 4.3.3.1 | Deliverables
[7 empty] | 4.3.3.2 | Work performance data
[7 empty] | 4.3.3.3 | Change requests
[7 empty] | 4.3.3.4 | Project management plan updates
[7 empty] | 4.3.3.5 | Project documents updates
|  |  | M | 4.4 | 4.4 Monitor and Control Project Work | I | 4.4.1.1 | Project management plan
[7 empty] | 4.4.1.2 | Schedule forecasts
[7 empty] | 4.4.1.3 | Cost forecasts
[7 empty] | 4.4.1.4 | Validated changes
[7 empty] | 4.4.1.5 | Work performance information
[7 empty] | 4.4.1.6 | Enterprise environmental factors
[7 empty] | 4.4.1.7 | Organizational process assets
[6 empty] | T | 4.4.2.1 | Expert judgment
[7 empty] | 4.4.2.2 | Analytical techniques
[7 empty] | 4.4.2.3 | Project management information system
[7 empty] | 4.4.2.4 | Meetings
[6 empty] | O | 4.4.3.1 | Change requests
[7 empty] | 4.4.3.2 | Work performance reports
[7 empty] | 4.4.3.3 | Project management plan updates
[7 empty] | 4.4.3.4 | Project documents updates
|  |  |  | 4.5 | 4.5 Perform Integrated Change Control | I | 4.5.1.1 | Project management plan
[7 empty] | 4.5.1.2 | Work performance reports
[7 empty] | 4.5.1.3 | Change requests
[7 empty] | 4.5.1.4 | Enterprise environmental factors
[7 empty] | 4.5.1.5 | Organizational process assets
[6 empty] | T | 4.5.2.1 | Expert judgment
[7 empty] | 4.5.2.2 | Meetings
[7 empty] | 4.5.2.3 | Change control tools
[6 empty] | O | 4.5.3.1 | Approved change requests
[7 empty] | 4.5.3.2 | Change log
[7 empty] | 4.5.3.3 | Project management plan updates
[7 empty] | 4.5.3.4 | Project documents updates
|  |  | C | 4.6 | 4.6 Close Project or Phase | I | 4.6.1.1 | Project management plan
[7 empty] | 4.6.1.2 | Accepted deliverables
[7 empty] | 4.6.1.3 | Organizational process assets
[6 empty] | T | 4.6.2.1 | Expert judgment
[7 empty] | 4.6.2.2 | Analytical techniques
[7 empty] | 4.6.2.3 | Meetings
[6 empty] | O | 4.6.3.1 | Final product, service, or result transition
[7 empty] | 4.6.3.2 | Organizational process assets updates
2 | 5 | Project Scope Management | I
|  |  | P | 5.1 | 5.1 Plan Scope Management
|  |  |  | 5.2 | 5.2 Collect Requirements
|  |  |  | 5.3 | 5.3 Define Scope
|  |  |  | 5.4 | 5.4 Create WBS
E
|  |  | M | 5.5 | 5.5 Validate Scope
|  |  |  | 5.6 | 5.6 Control Scope
C
3 | 6 | Project Time Management | I
|  |  | P | 6.1 | 6.1 Plan Schedule Management
|  |  |  | 6.2 | 6.2 Define Activities
|  |  |  | 6.3 | 6.3 Sequence Activities
|  |  |  | 6.4 | 6.4 Estimate Activity Resources
|  |  |  | 6.5 | 6.5 Estimate Activity Durations
|  |  |  | 6.6 | 6.6 Develop Schedule
E
|  |  | M | 6.7 | 6.7 Control Schedule
C
4 | 7 | Project Cost Management | I
|  |  | P | 7.1 | 7.1 Plan Cost Management
|  |  |  | 7.2 | 7.2 Estimate Costs
|  |  |  | 7.3 | 7.3 Determine Budget
E
|  |  | M | 7.4 | 7.4 Control Costs
C
5 | 8 | Project Quality Management | I
|  |  | P | 8.1 | 8.1 Plan Quality Management
|  |  | E | 8.2 | 8.2 Perform Quality Assurance
|  |  | M | 8.3 | 8.3 Control Quality
C
6 | 9 | Project Human Resource Management | I
|  |  | P | 9.1 | 9.1 Plan Human Resource Management
|  |  | E | 9.2 | 9.2 Acquire Project Team
|  |  |  | 9.3 | 9.3 Develop Project Team
|  |  |  | 9.4 | 9.4 Manage Project Team
M
C
7 | 10 | Project Communications Management | I
|  |  | P | 10.1 | 10.1 Plan Communications Management
|  |  | E | 10.2 | 10.2 Manage Communications
|  |  | M | 10.3 | 10.3 Control Communications
C
8 | 11 | Project Risk Management | I
|  |  | P | 11.1 | 11.1 Plan Risk Management
|  |  |  | 11.2 | 11.2 Identify Risks
|  |  |  | 11.3 | 11.3 Perform Qualitative Risk Analysis
|  |  |  | 11.4 | 11.4 Perform Quantitative Risk Analysis
|  |  |  | 11.5 | 11.5 Plan Risk Responses
E
|  |  | M | 11.6 | 11.6 Control Risks
C
9 | 12 | Project Procurement Management | I
|  |  | P | 12.1 | 12.1 Plan Procurement Management
|  |  | E | 12.2 | 12.2 Conduct Procurements
|  |  | M | 12.3 | 12.3 Control Procurements
|  |  | C | 12.4 | 12.4 Close Procurements
10 | 13 | Project Stakeholder Management | I | 13.1 | 13.1 Identify Stakeholders
|  |  | P | 13.2 | 13.2 Plan Stakeholder Management
|  |  | E | 13.3 | 13.3 Manage Stakeholder Engagement
|  |  | M | 13.4 | 13.4 Control Stakeholder Engagement
C
| 10 |  |  | 47

## Project Risk Mgt
# | PMBOK # | Knowlwdgee Area | Process Gourp | Process # | Process | Process Flow
1 | 4 | Project Integration Management | I | 4.1 | 4.1 Develop Project Charter | I | 4.1.1.1 | Project statement of work
[7 empty] | 4.1.1.2 | Business case
[7 empty] | 4.1.1.3 | Agreements
[7 empty] | 4.1.1.4 | Enterprise environmental factors
[7 empty] | 4.1.1.5 | Organizational process assets
[6 empty] | T | 4.1.2.1 | Expert judgment
[7 empty] | 4.1.2.2 | Facilitation techniques
[6 empty] | O | 4.1.3.1 | Project charter
|  |  | P | 4.2 | 4.2 Develop Project Management Plan | I | 4.2.1.1 | Project charter
[7 empty] | 4.2.1.2 | Outputs from other processes
[7 empty] | 4.2.1.3 | Enterprise environmental factors
[7 empty] | 4.2.1.4 | Organizational process assets
[6 empty] | T | 4.2.2.1 | Expert judgment
[7 empty] | 4.2.2.2 | Facilitation techniques
[6 empty] | O | 4.2.3.1 | Project management plan
|  |  | E | 4.3 | 4.3 Direct and Manage Project Work | I | 4.3.1.1 | Project management plan
[7 empty] | 4.3.1.2 | Approved change requests
[7 empty] | 4.3.1.3 | Enterprise environmental factors
[7 empty] | 4.3.1.4 | Organizational process assets
[6 empty] | T | 4.3.2.1 | Expert judgment
[7 empty] | 4.3.2.1 | Project management information system
[7 empty] | 4.3.2.1 | Meetings
[6 empty] | O | 4.3.3.1 | Deliverables
[7 empty] | 4.3.3.2 | Work performance data
[7 empty] | 4.3.3.3 | Change requests
[7 empty] | 4.3.3.4 | Project management plan updates
[7 empty] | 4.3.3.5 | Project documents updates
|  |  | M | 4.4 | 4.4 Monitor and Control Project Work | I | 4.4.1.1 | Project management plan
[7 empty] | 4.4.1.2 | Schedule forecasts
[7 empty] | 4.4.1.3 | Cost forecasts
[7 empty] | 4.4.1.4 | Validated changes
[7 empty] | 4.4.1.5 | Work performance information
[7 empty] | 4.4.1.6 | Enterprise environmental factors
[7 empty] | 4.4.1.7 | Organizational process assets
[6 empty] | T | 4.4.2.1 | Expert judgment
[7 empty] | 4.4.2.2 | Analytical techniques
[7 empty] | 4.4.2.3 | Project management information system
[7 empty] | 4.4.2.4 | Meetings
[6 empty] | O | 4.4.3.1 | Change requests
[7 empty] | 4.4.3.2 | Work performance reports
[7 empty] | 4.4.3.3 | Project management plan updates
[7 empty] | 4.4.3.4 | Project documents updates
|  |  |  | 4.5 | 4.5 Perform Integrated Change Control | I | 4.5.1.1 | Project management plan
[7 empty] | 4.5.1.2 | Work performance reports
[7 empty] | 4.5.1.3 | Change requests
[7 empty] | 4.5.1.4 | Enterprise environmental factors
[7 empty] | 4.5.1.5 | Organizational process assets
[6 empty] | T | 4.5.2.1 | Expert judgment
[7 empty] | 4.5.2.2 | Meetings
[7 empty] | 4.5.2.3 | Change control tools
[6 empty] | O | 4.5.3.1 | Approved change requests
[7 empty] | 4.5.3.2 | Change log
[7 empty] | 4.5.3.3 | Project management plan updates
[7 empty] | 4.5.3.4 | Project documents updates
|  |  | C | 4.6 | 4.6 Close Project or Phase | I | 4.6.1.1 | Project management plan
[7 empty] | 4.6.1.2 | Accepted deliverables
[7 empty] | 4.6.1.3 | Organizational process assets
[6 empty] | T | 4.6.2.1 | Expert judgment
[7 empty] | 4.6.2.2 | Analytical techniques
[7 empty] | 4.6.2.3 | Meetings
[6 empty] | O | 4.6.3.1 | Final product, service, or result transition
[7 empty] | 4.6.3.2 | Organizational process assets updates
2 | 5 | Project Scope Management | I
|  |  | P | 5.1 | 5.1 Plan Scope Management
|  |  |  | 5.2 | 5.2 Collect Requirements
|  |  |  | 5.3 | 5.3 Define Scope
|  |  |  | 5.4 | 5.4 Create WBS
E
|  |  | M | 5.5 | 5.5 Validate Scope
|  |  |  | 5.6 | 5.6 Control Scope
C
3 | 6 | Project Time Management | I
|  |  | P | 6.1 | 6.1 Plan Schedule Management
|  |  |  | 6.2 | 6.2 Define Activities
|  |  |  | 6.3 | 6.3 Sequence Activities
|  |  |  | 6.4 | 6.4 Estimate Activity Resources
|  |  |  | 6.5 | 6.5 Estimate Activity Durations
|  |  |  | 6.6 | 6.6 Develop Schedule
E
|  |  | M | 6.7 | 6.7 Control Schedule
C
4 | 7 | Project Cost Management | I
|  |  | P | 7.1 | 7.1 Plan Cost Management
|  |  |  | 7.2 | 7.2 Estimate Costs
|  |  |  | 7.3 | 7.3 Determine Budget
E
|  |  | M | 7.4 | 7.4 Control Costs
C
5 | 8 | Project Quality Management | I
|  |  | P | 8.1 | 8.1 Plan Quality Management
|  |  | E | 8.2 | 8.2 Perform Quality Assurance
|  |  | M | 8.3 | 8.3 Control Quality
C
6 | 9 | Project Human Resource Management | I
|  |  | P | 9.1 | 9.1 Plan Human Resource Management
|  |  | E | 9.2 | 9.2 Acquire Project Team
|  |  |  | 9.3 | 9.3 Develop Project Team
|  |  |  | 9.4 | 9.4 Manage Project Team
M
C
7 | 10 | Project Communications Management | I
|  |  | P | 10.1 | 10.1 Plan Communications Management
|  |  | E | 10.2 | 10.2 Manage Communications
|  |  | M | 10.3 | 10.3 Control Communications
C
8 | 11 | Project Risk Management | I
|  |  | P | 11.1 | 11.1 Plan Risk Management
|  |  |  | 11.2 | 11.2 Identify Risks
|  |  |  | 11.3 | 11.3 Perform Qualitative Risk Analysis
|  |  |  | 11.4 | 11.4 Perform Quantitative Risk Analysis
|  |  |  | 11.5 | 11.5 Plan Risk Responses
E
|  |  | M | 11.6 | 11.6 Control Risks
C
9 | 12 | Project Procurement Management | I
|  |  | P | 12.1 | 12.1 Plan Procurement Management
|  |  | E | 12.2 | 12.2 Conduct Procurements
|  |  | M | 12.3 | 12.3 Control Procurements
|  |  | C | 12.4 | 12.4 Close Procurements
10 | 13 | Project Stakeholder Management | I | 13.1 | 13.1 Identify Stakeholders
|  |  | P | 13.2 | 13.2 Plan Stakeholder Management
|  |  | E | 13.3 | 13.3 Manage Stakeholder Engagement
|  |  | M | 13.4 | 13.4 Control Stakeholder Engagement
C
| 10 |  |  | 47

## Project Procurement Mgt
# | PMBOK # | Knowlwdgee Area | Process Gourp | Process # | Process | Process Flow
1 | 4 | Project Integration Management | I | 4.1 | 4.1 Develop Project Charter | I | 4.1.1.1 | Project statement of work
[7 empty] | 4.1.1.2 | Business case
[7 empty] | 4.1.1.3 | Agreements
[7 empty] | 4.1.1.4 | Enterprise environmental factors
[7 empty] | 4.1.1.5 | Organizational process assets
[6 empty] | T | 4.1.2.1 | Expert judgment
[7 empty] | 4.1.2.2 | Facilitation techniques
[6 empty] | O | 4.1.3.1 | Project charter
|  |  | P | 4.2 | 4.2 Develop Project Management Plan | I | 4.2.1.1 | Project charter
[7 empty] | 4.2.1.2 | Outputs from other processes
[7 empty] | 4.2.1.3 | Enterprise environmental factors
[7 empty] | 4.2.1.4 | Organizational process assets
[6 empty] | T | 4.2.2.1 | Expert judgment
[7 empty] | 4.2.2.2 | Facilitation techniques
[6 empty] | O | 4.2.3.1 | Project management plan
|  |  | E | 4.3 | 4.3 Direct and Manage Project Work | I | 4.3.1.1 | Project management plan
[7 empty] | 4.3.1.2 | Approved change requests
[7 empty] | 4.3.1.3 | Enterprise environmental factors
[7 empty] | 4.3.1.4 | Organizational process assets
[6 empty] | T | 4.3.2.1 | Expert judgment
[7 empty] | 4.3.2.1 | Project management information system
[7 empty] | 4.3.2.1 | Meetings
[6 empty] | O | 4.3.3.1 | Deliverables
[7 empty] | 4.3.3.2 | Work performance data
[7 empty] | 4.3.3.3 | Change requests
[7 empty] | 4.3.3.4 | Project management plan updates
[7 empty] | 4.3.3.5 | Project documents updates
|  |  | M | 4.4 | 4.4 Monitor and Control Project Work | I | 4.4.1.1 | Project management plan
[7 empty] | 4.4.1.2 | Schedule forecasts
[7 empty] | 4.4.1.3 | Cost forecasts
[7 empty] | 4.4.1.4 | Validated changes
[7 empty] | 4.4.1.5 | Work performance information
[7 empty] | 4.4.1.6 | Enterprise environmental factors
[7 empty] | 4.4.1.7 | Organizational process assets
[6 empty] | T | 4.4.2.1 | Expert judgment
[7 empty] | 4.4.2.2 | Analytical techniques
[7 empty] | 4.4.2.3 | Project management information system
[7 empty] | 4.4.2.4 | Meetings
[6 empty] | O | 4.4.3.1 | Change requests
[7 empty] | 4.4.3.2 | Work performance reports
[7 empty] | 4.4.3.3 | Project management plan updates
[7 empty] | 4.4.3.4 | Project documents updates
|  |  |  | 4.5 | 4.5 Perform Integrated Change Control | I | 4.5.1.1 | Project management plan
[7 empty] | 4.5.1.2 | Work performance reports
[7 empty] | 4.5.1.3 | Change requests
[7 empty] | 4.5.1.4 | Enterprise environmental factors
[7 empty] | 4.5.1.5 | Organizational process assets
[6 empty] | T | 4.5.2.1 | Expert judgment
[7 empty] | 4.5.2.2 | Meetings
[7 empty] | 4.5.2.3 | Change control tools
[6 empty] | O | 4.5.3.1 | Approved change requests
[7 empty] | 4.5.3.2 | Change log
[7 empty] | 4.5.3.3 | Project management plan updates
[7 empty] | 4.5.3.4 | Project documents updates
|  |  | C | 4.6 | 4.6 Close Project or Phase | I | 4.6.1.1 | Project management plan
[7 empty] | 4.6.1.2 | Accepted deliverables
[7 empty] | 4.6.1.3 | Organizational process assets
[6 empty] | T | 4.6.2.1 | Expert judgment
[7 empty] | 4.6.2.2 | Analytical techniques
[7 empty] | 4.6.2.3 | Meetings
[6 empty] | O | 4.6.3.1 | Final product, service, or result transition
[7 empty] | 4.6.3.2 | Organizational process assets updates
2 | 5 | Project Scope Management | I
|  |  | P | 5.1 | 5.1 Plan Scope Management
|  |  |  | 5.2 | 5.2 Collect Requirements
|  |  |  | 5.3 | 5.3 Define Scope
|  |  |  | 5.4 | 5.4 Create WBS
E
|  |  | M | 5.5 | 5.5 Validate Scope
|  |  |  | 5.6 | 5.6 Control Scope
C
3 | 6 | Project Time Management | I
|  |  | P | 6.1 | 6.1 Plan Schedule Management
|  |  |  | 6.2 | 6.2 Define Activities
|  |  |  | 6.3 | 6.3 Sequence Activities
|  |  |  | 6.4 | 6.4 Estimate Activity Resources
|  |  |  | 6.5 | 6.5 Estimate Activity Durations
|  |  |  | 6.6 | 6.6 Develop Schedule
E
|  |  | M | 6.7 | 6.7 Control Schedule
C
4 | 7 | Project Cost Management | I
|  |  | P | 7.1 | 7.1 Plan Cost Management
|  |  |  | 7.2 | 7.2 Estimate Costs
|  |  |  | 7.3 | 7.3 Determine Budget
E
|  |  | M | 7.4 | 7.4 Control Costs
C
5 | 8 | Project Quality Management | I
|  |  | P | 8.1 | 8.1 Plan Quality Management
|  |  | E | 8.2 | 8.2 Perform Quality Assurance
|  |  | M | 8.3 | 8.3 Control Quality
C
6 | 9 | Project Human Resource Management | I
|  |  | P | 9.1 | 9.1 Plan Human Resource Management
|  |  | E | 9.2 | 9.2 Acquire Project Team
|  |  |  | 9.3 | 9.3 Develop Project Team
|  |  |  | 9.4 | 9.4 Manage Project Team
M
C
7 | 10 | Project Communications Management | I
|  |  | P | 10.1 | 10.1 Plan Communications Management
|  |  | E | 10.2 | 10.2 Manage Communications
|  |  | M | 10.3 | 10.3 Control Communications
C
8 | 11 | Project Risk Management | I
|  |  | P | 11.1 | 11.1 Plan Risk Management
|  |  |  | 11.2 | 11.2 Identify Risks
|  |  |  | 11.3 | 11.3 Perform Qualitative Risk Analysis
|  |  |  | 11.4 | 11.4 Perform Quantitative Risk Analysis
|  |  |  | 11.5 | 11.5 Plan Risk Responses
E
|  |  | M | 11.6 | 11.6 Control Risks
C
9 | 12 | Project Procurement Management | I
|  |  | P | 12.1 | 12.1 Plan Procurement Management
|  |  | E | 12.2 | 12.2 Conduct Procurements
|  |  | M | 12.3 | 12.3 Control Procurements
|  |  | C | 12.4 | 12.4 Close Procurements
10 | 13 | Project Stakeholder Management | I | 13.1 | 13.1 Identify Stakeholders
|  |  | P | 13.2 | 13.2 Plan Stakeholder Management
|  |  | E | 13.3 | 13.3 Manage Stakeholder Engagement
|  |  | M | 13.4 | 13.4 Control Stakeholder Engagement
C
| 10 |  |  | 47

## Project Stakeholder Mgt
# | PMBOK # | Knowlwdgee Area | Process Gourp | Process # | Process | Process Flow
1 | 4 | Project Integration Management | I | 4.1 | 4.1 Develop Project Charter | I | 4.1.1.1 | Project statement of work
[7 empty] | 4.1.1.2 | Business case
[7 empty] | 4.1.1.3 | Agreements
[7 empty] | 4.1.1.4 | Enterprise environmental factors
[7 empty] | 4.1.1.5 | Organizational process assets
[6 empty] | T | 4.1.2.1 | Expert judgment
[7 empty] | 4.1.2.2 | Facilitation techniques
[6 empty] | O | 4.1.3.1 | Project charter
|  |  | P | 4.2 | 4.2 Develop Project Management Plan | I | 4.2.1.1 | Project charter
[7 empty] | 4.2.1.2 | Outputs from other processes
[7 empty] | 4.2.1.3 | Enterprise environmental factors
[7 empty] | 4.2.1.4 | Organizational process assets
[6 empty] | T | 4.2.2.1 | Expert judgment
[7 empty] | 4.2.2.2 | Facilitation techniques
[6 empty] | O | 4.2.3.1 | Project management plan
|  |  | E | 4.3 | 4.3 Direct and Manage Project Work | I | 4.3.1.1 | Project management plan
[7 empty] | 4.3.1.2 | Approved change requests
[7 empty] | 4.3.1.3 | Enterprise environmental factors
[7 empty] | 4.3.1.4 | Organizational process assets
[6 empty] | T | 4.3.2.1 | Expert judgment
[7 empty] | 4.3.2.1 | Project management information system
[7 empty] | 4.3.2.1 | Meetings
[6 empty] | O | 4.3.3.1 | Deliverables
[7 empty] | 4.3.3.2 | Work performance data
[7 empty] | 4.3.3.3 | Change requests
[7 empty] | 4.3.3.4 | Project management plan updates
[7 empty] | 4.3.3.5 | Project documents updates
|  |  | M | 4.4 | 4.4 Monitor and Control Project Work | I | 4.4.1.1 | Project management plan
[7 empty] | 4.4.1.2 | Schedule forecasts
[7 empty] | 4.4.1.3 | Cost forecasts
[7 empty] | 4.4.1.4 | Validated changes
[7 empty] | 4.4.1.5 | Work performance information
[7 empty] | 4.4.1.6 | Enterprise environmental factors
[7 empty] | 4.4.1.7 | Organizational process assets
[6 empty] | T | 4.4.2.1 | Expert judgment
[7 empty] | 4.4.2.2 | Analytical techniques
[7 empty] | 4.4.2.3 | Project management information system
[7 empty] | 4.4.2.4 | Meetings
[6 empty] | O | 4.4.3.1 | Change requests
[7 empty] | 4.4.3.2 | Work performance reports
[7 empty] | 4.4.3.3 | Project management plan updates
[7 empty] | 4.4.3.4 | Project documents updates
|  |  |  | 4.5 | 4.5 Perform Integrated Change Control | I | 4.5.1.1 | Project management plan
[7 empty] | 4.5.1.2 | Work performance reports
[7 empty] | 4.5.1.3 | Change requests
[7 empty] | 4.5.1.4 | Enterprise environmental factors
[7 empty] | 4.5.1.5 | Organizational process assets
[6 empty] | T | 4.5.2.1 | Expert judgment
[7 empty] | 4.5.2.2 | Meetings
[7 empty] | 4.5.2.3 | Change control tools
[6 empty] | O | 4.5.3.1 | Approved change requests
[7 empty] | 4.5.3.2 | Change log
[7 empty] | 4.5.3.3 | Project management plan updates
[7 empty] | 4.5.3.4 | Project documents updates
|  |  | C | 4.6 | 4.6 Close Project or Phase | I | 4.6.1.1 | Project management plan
[7 empty] | 4.6.1.2 | Accepted deliverables
[7 empty] | 4.6.1.3 | Organizational process assets
[6 empty] | T | 4.6.2.1 | Expert judgment
[7 empty] | 4.6.2.2 | Analytical techniques
[7 empty] | 4.6.2.3 | Meetings
[6 empty] | O | 4.6.3.1 | Final product, service, or result transition
[7 empty] | 4.6.3.2 | Organizational process assets updates
2 | 5 | Project Scope Management | I
|  |  | P | 5.1 | 5.1 Plan Scope Management
|  |  |  | 5.2 | 5.2 Collect Requirements
|  |  |  | 5.3 | 5.3 Define Scope
|  |  |  | 5.4 | 5.4 Create WBS
E
|  |  | M | 5.5 | 5.5 Validate Scope
|  |  |  | 5.6 | 5.6 Control Scope
C
3 | 6 | Project Time Management | I
|  |  | P | 6.1 | 6.1 Plan Schedule Management
|  |  |  | 6.2 | 6.2 Define Activities
|  |  |  | 6.3 | 6.3 Sequence Activities
|  |  |  | 6.4 | 6.4 Estimate Activity Resources
|  |  |  | 6.5 | 6.5 Estimate Activity Durations
|  |  |  | 6.6 | 6.6 Develop Schedule
E
|  |  | M | 6.7 | 6.7 Control Schedule
C
4 | 7 | Project Cost Management | I
|  |  | P | 7.1 | 7.1 Plan Cost Management
|  |  |  | 7.2 | 7.2 Estimate Costs
|  |  |  | 7.3 | 7.3 Determine Budget
E
|  |  | M | 7.4 | 7.4 Control Costs
C
5 | 8 | Project Quality Management | I
|  |  | P | 8.1 | 8.1 Plan Quality Management
|  |  | E | 8.2 | 8.2 Perform Quality Assurance
|  |  | M | 8.3 | 8.3 Control Quality
C
6 | 9 | Project Human Resource Management | I
|  |  | P | 9.1 | 9.1 Plan Human Resource Management
|  |  | E | 9.2 | 9.2 Acquire Project Team
|  |  |  | 9.3 | 9.3 Develop Project Team
|  |  |  | 9.4 | 9.4 Manage Project Team
M
C
7 | 10 | Project Communications Management | I
|  |  | P | 10.1 | 10.1 Plan Communications Management
|  |  | E | 10.2 | 10.2 Manage Communications
|  |  | M | 10.3 | 10.3 Control Communications
C
8 | 11 | Project Risk Management | I
|  |  | P | 11.1 | 11.1 Plan Risk Management
|  |  |  | 11.2 | 11.2 Identify Risks
|  |  |  | 11.3 | 11.3 Perform Qualitative Risk Analysis
|  |  |  | 11.4 | 11.4 Perform Quantitative Risk Analysis
|  |  |  | 11.5 | 11.5 Plan Risk Responses
E
|  |  | M | 11.6 | 11.6 Control Risks
C
9 | 12 | Project Procurement Management | I
|  |  | P | 12.1 | 12.1 Plan Procurement Management
|  |  | E | 12.2 | 12.2 Conduct Procurements
|  |  | M | 12.3 | 12.3 Control Procurements
|  |  | C | 12.4 | 12.4 Close Procurements
10 | 13 | Project Stakeholder Management | I | 13.1 | 13.1 Identify Stakeholders
|  |  | P | 13.2 | 13.2 Plan Stakeholder Management
|  |  | E | 13.3 | 13.3 Manage Stakeholder Engagement
|  |  | M | 13.4 | 13.4 Control Stakeholder Engagement
C
| 10 |  |  | 47