## CPM
0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Prepare Room
Paint Trim
Paint Ceiling
Paint Walls
Paint walls 2nd coat
Clean UP

## EV
0 | days >> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| Cost | [5 empty] | Budget | Planned | Actual
Prepare Room | 200 | 100 | 100 |  |  |  | How much MONEY? | 1250 | 1200
[7 empty] | For WHAT? | 1250 | 950
Paint Trim | 150 |  |  | 75 | 75 |  | by WHEN? | 5th day | 5th Day
Paint Ceiling | 450 |  |  | 150 | 150 | 150
Paint Walls | 600 |  |  | 150 | 150 | 150 | 150
Paint walls 2nd coat | 200 | [6 empty] | 100 | 100
Clean UP | 100 | [8 empty] | 50 | 50
Project | 1700 | 100 | 100 | 375 | 375 | 300 | 150 | 100 | 100 | 50 | 50
Planned Value | PV | 100 | 200 | 575 | 950 | 1250 | 1400 | 1500 | 1600 | 1650 | 1700 | BAC - Budget At Completion
Earned Value | EV | 0 |  |  |  | 950
Actual Cost | AC | 100 | 190 | 700 | 1050 | 1000
How much money? | Cost
For what? | Scope
By when? | Time
Schedule Variance | SV = EV - PV |  |  |  |  | -300
Cost Variance | CV = EV - AC |  |  |  |  | -50
Sch Performance Index | SPI = EV / PV |  |  |  |  | 0.76
Cost Performance Index | CPI = EV / AC |  |  |  |  | 0.95
EAC | = AC + [(BAC - EV)/Tcpi] |  |  |  | Tcpi = To Complete Performance Index
In short Tcpi means Expected CPI or Expected Cost Efficiency
| = AC + [(BAC - EV)/cpi*spi] |  |  |  |  | 1038.7812
| = AC + [(BAC - EV)/0.76*0.95] |  |  |  |  | 0.722
1789.4737
0.052353
750

## Forcasting
As on 4th Month |  | What is ths expected / Forecasted / Predicted TOTAL at the End of the project
PV | 3000 | Estimate At Completion
EV | 2400 | EAC = ?
AC | 2800 | EAC = | Actual Spent So Far + | Cost of Remaining Work
BAC | 5000 | EAC = | AC + | Cost of (Total Planned Work - Total Done Work)
SPI | 0.8 | EAC = | AC + | Cost of (BAC - EV)
CPI | 0.85714 | EAC = | AC + | [(BAC - EV) / Expected CPI]
SV | -600 | EAC = | AC + | [(BAC - EV) / T.CPI]
CV | -400 |  |  | If T.CPI is 0.5
|  |  | 2800 + | [(5000 - 2400) / 0.5]
|  |  | 2800 + | 2600/ 0.5
|  | EAC = | 2800 + | 5200 | 8000
|  | EAC = | AC + | [(BAC - EV) / Expected CPI]
At current performance i.e. T-CPI = CPI = 0.86
|  |  | 2800 + | 2600/ 0.86
|  |  | 2800 + | 3023.2558
|  | EAC = | 5823.2558
|  | VAC = | BAC - EAC
-823.2558
|  | T-CPI = | (BAC - EV) / (EAC - AC)

## Sheet1
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Solve Question | 10 | 20 | 30 | 40 | 50
Read Process | 1 | 2 | 3 | 4 | 5
min |  |  |  |  | 100
min |  |  |  |  | 150
[5 empty] | 100 | PV for Q
[5 empty] | 300 | PV for Pr
Q EV |  |  |  |  | 45
Process EV |  |  |  |  | 4
[5 empty] | 90 | EV for Q
[5 empty] | 240 | EV for Pr
[5 empty] | 100 | AC fo Q
[5 empty] | 250 | AC for Pr
SV for Q = EV-PV |  |  |  |  | -10
SV for P = EV-PV |  |  |  |  | -60
SV of WP |  |  |  |  | -70

## Sheet2
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Process | 1 | 1 | 1 | 1 | 1 | 1 | 1
PV Process | 1 | 2 | 3 | 4 | 5 | 6 | 7
[5 empty] | 125 | PV
1250
3
[5 empty] | 75 | EV
750
| 30 | 40 | 20 | 25 | 130 | AC
1300
[5 empty] | 0.6 | SPI = EV/PV
[5 empty] | 0.57692 | CPI = EV/AC
[5 empty] | -50 | SV = EV-PV
[5 empty] | -55 | CV = EV-AC
5.8333

## Sheet5
Future | Not Ok | Communication | Time; Quality
| Ok | Cost ; Scope; Staeholders | Risk; HR ; Procurement
|  | OK | Not Ok
Present